## Заходи
№ п/п | Назва ОСР | Назва заходу | Головний виконавець | Результати моніторингу (останні) | Відмітка про виконання | % виконаних заходів (повністю та частково) | Оцінка досягнення ОСР
1.1. | ОСР 1.1.1.1 Studies aimed at ascertaining the overall indicators and causes of corruption in Ukraine, as well as measurements of experiences and perception of corruption by the population are undertaken regularly | 1.1.1.1.1. Organizing an annual (in the second half of each year) standardized survey on corruption in Ukraine according to the methodology approved by the National Agency on Corruption Prevention | National Agency on Corruption Prevention | The measure was implemented on time and in full | Implemented | 100% 3/3 | 0.0%
1.2. |  | 1.1.1.1.2. Organizing an expert survey on the assessment of the level of corruption in Ukraine according to the methodology approved by the National Agency, in 2023 and 2025 | National Agency on Corruption Prevention | The measure was implemented on time and in full | Implemented
1.3. |  | 1.1.1.1.3. Updating the Methodology of the Standardized Survey on Corruption in Ukraine, approved by an order of the National Agency, taking into account changes in the socio-political situation and the results of recent studies on corrupt practices in the areas covered by the standardized survey | National Agency on Corruption Prevention | The measure was implemented on time and in full | Implemented
2.1. | ОСР 1.1.1.2 A single unified system for gathering, consolidating, and visualizing statistical data prescribed by Part 2 of Article 183 of the Law of Ukraine On Prevention of Corruption (hereinafter “the Law”) on the performance of the National Agency, the National Anticorruption Bureau of Ukraine, the State Bureau of Investigations, ARMA, the National Police of Ukraine, the prosecutorial authorities, courts and other government agencies has been implemented | 1.1.1.2.1. Defining the procedure by which the National Anticorruption Bureau, the State Bureau of Investigations, the Asset Recovery and Management Agency, the National Police, prosecutorial authorities, courts, and other government agencies shall furnish information prescribed by Article 183 of the Law to the National Agency | National Agency on Corruption Prevention | The measure was implemented on time and in full | Implemented | 100% 10/10 | 0.0%
2.2. |  | 1.1.1.2.2.(7) Annual submission (by February 15) by specially authorized anticorruption entities and actors implementing the 2023-2025 State Anticorruption Program (hereinafter “the Program”) of statistical data on the results of their work to the National Agency, with mandatory inclusion of data specified in Part 2 of Article 183 of the Law | Economic Security Bureau of Ukraine | The measure was implemented on time and in full | Implemented
2.3. |  | 1.1.1.2.2.(8) Annual submission (by February 15) by specially authorized anticorruption entities and actors implementing the 2023-2025 State Anticorruption Program (hereinafter “the Program”) of statistical data on the results of their work to the National Agency, with mandatory inclusion of data specified in Part 2 of Article 183 of the Law | Security Service of Ukraine | The measure was implemented on time, but partially | Partially implemented
2.4. |  | 1.1.1.2.2.(6) Annual submission (by February 15) by specially authorized anticorruption entities and actors implementing the 2023-2025 State Anticorruption Program (hereinafter “the Program”) of statistical data on the results of their work to the National Agency, with mandatory inclusion of data specified in Part 2 of Article 183 of the Law | State Judicial Administration of Ukraine | The measure was implemented on time and in full | Implemented
2.5. |  | 1.1.1.2.2.(5) Annual submission (by February 15) by specially authorized anticorruption entities and actors implementing the 2023-2025 State Anticorruption Program (hereinafter “the Program”) of statistical data on the results of their work to the National Agency, with mandatory inclusion of data specified in Part 2 of Article 183 of the Law | Prosecutor General’s Office of Ukraine | The measure was implemented on time and in full | Implemented
2.6. |  | 1.1.1.2.2.(4) Annual submission (by February 15) by specially authorized anticorruption entities and actors implementing the 2023-2025 State Anticorruption Program (hereinafter “the Program”) of statistical data on the results of their work to the National Agency, with mandatory inclusion of data specified in Part 2 of Article 183 of the Law | National Police of Ukraine | The measure was implemented on time and in full | Implemented
2.7. |  | 1.1.1.2.2.(3) Annual submission (by February 15) by specially authorized anticorruption entities and actors implementing the 2023-2025 State Anticorruption Program (hereinafter “the Program”) of statistical data on the results of their work to the National Agency, with mandatory inclusion of data specified in Part 2 of Article 183 of the Law | Asset Recovery and Management Agency | The measure was implemented on time and in full | Implemented
2.8. |  | 1.1.1.2.2.(2) Annual submission (by February 15) by specially authorized anticorruption entities and actors implementing the 2023-2025 State Anticorruption Program (hereinafter “the Program”) of statistical data on the results of their work to the National Agency, with mandatory inclusion of data specified in Part 2 of Article 183 of the Law | State Bureau of Investigation | The measure was implemented on time and in full | Implemented
2.9. |  | 1.1.1.2.2.(1) Annual submission (by February 15) by specially authorized anticorruption entities and actors implementing the 2023-2025 State Anticorruption Program (hereinafter “the Program”) of statistical data on the results of their work to the National Agency, with mandatory inclusion of data specified in Part 2 of Article 183 of the Law | National Anti-Corruption Bureau of Ukraine | The measure was implemented on time and in full | Implemented
2.10. |  | 1.1.1.2.3. Gathering, consolidating, and visualizing (by April 15) statistical data submitted by specially authorized anticorruption entities and other government agencies pursuant to Article 183 of the Law, on the official website of the National Agency (following the creation of the information system for monitoring the implementation of the state anticorruption policy (hereinafter “the information monitoring system”) — within a dedicated segment of this system) | National Agency on Corruption Prevention | The measure was implemented on time and in full | Implemented
3.1. | ОСР 1.1.1.3 While shaping and implementing the state policy, the National Agency, the Cabinet of Ministers of Ukraine, the Parliament of Ukraine, and other government agencies use official statistical data, the results of assessment of corruption risks, and summaries of the most widespread corrupt practices, and also consider the results of opinion polls and other studies | 1.1.1.3.1. Creating a dedicated page on the official website of the National Agency to reflect key statistics on the progress made in combating corruption or corruption-related crimes | National Agency on Corruption Prevention | The measure was implemented on time and in full | Implemented | 62.5% 5/8 | 0.0%
3.2. |  | 1.1.1.3.2. Drafting and submitting to the Cabinet of Ministers of Ukraine a draft law proposing amendments to the Law, under which the National Agency would be tasked with launching and maintaining on an ongoing basis the Unified Nationwide Register “Status of the Fight Against Corruption-Related Administrative Offenses” as part of the information monitoring system | National Agency on Corruption Prevention | The measure has not been implemented | Not implemented
3.3. |  | 1.1.1.3.3. Drafting and approving the Procedure by which the National Agency shall maintain the Unified Nationwide Register “Status of the Fight Against Corruption-Related Administrative Offenses”, as well as the forms to be used by agencies of the National Police, prosecutorial authorities, and the State Judicial Administration (SJA) to submit the relevant information | National Agency on Corruption Prevention |  | Не підлягають виконанню
3.4. |  | 1.1.1.3.4. Granting unrestricted round-the-clock access to the Unified Nationwide Register “Status of the Fight Against Corruption-Related Administrative Offenses” through the information monitoring system | National Agency on Corruption Prevention |  | Не підлягають виконанню
3.5. |  | 1.1.1.3.5. Creating a dedicated page—“Library of Major Opinion Polls”—on the official website of the National Agency, to publish opinion polls conducted in Ukraine over the past decade, which shed light on specific issues of perception, prevalence, and causes of corruption, as well as the effectiveness of efforts to prevent and combat corruption | National Agency on Corruption Prevention | The measure was implemented on time and in full | Implemented
3.6. |  | 1.1.1.3.6. Creating a dedicated page—“Library of Fundamental Analytical Studies”—on the official website of the National Agency, to publish the most comprehensive and fundamental studies (monographs, theses, textbooks, collected works, etc.) of recent years dealing with the issues of preventing and combating corruption | National Agency on Corruption Prevention | The measure was implemented on time and in full | Implemented
3.7. |  | 1.1.1.3.7. Creating a dedicated page—“Academic Periodicals”—on the official website of the National Agency, to publish academic articles of recent years devoted to the issues of preventing and combating corruption | National Agency on Corruption Prevention | The measure was implemented on time and in full | Implemented
3.8. |  | 1.1.1.3.8. Submitting key information relating to the issues of preventing and combating corruption every year to the Cabinet of Ministers of Ukraine, the Parliament of Ukraine, the President of Ukraine, the Ukrainian Parliament committee overseeing the issues of combating corruption, the National Council on the Anticorruption Policy, as well as other government agencies, in order to enable these authorities to consider this information while formulating the anticorruption and sectoral policies | National Agency on Corruption Prevention | The measure was implemented on time, but partially | Partially implemented
4.1. | ОСР 1.1.1.4 Information on the progress made in implementing the anticorruption policy is gathered, analyzed, and made public with the use of modern IT tools | 1.1.1.4.1. Creating and launching the information monitoring system | National Agency on Corruption Prevention | The measure was implemented on time and in full | Implemented | 100% 3/3 | 0.0%
4.2. |  | 1.1.1.4.2. Drafting and approving the Regulation on the information system for monitoring the implementation of the state anticorruption policy, which specifically obligates all Program implementing actors to submit a quarterly report (no later than 15 days after the end of the reporting quarter) to the National Agency with information on the progress of implementation of the Program activities by entering this information into the classified section of the information monitoring system | National Agency on Corruption Prevention | The measure was implemented on time and in full | Implemented
4.3. |  | 1.1.1.4.3. Ensuring the population of the information monitoring system with information indicated in Part 1 of Article 184 of the Law | National Agency on Corruption Prevention | The measure was implemented on time and in full | Implemented
5.1. | ОСР 1.1.1.5 Sufficient funding and other essential resources are allocated for the needs of shaping and implementing the anticorruption policy | 1.1.1.5.1. Annually formulating the performance indicators of Budget Program 6331030 “Implementation of Anticorruption Strategies” aimed at implementing the Program activities | National Agency on Corruption Prevention | The measure was implemented on time and in full | Implemented | 77.8% 28/36 | 0.0%
5.2. |  | 1.1.1.5.2. Determining the tentative scope of budget allocations required for the relevant planning year for the implementation of activities of Budget Program 6331030 “Implementation of Anticorruption Strategies” | National Agency on Corruption Prevention | The measure was implemented on time and in full | Implemented
5.3. |  | 1.1.1.5.3. Approving sufficient financial resources within the State Budget of Ukraine for proper implementation of the activities outlined in Budget Program 6331030 “Implementation of Anticorruption Strategies” | Ministry of Finance of Ukraine | The measure was implemented on time and in full | Implemented
5.4. |  | 1.1.1.5.4.(13) Carrying out financial economic calculations of needs (in particular, by developing technical economic justification of developing/modernization of hardware and software) to perform measures indicated in subclauses 1.5.3.1.6, 2.2.2.4.8, 2.2.3.1.1, 2.2.3.1.3, 2.2.3.3.3, 2.2.3.3.4, 2.4.2.3.5, 2.4.3.1.7, 2.4.3.1.9, 2.4.3.1.10, 2.5.1.1.1, 2.5.1.1.2, 2.5.1.2.2–2.5.1.4.2, 2.5.10.3.2, 2.5.10.3.3, 2.7.5.2.2, 2.7.7.1.4, 2.7.7.2.4, 3.3.2.3.4, 3.3.3.8.2 (in particular, while developing budget proposals for 2025) | Economic Security Bureau of Ukraine | The measure has not been implemented | Not implemented
5.5. |  | 1.1.1.5.4.(14) Carrying out financial economic calculations of needs (in particular, by developing technical economic justification of developing/modernization of hardware and software) to perform measures indicated in subclauses 1.5.3.1.6, 2.2.2.4.8, 2.2.3.1.1, 2.2.3.1.3, 2.2.3.3.3, 2.2.3.3.4, 2.4.2.3.5, 2.4.3.1.7, 2.4.3.1.9, 2.4.3.1.10, 2.5.1.1.1, 2.5.1.1.2, 2.5.1.2.2–2.5.1.4.2, 2.5.10.3.2, 2.5.10.3.3, 2.7.5.2.2, 2.7.7.1.4, 2.7.7.2.4, 3.3.2.3.4, 3.3.3.8.2 (in particular, while developing budget proposals for 2025) | Asset Recovery and Management Agency | The measure was implemented on time and in full | Implemented
5.6. |  | 1.1.1.5.4.(15) Carrying out financial economic calculations of needs (in particular, by developing technical economic justification of developing/modernization of hardware and software) to perform measures indicated in subclauses 1.5.3.1.6, 2.2.2.4.8, 2.2.3.1.1, 2.2.3.1.3, 2.2.3.3.3, 2.2.3.3.4, 2.4.2.3.5, 2.4.3.1.7, 2.4.3.1.9, 2.4.3.1.10, 2.5.1.1.1, 2.5.1.1.2, 2.5.1.2.2–2.5.1.4.2, 2.5.10.3.2, 2.5.10.3.3, 2.7.5.2.2, 2.7.7.1.4, 2.7.7.2.4, 3.3.2.3.4, 3.3.3.8.2 (in particular, while developing budget proposals for 2025) | Security Service of Ukraine | The measure has not been implemented | Not implemented
5.7. |  | 1.1.1.5.4.(16) Carrying out financial economic calculations of needs (in particular, by developing technical economic justification of developing/modernization of hardware and software) to perform measures indicated in subclauses 1.5.3.1.6, 2.2.2.4.8, 2.2.3.1.1, 2.2.3.1.3, 2.2.3.3.3, 2.2.3.3.4, 2.4.2.3.5, 2.4.3.1.7, 2.4.3.1.9, 2.4.3.1.10, 2.5.1.1.1, 2.5.1.1.2, 2.5.1.2.2–2.5.1.4.2, 2.5.10.3.2, 2.5.10.3.3, 2.7.5.2.2, 2.7.7.1.4, 2.7.7.2.4, 3.3.2.3.4, 3.3.3.8.2 (in particular, while developing budget proposals for 2025) | State Property Fund of Ukraine | The measure was implemented on time and in full | Implemented
5.8. |  | 1.1.1.5.4.(17) Carrying out financial economic calculations of needs (in particular, by developing technical economic justification of developing/modernization of hardware and software) to perform measures indicated in subclauses 1.5.3.1.6, 2.2.2.4.8, 2.2.3.1.1, 2.2.3.1.3, 2.2.3.3.3, 2.2.3.3.4, 2.4.2.3.5, 2.4.3.1.7, 2.4.3.1.9, 2.4.3.1.10, 2.5.1.1.1, 2.5.1.1.2, 2.5.1.2.2–2.5.1.4.2, 2.5.10.3.2, 2.5.10.3.3, 2.7.5.2.2, 2.7.7.1.4, 2.7.7.2.4, 3.3.2.3.4, 3.3.3.8.2 (in particular, while developing budget proposals for 2025) | Antimonopoly Committee of Ukraine | The measure was implemented on time and in full | Implemented
5.9. |  | 1.1.1.5.4.(18) Carrying out financial economic calculations of needs (in particular, by developing technical economic justification of developing/modernization of hardware and software) to perform measures indicated in subclauses 1.5.3.1.6, 2.2.2.4.8, 2.2.3.1.1, 2.2.3.1.3, 2.2.3.3.3, 2.2.3.3.4, 2.4.2.3.5, 2.4.3.1.7, 2.4.3.1.9, 2.4.3.1.10, 2.5.1.1.1, 2.5.1.1.2, 2.5.1.2.2–2.5.1.4.2, 2.5.10.3.2, 2.5.10.3.3, 2.7.5.2.2, 2.7.7.1.4, 2.7.7.2.4, 3.3.2.3.4, 3.3.3.8.2 (in particular, while developing budget proposals for 2025) | State Statistics Service of Ukraine | The measure was implemented on time and in full | Implemented
5.10. |  | 1.1.1.5.4.(19) Carrying out financial economic calculations of needs (in particular, by developing technical economic justification of developing/modernization of hardware and software) to perform measures indicated in subclauses 1.5.3.1.6, 2.2.2.4.8, 2.2.3.1.1, 2.2.3.1.3, 2.2.3.3.3, 2.2.3.3.4, 2.4.2.3.5, 2.4.3.1.7, 2.4.3.1.9, 2.4.3.1.10, 2.5.1.1.1, 2.5.1.1.2, 2.5.1.2.2–2.5.1.4.2, 2.5.10.3.2, 2.5.10.3.3, 2.7.5.2.2, 2.7.7.1.4, 2.7.7.2.4, 3.3.2.3.4, 3.3.3.8.2 (in particular, while developing budget proposals for 2025) | Administration of State Service of Special Commucations and Information Protection of Ukraine | The measure has not been implemented | Not implemented
5.11. |  | 1.1.1.5.4.(21) Carrying out financial economic calculations of needs (in particular, by developing technical economic justification of developing/modernization of hardware and software) to perform measures indicated in subclauses 1.5.3.1.6, 2.2.2.4.8, 2.2.3.1.1, 2.2.3.1.3, 2.2.3.3.3, 2.2.3.3.4, 2.4.2.3.5, 2.4.3.1.7, 2.4.3.1.9, 2.4.3.1.10, 2.5.1.1.1, 2.5.1.1.2, 2.5.1.2.2–2.5.1.4.2, 2.5.10.3.2, 2.5.10.3.3, 2.7.5.2.2, 2.7.7.1.4, 2.7.7.2.4, 3.3.2.3.4, 3.3.3.8.2 (in particular, while developing budget proposals for 2025) | State Regulatory Service of Ukraine | The measure was implemented on time and in full | Implemented
5.12. |  | 1.1.1.5.4.(22) Carrying out financial economic calculations of needs (in particular, by developing technical economic justification of developing/modernization of hardware and software) to perform measures indicated in subclauses 1.5.3.1.6, 2.2.2.4.8, 2.2.3.1.1, 2.2.3.1.3, 2.2.3.3.3, 2.2.3.3.4, 2.4.2.3.5, 2.4.3.1.7, 2.4.3.1.9, 2.4.3.1.10, 2.5.1.1.1, 2.5.1.1.2, 2.5.1.2.2–2.5.1.4.2, 2.5.10.3.2, 2.5.10.3.3, 2.7.5.2.2, 2.7.7.1.4, 2.7.7.2.4, 3.3.2.3.4, 3.3.3.8.2 (in particular, while developing budget proposals for 2025) | State Agency for Restoration and Infrastructure Development of Ukraine | The measure was implemented on time and in full | Implemented
5.13. |  | 1.1.1.5.4.(23) Carrying out financial economic calculations of needs (in particular, by developing technical economic justification of developing/modernization of hardware and software) to perform measures indicated in subclauses 1.5.3.1.6, 2.2.2.4.8, 2.2.3.1.1, 2.2.3.1.3, 2.2.3.3.3, 2.2.3.3.4, 2.4.2.3.5, 2.4.3.1.7, 2.4.3.1.9, 2.4.3.1.10, 2.5.1.1.1, 2.5.1.1.2, 2.5.1.2.2–2.5.1.4.2, 2.5.10.3.2, 2.5.10.3.3, 2.7.5.2.2, 2.7.7.1.4, 2.7.7.2.4, 3.3.2.3.4, 3.3.3.8.2 (in particular, while developing budget proposals for 2025) | National Commission on Securities and Stock Market | The measure was implemented on time and in full | Implemented
5.14. |  | 1.1.1.5.4.(20) Carrying out financial economic calculations of needs (in particular, by developing technical economic justification of developing/modernization of hardware and software) to perform measures indicated in subclauses 1.5.3.1.6, 2.2.2.4.8, 2.2.3.1.1, 2.2.3.1.3, 2.2.3.3.3, 2.2.3.3.4, 2.4.2.3.5, 2.4.3.1.7, 2.4.3.1.9, 2.4.3.1.10, 2.5.1.1.1, 2.5.1.1.2, 2.5.1.2.2–2.5.1.4.2, 2.5.10.3.2, 2.5.10.3.3, 2.7.5.2.2, 2.7.7.1.4, 2.7.7.2.4, 3.3.2.3.4, 3.3.3.8.2 (in particular, while developing budget proposals for 2025) | State Agency of Ukraine for the Development of Melioration, Fisheries and Food Programs | The measure was implemented on time and in full | Implemented
5.15. |  | 1.1.1.5.4.(11) Carrying out financial economic calculations of needs (in particular, by developing technical economic justification of developing/modernization of hardware and software) to perform measures indicated in subclauses 1.5.3.1.6, 2.2.2.4.8, 2.2.3.1.1, 2.2.3.1.3, 2.2.3.3.3, 2.2.3.3.4, 2.4.2.3.5, 2.4.3.1.7, 2.4.3.1.9, 2.4.3.1.10, 2.5.1.1.1, 2.5.1.1.2, 2.5.1.2.2–2.5.1.4.2, 2.5.10.3.2, 2.5.10.3.3, 2.7.5.2.2, 2.7.7.1.4, 2.7.7.2.4, 3.3.2.3.4, 3.3.3.8.2 (in particular, while developing budget proposals for 2025) | National Police of Ukraine | The measure has not been implemented | Not implemented
5.16. |  | 1.1.1.5.4.(12) Carrying out financial economic calculations of needs (in particular, by developing technical economic justification of developing/modernization of hardware and software) to perform measures indicated in subclauses 1.5.3.1.6, 2.2.2.4.8, 2.2.3.1.1, 2.2.3.1.3, 2.2.3.3.3, 2.2.3.3.4, 2.4.2.3.5, 2.4.3.1.7, 2.4.3.1.9, 2.4.3.1.10, 2.5.1.1.1, 2.5.1.1.2, 2.5.1.2.2–2.5.1.4.2, 2.5.10.3.2, 2.5.10.3.3, 2.7.5.2.2, 2.7.7.1.4, 2.7.7.2.4, 3.3.2.3.4, 3.3.3.8.2 (in particular, while developing budget proposals for 2025) | National Anti-Corruption Bureau of Ukraine | The measure has not been implemented | Not implemented
5.17. |  | 1.1.1.5.4.(1) Carrying out financial economic calculations of needs (in particular, by developing technical economic justification of developing/modernization of hardware and software) to perform measures indicated in subclauses 1.5.3.1.6, 2.2.2.4.8, 2.2.3.1.1, 2.2.3.1.3, 2.2.3.3.3, 2.2.3.3.4, 2.4.2.3.5, 2.4.3.1.7, 2.4.3.1.9, 2.4.3.1.10, 2.5.1.1.1, 2.5.1.1.2, 2.5.1.2.2–2.5.1.4.2, 2.5.10.3.2, 2.5.10.3.3, 2.7.5.2.2, 2.7.7.1.4, 2.7.7.2.4, 3.3.2.3.4, 3.3.3.8.2 (in particular, while developing budget proposals for 2025) | National Agency on Corruption Prevention | The measure was implemented on time and in full | Implemented
5.18. |  | 1.1.1.5.4.(2) Carrying out financial economic calculations of needs (in particular, by developing technical economic justification of developing/modernization of hardware and software) to perform measures indicated in subclauses 1.5.3.1.6, 2.2.2.4.8, 2.2.3.1.1, 2.2.3.1.3, 2.2.3.3.3, 2.2.3.3.4, 2.4.2.3.5, 2.4.3.1.7, 2.4.3.1.9, 2.4.3.1.10, 2.5.1.1.1, 2.5.1.1.2, 2.5.1.2.2–2.5.1.4.2, 2.5.10.3.2, 2.5.10.3.3, 2.7.5.2.2, 2.7.7.1.4, 2.7.7.2.4, 3.3.2.3.4, 3.3.3.8.2 (in particular, while developing budget proposals for 2025) | Ministry of Finance of Ukraine | The measure was implemented on time and in full | Implemented
5.19. |  | 1.1.1.5.4.(3) Carrying out financial economic calculations of needs (in particular, by developing technical economic justification of developing/modernization of hardware and software) to perform measures indicated in subclauses 1.5.3.1.6, 2.2.2.4.8, 2.2.3.1.1, 2.2.3.1.3, 2.2.3.3.3, 2.2.3.3.4, 2.4.2.3.5, 2.4.3.1.7, 2.4.3.1.9, 2.4.3.1.10, 2.5.1.1.1, 2.5.1.1.2, 2.5.1.2.2–2.5.1.4.2, 2.5.10.3.2, 2.5.10.3.3, 2.7.5.2.2, 2.7.7.1.4, 2.7.7.2.4, 3.3.2.3.4, 3.3.3.8.2 (in particular, while developing budget proposals for 2025) | Ministry for Communities and Territories Development of Ukraine | The measure was not implemented on time and in full | Implemented
5.20. |  | 1.1.1.5.4.(4) Carrying out financial economic calculations of needs (in particular, by developing technical economic justification of developing/modernization of hardware and software) to perform measures indicated in subclauses 1.5.3.1.6, 2.2.2.4.8, 2.2.3.1.1, 2.2.3.1.3, 2.2.3.3.3, 2.2.3.3.4, 2.4.2.3.5, 2.4.3.1.7, 2.4.3.1.9, 2.4.3.1.10, 2.5.1.1.1, 2.5.1.1.2, 2.5.1.2.2–2.5.1.4.2, 2.5.10.3.2, 2.5.10.3.3, 2.7.5.2.2, 2.7.7.1.4, 2.7.7.2.4, 3.3.2.3.4, 3.3.3.8.2 (in particular, while developing budget proposals for 2025) | Ministry of Justice of Ukraine | The measure was implemented on time and in full | Implemented
5.21. |  | 1.1.1.5.4.(7) Carrying out financial economic calculations of needs (in particular, by developing technical economic justification of developing/modernization of hardware and software) to perform measures indicated in subclauses 1.5.3.1.6, 2.2.2.4.8, 2.2.3.1.1, 2.2.3.1.3, 2.2.3.3.3, 2.2.3.3.4, 2.4.2.3.5, 2.4.3.1.7, 2.4.3.1.9, 2.4.3.1.10, 2.5.1.1.1, 2.5.1.1.2, 2.5.1.2.2–2.5.1.4.2, 2.5.10.3.2, 2.5.10.3.3, 2.7.5.2.2, 2.7.7.1.4, 2.7.7.2.4, 3.3.2.3.4, 3.3.3.8.2 (in particular, while developing budget proposals for 2025) | Ministry of Social Policy, Family and Unity of Ukraine | The measure was implemented on time and in full | Implemented
5.22. |  | 1.1.1.5.4.(8) Carrying out financial economic calculations of needs (in particular, by developing technical economic justification of developing/modernization of hardware and software) to perform measures indicated in subclauses 1.5.3.1.6, 2.2.2.4.8, 2.2.3.1.1, 2.2.3.1.3, 2.2.3.3.3, 2.2.3.3.4, 2.4.2.3.5, 2.4.3.1.7, 2.4.3.1.9, 2.4.3.1.10, 2.5.1.1.1, 2.5.1.1.2, 2.5.1.2.2–2.5.1.4.2, 2.5.10.3.2, 2.5.10.3.3, 2.7.5.2.2, 2.7.7.1.4, 2.7.7.2.4, 3.3.2.3.4, 3.3.3.8.2 (in particular, while developing budget proposals for 2025) | Ministry of Education and Science of Ukraine | The measure was implemented on time and in full | Implemented
5.23. |  | 1.1.1.5.4.(9) Carrying out financial economic calculations of needs (in particular, by developing technical economic justification of developing/modernization of hardware and software) to perform measures indicated in subclauses 1.5.3.1.6, 2.2.2.4.8, 2.2.3.1.1, 2.2.3.1.3, 2.2.3.3.3, 2.2.3.3.4, 2.4.2.3.5, 2.4.3.1.7, 2.4.3.1.9, 2.4.3.1.10, 2.5.1.1.1, 2.5.1.1.2, 2.5.1.2.2–2.5.1.4.2, 2.5.10.3.2, 2.5.10.3.3, 2.7.5.2.2, 2.7.7.1.4, 2.7.7.2.4, 3.3.2.3.4, 3.3.3.8.2 (in particular, while developing budget proposals for 2025) | Prosecutor General’s Office of Ukraine | The measure has not been implemented | Not implemented
5.24. |  | 1.1.1.5.4.(10) Carrying out financial economic calculations of needs (in particular, by developing technical economic justification of developing/modernization of hardware and software) to perform measures indicated in subclauses 1.5.3.1.6, 2.2.2.4.8, 2.2.3.1.1, 2.2.3.1.3, 2.2.3.3.3, 2.2.3.3.4, 2.4.2.3.5, 2.4.3.1.7, 2.4.3.1.9, 2.4.3.1.10, 2.5.1.1.1, 2.5.1.1.2, 2.5.1.2.2–2.5.1.4.2, 2.5.10.3.2, 2.5.10.3.3, 2.7.5.2.2, 2.7.7.1.4, 2.7.7.2.4, 3.3.2.3.4, 3.3.3.8.2 (in particular, while developing budget proposals for 2025) | State Bureau of Investigation | The measure has not been implemented | Not implemented
5.25. |  | 1.1.1.5.4.(5) Carrying out financial economic calculations of needs (in particular, by developing technical economic justification of developing/modernization of hardware and software) to perform measures indicated in subclauses 1.5.3.1.6, 2.2.2.4.8, 2.2.3.1.1, 2.2.3.1.3, 2.2.3.3.3, 2.2.3.3.4, 2.4.2.3.5, 2.4.3.1.7, 2.4.3.1.9, 2.4.3.1.10, 2.5.1.1.1, 2.5.1.1.2, 2.5.1.2.2–2.5.1.4.2, 2.5.10.3.2, 2.5.10.3.3, 2.7.5.2.2, 2.7.7.1.4, 2.7.7.2.4, 3.3.2.3.4, 3.3.3.8.2 (in particular, while developing budget proposals for 2025) | Ministry of Economy, Environment and Agriculture of Ukraine | The measure was implemented on time and in full | Implemented
5.26. |  | 1.1.1.5.5.(8) Carrying out financial economic calculations of needs (in particular, by developing technical economic justification of developing/modernization of hardware and software) to perform measures indicated in subclauses 2.2.1.1.5, 2.2.2.1.3, 2.2.2.2.6, 2.2.2.4.9, 2.5.4.3.3, 2.5.5.1.4, 2.7.1.1.3, 2.7.1.2.3, 2.7.3.3.5, 2.7.3.4.8, due to adoption of regulatory legal acts (in particular, while developing budget proposals for 2025) | State Service of Ukraine for Geodesy, Cartography and Cadastre | The measure was implemented on time, but partially | Partially implemented
5.27. |  | 1.1.1.5.5.(12) Carrying out financial economic calculations of needs (in particular, by developing technical economic justification of developing/modernization of hardware and software) to perform measures indicated in subclauses 2.2.1.1.5, 2.2.2.1.3, 2.2.2.2.6, 2.2.2.4.9, 2.5.4.3.3, 2.5.5.1.4, 2.7.1.1.3, 2.7.1.2.3, 2.7.3.3.5, 2.7.3.4.8, due to adoption of regulatory legal acts (in particular, while developing budget proposals for 2025) | Fund for Social Protection of Persons with Disabilities | The measure was implemented on time, but partially | Partially implemented
5.28. |  | 1.1.1.5.5.(11) Carrying out financial economic calculations of needs (in particular, by developing technical economic justification of developing/modernization of hardware and software) to perform measures indicated in subclauses 2.2.1.1.5, 2.2.2.1.3, 2.2.2.2.6, 2.2.2.4.9, 2.5.4.3.3, 2.5.5.1.4, 2.7.1.1.3, 2.7.1.2.3, 2.7.3.3.5, 2.7.3.4.8, due to adoption of regulatory legal acts (in particular, while developing budget proposals for 2025) | State Enterprise "Medical Procurement of Ukraine" | The measure was implemented on time and in full | Implemented
5.29. |  | 1.1.1.5.5.(10) Carrying out financial economic calculations of needs (in particular, by developing technical economic justification of developing/modernization of hardware and software) to perform measures indicated in subclauses 2.2.1.1.5, 2.2.2.1.3, 2.2.2.2.6, 2.2.2.4.9, 2.5.4.3.3, 2.5.5.1.4, 2.7.1.1.3, 2.7.1.2.3, 2.7.3.3.5, 2.7.3.4.8, due to adoption of regulatory legal acts (in particular, while developing budget proposals for 2025) | National Health Service of Ukraine | The measure was implemented on time and in full | Implemented
5.30. |  | 1.1.1.5.5.(9) Carrying out financial economic calculations of needs (in particular, by developing technical economic justification of developing/modernization of hardware and software) to perform measures indicated in subclauses 2.2.1.1.5, 2.2.2.1.3, 2.2.2.2.6, 2.2.2.4.9, 2.5.4.3.3, 2.5.5.1.4, 2.7.1.1.3, 2.7.1.2.3, 2.7.3.3.5, 2.7.3.4.8, due to adoption of regulatory legal acts (in particular, while developing budget proposals for 2025) | State Regulatory Service of Ukraine | The measure was implemented on time, but partially | Partially implemented
5.31. |  | 1.1.1.5.5.(7) Carrying out financial economic calculations of needs (in particular, by developing technical economic justification of developing/modernization of hardware and software) to perform measures indicated in subclauses 2.2.1.1.5, 2.2.2.1.3, 2.2.2.2.6, 2.2.2.4.9, 2.5.4.3.3, 2.5.5.1.4, 2.7.1.1.3, 2.7.1.2.3, 2.7.3.3.5, 2.7.3.4.8, due to adoption of regulatory legal acts (in particular, while developing budget proposals for 2025) | State Agency of Ukraine for the Development of Melioration, Fisheries and Food Programs | The measure was implemented on time, but partially | Partially implemented
5.32. |  | 1.1.1.5.5.(6) Carrying out financial economic calculations of needs (in particular, by developing technical economic justification of developing/modernization of hardware and software) to perform measures indicated in subclauses 2.2.1.1.5, 2.2.2.1.3, 2.2.2.2.6, 2.2.2.4.9, 2.5.4.3.3, 2.5.5.1.4, 2.7.1.1.3, 2.7.1.2.3, 2.7.3.3.5, 2.7.3.4.8, due to adoption of regulatory legal acts (in particular, while developing budget proposals for 2025) | State Service of Geology and Mineral Resources of Ukraine | The measure was implemented on time and in full | Implemented
5.33. |  | 1.1.1.5.5.(5) Carrying out financial economic calculations of needs (in particular, by developing technical economic justification of developing/modernization of hardware and software) to perform measures indicated in subclauses 2.2.1.1.5, 2.2.2.1.3, 2.2.2.2.6, 2.2.2.4.9, 2.5.4.3.3, 2.5.5.1.4, 2.7.1.1.3, 2.7.1.2.3, 2.7.3.3.5, 2.7.3.4.8, due to adoption of regulatory legal acts (in particular, while developing budget proposals for 2025) | State Forest Resources Agency of Ukraine | Implementation of the measure has not started | Не підлягають виконанню
5.34. |  | 1.1.1.5.5.(4) Carrying out financial economic calculations of needs (in particular, by developing technical economic justification of developing/modernization of hardware and software) to perform measures indicated in subclauses 2.2.1.1.5, 2.2.2.1.3, 2.2.2.2.6, 2.2.2.4.9, 2.5.4.3.3, 2.5.5.1.4, 2.7.1.1.3, 2.7.1.2.3, 2.7.3.3.5, 2.7.3.4.8, due to adoption of regulatory legal acts (in particular, while developing budget proposals for 2025) | Ministry of Health of Ukraine | The measure was implemented on time and in full | Implemented
5.35. |  | 1.1.1.5.5.(3) Carrying out financial economic calculations of needs (in particular, by developing technical economic justification of developing/modernization of hardware and software) to perform measures indicated in subclauses 2.2.1.1.5, 2.2.2.1.3, 2.2.2.2.6, 2.2.2.4.9, 2.5.4.3.3, 2.5.5.1.4, 2.7.1.1.3, 2.7.1.2.3, 2.7.3.3.5, 2.7.3.4.8, due to adoption of regulatory legal acts (in particular, while developing budget proposals for 2025) | Ministry of Social Policy, Family and Unity of Ukraine | The measure was implemented on time, but partially | Partially implemented
5.36. |  | 1.1.1.5.5.(1) Carrying out financial economic calculations of needs (in particular, by developing technical economic justification of developing/modernization of hardware and software) to perform measures indicated in subclauses 2.2.1.1.5, 2.2.2.1.3, 2.2.2.2.6, 2.2.2.4.9, 2.5.4.3.3, 2.5.5.1.4, 2.7.1.1.3, 2.7.1.2.3, 2.7.3.3.5, 2.7.3.4.8, due to adoption of regulatory legal acts (in particular, while developing budget proposals for 2025) | Ministry of Economy, Environment and Agriculture of Ukraine | The measure was implemented on time, but partially | Partially implemented
6.1. | ОСР 1.1.1.6 The coordination of implementation of the anticorruption policy is efficient and effective, particularly owing to the creation of effective mechanisms of cooperation between the anticorruption institutions and other government agencies and local self-government bodies | 1.1.1.6.1. Drafting and approving the Procedure for Coordinating the Implementation of Anti-Сorruption Strategy for 2021-2025, approved by the Law of Ukraine dated June 20, 2022, No. 2322-IX On the Fundamentals of the State Anti-Corruption Policy for 2021-2025 (hereinafter “the Anticorruption Strategy”) and the Program | National Agency on Corruption Prevention | The measure was implemented on time and in full | Implemented | 100% 7/7 | 0.0%
6.2. |  | 1.1.1.6.4. Drafting and approving (by an order of the National Agency) the Regulation on the Coordinating Working Group on the Issues of the Anticorruption Policy (as a consultative and advisory body of the National Agency), which defines the key objectives of this body as follows: 1) facilitating the coordination of the efforts of government agencies towards the implementation of the Anticorruption Strategy and implementation of Program activities; 2) preparing proposals regarding the formulation and implementation of the state anticorruption policy (particularly in matters of improving the regulatory and legislative framework). | National Agency on Corruption Prevention | The measure was not implemented on time and in full | Implemented
6.3. |  | 1.1.1.6.5. Formulating proposals regarding the individual members of the Coordinating Working Group on the Issues of the Anticorruption Policy and submitting them to the Cabinet of Ministers of Ukraine | National Agency on Corruption Prevention | The measure was not implemented on time and in full | Implemented
6.4. |  | 1.1.1.6.6. Approving the individual members of the Coordinating Working Group on the Issues of the Anticorruption Policy, which is co-chaired by the Chairman of the National Agency and the a minister of the Cabinet of Ministers of Ukraine | National Agency on Corruption Prevention | The measure was not implemented on time and in full | Implemented
6.5. |  | 1.1.1.6.7. Implementation of measures by the National Agency towards encouraging the Program implementing actors to implement the Program activities in a timely manner and effectively. In particular, at least once every quarter the National Agency shall send official letters to those Program actors that have failed to implement or have inadequately implemented the activities in respect of which they have been designated as implementing actors. | National Agency on Corruption Prevention | The measure was implemented on time, but partially | Partially implemented
6.6. |  | 1.1.1.6.8. Ensuring the quarterly update of the Cabinet of Ministers of Ukraine, the Parliament of Ukraine (particularly the Ukrainian Parliament committee overseeing the issues of combating corruption), and the President of Ukraine on the status of Program implementation | National Agency on Corruption Prevention | The measure was implemented on time and in full | Implemented
6.7. |  | 1.1.1.6.9. Analyzing the issue of establishment of regional offices of the National Agency and using the analysis findings to make a justified decision to either establish them or decide that no need for such offices exists | National Agency on Corruption Prevention | The measure was implemented on time and in full | Implemented
7.1. | ОСР 1.1.1.7 The results of monitoring and evaluation of the effectiveness of the anticorruption policy are complete, credible, objective, and public | 1.1.1.7.1. Drafting and approving the Procedure for Monitoring and Assessing the Implementation of the Anticorruption Strategy and Program | National Agency on Corruption Prevention | The measure was implemented on time and in full | Implemented | 57.1% 8/14 | 0.0%
7.2. |  | 1.1.1.7.2. Conducting the quarterly monitoring of the status of implementation of the Program activities in the manner prescribed by the National Agency | National Agency on Corruption Prevention | The measure was implemented on time and in full | Implemented
7.3. |  | 1.1.1.7.3. Publishing on the official website of the National Agency the findings of the quarterly monitoring of the status of implementation of the Program activities; after the launch of the information monitoring system, the monitoring findings will be published using this system | National Agency on Corruption Prevention | The measure was implemented on time and in full | Implemented
7.4. |  | 1.1.1.7.4. Conducting the annual assessment of the progress of achievement of the anticipated strategic results outlined in the Anticorruption Strategy and the Program, in the manner prescribed by the National Agency | National Agency on Corruption Prevention | The measure was implemented on time and in full | Implemented
7.5. |  | 1.1.1.7.5. Organizing two expert surveys (2024, 2025) among experts in matters of formulation and implementation of the anticorruption and legal policies with the objective of assessing the accomplishment of indicators of anticipated strategic results outlined in Clauses 1 - 3 of this appendix | National Agency on Corruption Prevention | The measure has not been implemented | Not implemented
7.6. |  | 1.1.1.7.6. Organizing two expert surveys (2024, 2025) among experts in matters of justice and activities of law enforcement and prosecutorial authorities with the objective of assessing the accomplishment of indicators of anticipated strategic results outlined in Clauses 2 and 3 of this appendix | National Agency on Corruption Prevention | The measure has not been implemented | Not implemented
7.7. |  | 1.1.1.7.7. Organizing two expert surveys (2024, 2025) among experts in matters of regulation of the economy and commerce with the objective of assessing the accomplishment of indicators of anticipated strategic results outlined in subclauses 2.2, 2.3, and 2.4 of Clause 2 this appendix | National Agency on Corruption Prevention | The measure has not been implemented | Not implemented
7.8. |  | 1.1.1.7.8. Organizing two expert surveys (2024, 2025) among experts in matters of land relations with the objective of assessing the accomplishment of indicators of anticipated strategic results outlined in subclause 2.5 of Clause 2 this appendix | National Agency on Corruption Prevention | The measure has not been implemented | Not implemented
7.9. |  | 1.1.1.7.9. Organizing two expert surveys (2024, 2025) among experts in matters of the customs policy with the objective of assessing the accomplishment of indicators of anticipated strategic results outlined in subclause 2.3 of Clause 2 this appendix | National Agency on Corruption Prevention | The measure has not been implemented | Not implemented
7.10. |  | 1.1.1.7.10. Organizing two expert surveys (2024, 2025) among experts in matters of defense with the objective of assessing the accomplishment of indicators of anticipated strategic results outlined in subclause 2.6 of Clause 2 this appendix | National Agency on Corruption Prevention | The measure has not been implemented | Not implemented
7.11. |  | 1.1.1.7.11. Publishing on the official website of the National Agency the findings of the annual assessment of the progress of accomplishment of the strategic results outlined in the Anticorruption Strategy and Program (after the launch of the information monitoring system, the assessment findings will be published using this system) | National Agency on Corruption Prevention | The measure was implemented on time and in full | Implemented
7.12. |  | 1.1.1.7.12. Preparing a report on the status of implementation of the Anticorruption Strategy and the Program, indicating the activities completed, the activities currently in progress, and the activities that have not been completed as well as those responsible and the causes of the failure to complete them | National Agency on Corruption Prevention | The measure was implemented on time and in full | Implemented
7.13. |  | 1.1.1.7.13. Preparing the National Report on the Effectiveness of Implementation of the 2023-2025 State Anticorruption Policy, including the information indicated in Part 3 of Article 20 of the Law | National Agency on Corruption Prevention | The measure was implemented on time and in full | Implemented
7.14. |  | 1.1.1.7.14. Publishing on the official website of the National Agency the National Report on the Effectiveness of Implementation of the 2023-2025 State Anticorruption Policy and submitting to the Cabinet of Ministers of Ukraine, the Ukrainian Parliament, and the President of Ukraine | National Agency on Corruption Prevention | The measure was implemented on time and in full | Implemented
8.1. | ОСР 1.1.1.8 Anticorruption programs and other program documents of anticorruption nature issued by government agencies, local self-government bodies, and other public institutions are an effective mechanism for overcoming and preventing corrupt practices in the public sector; the public is involved in their development and monitoring | 1.1.1.8.1. Drafting and submitting to the Cabinet of Ministers of Ukraine a draft law proposing to amend the Law to: 2) supplement Article 19 of the Law with an exhaustive list of entities that are obligated to adopt corruption risk management documents in coordination with the National Agency; 4) define the powers of the National Agency to approve the corruption risk management methodology; carry out strategic analysis of corruption risks in the areas defined by the National Agency and issue proposals based on the analysis findings, the consideration of which is mandatory; monitor the implementation of corruption risk management plans of the entities indicated in Article 19 of the Law; 5) define the corruption risk management role of the head and corruption risk management tasks of anticorruption units (anticorruption officers), according to the methodology approved by the National Agency; 6) abolish the requirement for the National Agency to approve anticorruption programs of the entities indicated in Article 19 of the Law; 7) define the obligation of the entities indicated in Article 19 of the Law to approve corruption risk management documents taking into account the proposals and critical feedback from the National Agency, and also ensure the mandatory implementation of such documents; 8) define the task of anticorruption units (anticorruption officers) to analyze potential and existing contracting parties of the relevant agency using the risk-based approach and submit proposals to the head of this agency. | National Agency on Corruption Prevention | The measure has not been implemented | Not implemented | 12.5% 1/8 | 0.0%
8.2. |  | 1.1.1.8.2. Drafting an order of the National Agency to amend the Corruption Risk Management Methodology | National Agency on Corruption Prevention | Implementation of the measure has not started | Не підлягають виконанню
8.3. |  | 1.1.1.8.3. Holding a public discussion of the draft order indicated in subclause 1.1.1.8.2, and ensuring its revision (if needed), approval, and submission for state registration | National Agency on Corruption Prevention | Implementation of the measure has not started | Не підлягають виконанню
8.4. |  | 1.1.1.8.4. Supporting the state registration of the order indicated in subclause 1.1.1.8.2 and its official publication | National Agency on Corruption Prevention | Implementation of the measure has not started | Не підлягають виконанню
8.5. |  | 1.1.1.8.5. Drafting an order of the National Agency to amend the Model Regulation on the Authorized Unit (Authorized Officer) Tasked with the Prevention and Detection of Corruption, specifically by updating the tasks of the authorized unit (authorized officer) in matters of organizing corruption risk management, analyzing potential and existing contracting parties, and submitting the information about them to the head of the relevant agency, annually submitting information about the implementation of activities under the anticorruption program of the relevant agency to the National Agency via the anticorruption portal | National Agency on Corruption Prevention | Implementation of the measure has not started | Не підлягають виконанню
8.6. |  | 1.1.1.8.6. Holding a public discussion of the draft order indicated in subclause 1.1.1.8.5, and ensuring its revision (if needed), issuance, and submission for state registration | National Agency on Corruption Prevention | Implementation of the measure has not started | Не підлягають виконанню
8.7. |  | 1.1.1.8.7. Supporting the state registration of the order indicated in subclause 1.1.1.8.5 and its official publication | National Agency on Corruption Prevention | Implementation of the measure has not started | Не підлягають виконанню
8.8. |  | 1.1.1.8.8. Conducting the annual strategic analysis of corruption risks in priority sectors defined by the National Agency and publishing the findings of this strategic analysis | National Agency on Corruption Prevention | The measure was implemented on time and in full | Implemented