## Заходи
№ п/п | Назва ОСР | Назва заходу | Головний виконавець | Результати моніторингу (останні) | Відмітка про виконання | % виконаних заходів (повністю та частково) | Оцінка досягнення ОСР
1.1. | ОСР 1.4.2.2 Declarants spend less time when filling out declarations and make fewer mistakes when entering information, particularly owing to the updated declaration form and the ability to automatically migrate specific details from other state registers into the declaration | 1.4.2.2.1. Drafting and submitting to the Cabinet of Ministers of Ukraine a draft law proposing to provide a more detailed wording of the provisions in Article 46 of the Law and optimize the list of information that must be declared | National Agency on Corruption Prevention | The measure has not been implemented | Not implemented | 83.3% 5/6 | 0.0%
1.2. |  | 1.4.2.2.2. Development and submission of a draft regulation of Cabinet of Ministers of Ukraine to identify the verification procedure applied in public electronic registers, such as: 1) individuals’ identification data; 2) addresses in accordance with the Unified state address register | Ministry of Digital Transformation of Ukraine | The measure was not implemented on time and in full | Implemented
1.3. |  | 1.4.2.2.3. Performance of analysis on interaction and technical compatibility (interoperability) of the Unified state declaration register of individuals authorized to perform state and local government functions, and other state registers, including: 1) identification of reasons for insufficient compatibility of data from public electronic registers and other information communication systems with data from declarations, submitted to the Unified state declaration register of individuals authorized to perform state and local government functions; 2) development of proposals on elimination of reasons for insufficient compatibility of registers | National Agency on Corruption Prevention | The measure was implemented on time and in full | Implemented
1.4. |  | 1.4.2.2.4. Adding data on owners, due vehicle users, transferred to the Unified state vehicle register from previous registers, other information systems, with data about the taxpayer registration card no. or unique record no. in Unified state demographic register (if such number was assigned) | Ministry of Internal Affairs of Ukraine | The measure was implemented on time and in full | Implemented
1.5. |  | 1.4.2.2.5. Implementation of electronic personal data verification service | State Migration Service of Ukraine | The measure was implemented on time, but partially | Partially implemented
1.6. |  | 1.4.2.2.6. Provision of free access to declaration subjects using the program tools of the Unified state regarding individual and family data, contrained in information and communication systems, reference systems, registers, data banks, owned (administered) by the state bodies of local government bodies, including restricted access data, automatically accessible for National Agency on Corruption Prevention, including automated transfer of such data to declaration forms | National Agency on Corruption Prevention | The measure was implemented on time and in full | Implemented
2.1. | ОСР 1.4.2.3 Declarants are able to receive comprehensive information and advice on filling out the declaration, in particular through proper outreach and awareness-raising efforts | 1.4.2.3.1. Providing declarants with up-to-date clarifications of the provisions of anticorruption legislation | National Agency on Corruption Prevention | The measure was implemented on time and in full | Implemented | 100% 1/1 | 0.0%
3.1. | ОСР 1.4.2.4 Regulations are in place, which define the specific considerations of amendments to the rules of declaration during the period of submission of annual declarations in order to ensure stability and predictability of the rules of declaration | 1.4.2.4.1. Drafting and submitting to the Cabinet of Ministers of Ukraine a draft law proposing to amend the Law to: 1) prohibit changes to the rules of electronic declaration during the period of submission of annual declarations; 2) stipulate that should changes to the rules of electronic declaration be made later than six months prior to the start of a new reporting period, such changes shall take effect after the end of this reporting period. | National Agency on Corruption Prevention | The measure has not been implemented | Not implemented | 0% 0/1 | 0.0%