## Заходи
№ п/п | Назва ОСР | Назва заходу | Головний виконавець | Результати моніторингу (останні) | Відмітка про виконання | % виконаних заходів (повністю та частково) | Оцінка досягнення ОСР
1.1. | ОСР 1.5.2.1 Contributions to political parties by individuals who do not have a sufficient legitimate income to afford such contributions have been rendered impossible | 1.5.2.1.1. Drafting and submitting to the Cabinet of Ministers of Ukraine the Draft Law of Ukraine On Amendments to Select Legislative Acts of Ukraine Towards Minimizing the Potential Oligarchic Influence on Political Parties, Involvement of Individuals Living with Disabilities in the Activity of Political Parties, and Improvement of the Mechanism of State Funding of Statutory Activities of a Political Party, the Law of Ukraine On Political Parties of Ukraine towards minimizing the potential oligarchic influence on political parties and improving the mechanism of state funding of statutory activities of a political party, which proposes: 1) limiting the total annual amount (sum) of contributions in support of a political party per citizen of Ukraine: no more than 20 percent of the citizen’s cumulative income over the past five calendar years; 2) prohibiting individuals acting in the interests of a third party from making contributions in support of political parties | National Agency on Corruption Prevention | The measure was implemented late and partially | Partially implemented | 100% 1/1 | 0.0%
2.1. | ОСР 1.5.2.4 The procedure for using online mass media, outdoor advertising, social media and other online platforms for election campaign purposes has been established | 1.5.2.4.1. Supporting the consideration of the Draft Law of Ukraine On Amendments to the Election Code of Ukraine Towards Improvement of the Regulation of the Communications Support of Elections and Pre-election Campaigning (registration number 8310 dated December 27, 2022) in the Parliament of Ukraine (particularly if the President of Ukraine vetoes the draft law) | Ministry of Culture and Strategic Communications of Ukraine | The measure was implemented on time, but partially | Partially implemented | 100% 1/1 | 0.0%