## Заходи
№ п/п | Назва ОСР | Назва заходу | Головний виконавець | Результати моніторингу (останні) | Відмітка про виконання | % виконаних заходів (повністю та частково) | Оцінка досягнення ОСР
1.1. | ОСР 1.6.2.1 Legislation has been amended to ensure convenient reporting of corruption and effective review of such reports; The Single Portal for Whistleblower Reports is functioning | 1.6.2.1.1. Launching the Single Portal for Whistleblower Reports | National Agency on Corruption Prevention | The measure was not implemented on time and in full | Implemented | 100% 6/6 | 0.0%
1.2. |  | 1.6.2.1.2. Connecting government agencies, local self-government bodies, and legal entities under public law to the Unified Whistleblower Reporting Portal under the procedure approved by the National Agency | National Agency on Corruption Prevention | The measure was implemented on time, but partially | Partially implemented
1.3. |  | 1.6.2.1.3. Developing the requisite training and methodological materials and conducting trainings for employees of anticorruption units (anticorruption officers) focusing on effective organization of work with the Unified Whistleblower Reporting Portal | National Agency on Corruption Prevention | The measure was implemented on time and in full | Implemented
1.4. |  | 1.6.2.1.4. Creating online courses for anticorruption units (anticorruption officers) focusing on effective organization of work with the Unified Whistleblower Reporting Portal | National Agency on Corruption Prevention | The measure was implemented on time and in full | Implemented
1.5. |  | 1.6.2.1.5. Conducting a survey of employees of anticorruption units (anticorruption officers) on the convenience and effectiveness of handling of corruption reports with the aid of the Unified Whistleblower Reporting Portal | National Agency on Corruption Prevention | The measure was implemented on time and in full | Implemented
1.6. |  | 1.6.2.1.6. Preparing and publicizing consolidated information about the distribution of the number of reports submitted by whistleblowers among the channels prescribed by law | National Agency on Corruption Prevention | The measure was not implemented on time and in full | Implemented
2.1. | ОСР 1.6.2.2 A significant number of citizens are well aware of the procedure and channels for reporting corruption owing to effective outreach and awareness-raising efforts | 1.6.2.2.1. Implementing the activities outlined in the Anticorruption Communications Strategy | National Agency on Corruption Prevention | The measure was implemented on time and in full | Implemented | 100% 1/1 | 0.0%
3.1. | ОСР 1.6.2.3 Appropriate internal channels for submission of corruption reports that contain information classified as a secret of state, a secret of the investigation, as well as official information gathered in the course of field detective operations, counterintelligence activities in the national defense sector have been created | 1.6.2.3.1. Drafting and submitting to the Cabinet of Ministers of Ukraine a draft law proposing to provide for the creation of appropriate internal channels for secure submission of corruption reports that contain information classified as a secret of state, a secret of the investigation, as well as official information gathered in the course of field detective operations, counterintelligence activities in the national defense sector | National Agency on Corruption Prevention | The measure has not been implemented | Not implemented | 0% 0/2 | 0.0%
3.2. |  | 1.6.2.3.2. Monitoring of the creation of internal channels for secure (particularly anonymous) submission of corruption reports at all agencies conducting field detective, counterintelligence, or intelligence activities in the national defense sector | National Agency on Corruption Prevention | The measure has not been implemented | Not implemented