## Заходи
№ п/п | Назва ОСР | Назва заходу | Головний виконавець | Результати моніторингу (останні) | Відмітка про виконання | % виконаних заходів (повністю та частково) | Оцінка досягнення ОСР
1.1. | ОСР 2.1.1.1 Integrity has been defined as a mandatory legislative requirement for members of the High Council of Justice, the High Qualification Commission of Judges of Ukraine, and disciplinary authorities in the justice system | 2.1.1.1.1. Monitoring the draft laws that propose amendments to the Laws of Ukraine On the Judicial System and Status of Judges and On the High Council of Justice regarding the assessment of conformity to the criteria of integrity on the part of candidates for the position of a member of the High Council of Justice, the High Qualification Commission of Judges of Ukraine, and the indicators based on which the assessment of conformity to the criterion of integrity is carried out, as well as preparation of the relevant proposals | High Council of Justice | The measure was implemented on time and in full | Implemented | 100% 1/1 | 0.0%
2.1. | ОСР 2.1.1.2 The integrity of new members of the High Council of Justice and the High Qualification Commission of Judges of Ukraine is assessed by an independent commission; the current composition of the High Council of Justice is checked for compliance with the requirements of integrity and professional ethics; new members of the High Council of Justice and the High Qualification Commission of Judges of Ukraine meet these requirements; the issue of dismissal of members who did not meet these requirements is considered | 2.1.1.2.1. Conducting the assessment of conformity of the candidates for positions of members of the High Council of Justice to the requirements of professional ethics and integrity | Ethics Council | The measure was implemented on time and in full | Implemented | 66.7% 2/3 | 0.0%
2.2. |  | 2.1.1.2.2. Conducting the assessment of conformity of the candidates for vacant positions of members of the High Qualification Commission of Judges of Ukraine to the criterion of integrity | competition commission for holding a competition for the position of a member of the Higher Qualification Commission of Judges of Ukraine | The measure was implemented on time and in full | Implemented
2.3. |  | 2.1.1.2.3. Drafting and submitting to the Cabinet of Ministers of Ukraine a draft law that: 1) amends Article 951 of the Law of Ukraine On the Judicial System and Status of Judges regarding the inclusion of civil society representatives in the competitive selection committee (instead of international experts pursuant to Clause 50 of Section XII “Final and Transitional Provisions” of said Law); 2) amends Article 91 of the Law of Ukraine On the High Council of Justice regarding the inclusion of civil society representatives in the Ethics Council (instead of international experts pursuant to Clause 231 of Section III “Final and Transitional Provisions” of said Law). | National Agency on Corruption Prevention | The measure has not been implemented | Not implemented
3.1. | ОСР 2.1.1.3 A member of the High Council of Justice or the High Qualification Commission of Judges of Ukraine is unable to pass decisions when faced with a conflict of interest | 2.1.1.3.1. Arranging an analytical study of the mechanism of prevention and resolution of conflicts of interest in the proceedings of the High Council of Justice and the High Qualification Commission of Judges of Ukraine, the problems inherent in this mechanism and proposals on how to address them, and the presentation of the analytical study (particularly regarding the possibility of reporting a potential conflict of interest or submitting a voluntary declaration of private interest) | National Agency on Corruption Prevention | The measure was not implemented on time and in full | Implemented | 50% 1/2 | 0.0%
3.2. |  | 2.1.1.3.2. Drafting and submitting to the Cabinet of Ministers of Ukraine a draft law proposing to eliminate the existing problems inherent in the mechanism of prevention and regulation of the conflict of interest in the proceedings of the High Council of Justice and the High Qualification Commission of Judges of Ukraine, taking into account the findings of the analytical study indicated in subclause 2.1.1.3.1 | National Agency on Corruption Prevention | The measure has not been implemented | Not implemented