## Заходи
№ п/п | Назва ОСР | Назва заходу | Головний виконавець | Результати моніторингу (останні) | Відмітка про виконання | % виконаних заходів (повністю та частково) | Оцінка досягнення ОСР
1.1. | ОСР 2.1.2.1 The High Qualification Commission of Judges of Ukraine, the High Council of Justice, together with the bodies involved in the assessment, judicial self-government bodies and the public have developed and implemented clear and predictable criteria (indicators) of integrity and professional ethics for the qualification assessment of judges and selection of new judges | 2.1.2.1.1. Conducting (and publishing the findings of) an analytical study of the practices of evaluation of judges for conformity to the criteria of integrity and professional ethics and evaluation of candidates for conformity to the criterion of integrity by the High Qualification Commission of Judges, the Public Council on Integrity, and the Public Council of International Experts | Higher Qualification Commission of Judges of Ukraine | The measure was not implemented on time and in full | Implemented | 100% 7/7 | 0.0%
1.2. |  | 2.1.2.1.2. Conducting (and publishing the findings of) an analytical study of the practices of evaluation of judges for conformity to the criteria of integrity and professional ethics and evaluation of candidates for conformity to the criterion of integrity by the High Council of Justice | High Council of Justice | The measure was implemented on time and in full | Implemented
1.3. |  | 2.1.2.1.3. Conducting and publicizing a comparative analysis of the reports issued by the High Council of Justice, the High Qualification Commission of Judges of Ukraine, the Public Council on Integrity, and the Public Council of International Experts on the analysis of the practices of evaluation of judges for conformity to the criteria of integrity and professional ethics and evaluation of candidates for conformity to the criterion of integrity | High Council of Justice | The measure was implemented on time and in full | Implemented
1.4. |  | 2.1.2.1.4. Drafting and submitting to the Cabinet of Ministers of Ukraine a draft law proposing to grant the High Council of Justice the powers to approve Unified judge (candidate for a position of a judge) integrity and professional ethics estimation indicators during all procedures of selection and evaluation of judges | Ministry of Justice of Ukraine | The measure was implemented on time and in full | Implemented
1.5. |  | 2.1.2.1.5. Drafting the Unified judge (candidate for a position of a judge) integrity and professional ethics estimation indicators taking into account the best practices identified based on the findings of the analysis of the practices of evaluation by the High Council of Justice, the High Qualification Commission of Judges of Ukraine, the Public Council of International Experts, and the Public Council on Integrity | High Council of Justice | The measure was not implemented on time and in full | Implemented
1.6. |  | 2.1.2.1.6. Holding consultations with the participation of the High Council of Justice, the High Qualification Commission of Judges of Ukraine, the Public Council on Integrity, the Council of Judges of Ukraine, NGOs, and other stakeholders on the draft of Unified judge (candidate for a position of a judge) integrity and professional ethics estimation indicators, obtaining expert opinions, and revising the draft | High Council of Justice | The measure was not implemented on time and in full | Implemented
1.7. |  | 2.1.2.1.7. Clearing, approving, and publicizing the revised draft of Unified judge (candidate for a position of a judge) integrity and professional ethics estimation indicators | High Council of Justice | The measure was not implemented on time and in full | Implemented
2.1. | ОСР 2.1.2.2 Improvements have been made to the mechanism of evaluation of candidates for conformity to the criteria (indicators) of integrity as part of procedures to select and appoint new judges with the involvement of the Public Council on Integrity | 2.1.2.2.1. Preparing and publicizing an analytical report on the expediency of forming the secretariat of the Public Council on Integrity, on ways to incorporate the recommendations of XV GRECO, and presenting the report | National Agency on Corruption Prevention | The measure has not been implemented | Not implemented | 0% 0/2 | 0.0%
2.2. |  | 2.1.2.2.2. Drafting and submitting to the Cabinet of Ministers of Ukraine a draft law that: 1) provides for the evaluation of candidates for the position of a judge for conformity to the criterion of integrity in all judge selection procedures; 2) provides for the involvement of the Public Council on Integrity in helping the High Qualification Commission of Judges of Ukraine to determine whether or not candidates for the position of a judge conform to the criterion of integrity in all judge selection procedures; 3) defines a new mechanism for considering the opinion of the Public Council on Integrity to the effect that a judge (a candidate for the position of a judge) does not conform to the criteria of professional ethics and integrity, or for verifying the ability of this judge (candidate for the position of a judge) to administer justice when such an opinion has been issued; 4) grants members of the Public Council on Integrity and authorized officers of the secretariat of the Public Council on Integrity full access to personal files of judges (personal files of candidates for the position of a judge); 5) provides for the creation of the secretariat of the Public Council on Integrity, which would assist the members of the Public Council on Integrity while they exercise the legislatively prescribed powers, and identify the source of funding for their activities (if the formation of this secretariat has been deemed expedient according to the findings of the analytical study indicated in subclause 2.1.2.2.1); 6) provides for the involvement of the Public Council on Integrity in determining the schedules, time frames, and sequence of evaluations of judges and candidates for the position of a judge. | National Agency on Corruption Prevention | The measure has not been implemented | Not implemented
3.1. | ОСР 2.1.2.3 Improvements have been made to the mechanism by which the High Qualification Commission of Judges of Ukraine conducts procedures of evaluation of qualifications of judges and competitive selection procedures in order to avoid unjustified delays | 2.1.2.3.1. Developing a draft act that would simplify the procedure of administering examinations and tests, particularly regarding the possibility of evaluation of practical knowledge by specialists hired by the High Qualification Commission of Judges of Ukraine, simplify the scoring based on the results of psychological tests, and so forth | Higher Qualification Commission of Judges of Ukraine | The measure was implemented on time and in full | Implemented | 71.4% 5/7 | 0.0%
3.2. |  | 2.1.2.3.2. Holding a public discussion of the draft act indicated in subclause 2.1.2.3.1, and ensuring its revision (if needed) | Higher Qualification Commission of Judges of Ukraine | The measure was implemented on time and in full | Implemented
3.3. |  | 2.1.2.3.3. Approving and publicizing the draft act indicated in subclause 2.1.2.3.1 | Higher Qualification Commission of Judges of Ukraine | The measure was implemented on time and in full | Implemented
3.4. |  | 2.1.2.3.4. Preparing and publicizing an analytical report on the expediency of continued improvement and simplification of judge selection procedures, evaluation of qualifications of judges (candidates for the position of a judge) with the objective of avoiding unjustified delays | Ministry of Justice of Ukraine | The measure was not implemented on time and in full | Implemented
3.5. |  | 2.1.2.3.5. Discussing the conclusions and recommendations outlined in the analytical report indicated in subclause 2.1.2.3.4 with the participation of representatives of government agencies, NGOs, international organizations, participants of international technical assistance projects, and the academic community | Ministry of Justice of Ukraine | The measure was implemented late and partially | Partially implemented
3.6. |  | 2.1.2.3.6. Developing software and deploying hardware needed to create and maintain personal files of judges (personal files of candidates for positions of judges) in electronic form in the Unified Judicial Information and Telecommunication System | State Judicial Administration of Ukraine | The measure has not been implemented | Not implemented
3.7. |  | 2.1.2.3.7. Preparing and approving a regulation governing the procedure of operation of the subsystem designed to create and maintain personal files of judges (personal files of candidates for positions of judges) in electronic form in the Unified Judicial Information and Telecommunication System | High Council of Justice | The measure has not been implemented | Not implemented
4.1. | ОСР 2.1.2.4 An objective and transparent methodology for scoring and determining the results by members of the High Qualification Commission of Judges of Ukraine and the High Council of Justice when making decisions in the selection, evaluation, and promotion of judges, as well as for publishing information on the examinations, has been introduced | 2.1.2.4.1. Drafting and submitting to the Cabinet of Ministers of Ukraine a draft law that: 1) mandates the publication by the High Qualification Commission of Judges of Ukraine of the results of examinations during the assessment of qualifications of judges (while safeguarding the personal data) | Ministry of Justice of Ukraine | The measure was implemented on time and in full | Implemented | 100% 7/7 | 0.0%
4.2. |  | 2.1.2.4.2. Developing the draft professional profile of a judge | Higher Qualification Commission of Judges of Ukraine | The measure was not implemented on time and in full | Implemented
4.3. |  | 2.1.2.4.3. Holding consultations with the participation of the High Council of Justice, the High Qualification Commission of Judges of Ukraine, the Public Council on Integrity, the Council of Judges of Ukraine, NGOs, and other stakeholders on the draft professional profile of a judge, obtaining expert opinions, and revising the draft | Higher Qualification Commission of Judges of Ukraine | The measure was not implemented on time and in full | Implemented
4.4. |  | 2.1.2.4.4. Approving and publicizing the revised professional profile of a judge | Higher Qualification Commission of Judges of Ukraine | The measure was not implemented on time and in full | Implemented
4.5. |  | 2.1.2.4.5. Developing the draft of detailed methods of the High Qualification Commission of Judges of Ukraine for the scoring of judges (candidates for the position of a judge) at each stage of judge selection and qualification evaluation procedures | Higher Qualification Commission of Judges of Ukraine | The measure was not implemented on time and in full | Implemented
4.6. |  | 2.1.2.4.6. Holding consultations with the participation of the High Council of Justice, the High Qualification Commission of Judges of Ukraine, the Public Council on Integrity, the Council of Judges of Ukraine, NGOs, and other stakeholders on the draft of detailed methods of the High Qualification Commission of Judges of Ukraine for the scoring of judges (candidates for the position of a judge) at each stage of judge selection and qualification evaluation procedures, obtaining expert opinions, and revising the draft | Higher Qualification Commission of Judges of Ukraine | The measure was implemented on time and in full | Implemented
4.7. |  | 2.1.2.4.7. Approving the revised detailed methods of the High Qualification Commission of Judges of Ukraine for the scoring of judges (candidates for the position of a judge) at each stage of judge selection and qualification evaluation procedures, and publicizing them | Higher Qualification Commission of Judges of Ukraine | The measure was not implemented on time and in full | Implemented