## Заходи
№ п/п | Назва ОСР | Назва заходу | Головний виконавець | Результати моніторингу (останні) | Відмітка про виконання | % виконаних заходів (повністю та частково) | Оцінка досягнення ОСР
1.1. | ОСР 2.2.1.1 An official tool for preparing and conducting public procurement in the sector of information technology development has been developed and put into commercial operation, which provides for visualization of procurement, availability of electronic communication networks, and automation of anticipated cost calculations | 2.2.1.1.1. Provision of analytical research, focusing on the following: 1) identification of real information, analytical and other digitalization needs of customers, in particular, the following: tools for preparation of public procurement of hardware and software, including their functionality; tools to conduct public procurement of hardware and software, and its functionality; 2) question of recognition of invalidity of legal actions in case of failure to use the aforementioned tools; 3) identification of necessity / absence of need to make amendments to appropriate legislative acts to settle the issue of implementation of tools to prepare and/or performance of public procurement of hardware and software | Ministry of Digital Transformation of Ukraine | The measure was not implemented on time and in full | Implemented | 100% 7/7 | 0.0%
1.2. |  | 2.2.1.1.2. Holding a presentation of the findings of the analytical study indicated in subclause 2.2.1.1.1, followed by its expert discussion | Ministry of Digital Transformation of Ukraine | The measure was not implemented on time and in full | Implemented
1.3. |  | 2.2.1.1.3. Developing and publicizing the concept of the tool for preparing and/or the tool of conducting public procurement in the sector of information technology development, taking into account the findings of the study indicated in subclause 2.2.1.1.1 | Ministry of Digital Transformation of Ukraine | The measure was not implemented on time and in full | Implemented
1.4. |  | 2.2.1.1.5. Development of tool to prepare and/or performance of public procurement of hardware and software, which ensures: 1) automation of calculations of expected costs of goods, works, or services; 2) visualization of procurement statistics; 3) other functionality, related to users’ needs according to the results of the expert discussion, indicated in subclause 2.2.1.1.1 | Ministry of Digital Transformation of Ukraine | The measure was implemented on time and in full | Implemented
1.5. |  | 2.2.1.1.9. Analyzing the Law of Ukraine On the National Information Technology Development Program and amending normative legal acts based on the analysis findings (if needed) | Ministry of Digital Transformation of Ukraine | The measure was implemented on time and in full | Implemented
1.6. |  | 2.2.1.1.10. Creating the information and communications system “Unified Information Logging System of the National Information Technology Development Program” | Ministry of Digital Transformation of Ukraine | The measure was not implemented on time and in full | Implemented
1.7. |  | 2.2.1.1.11. Putting the information and communications system “Unified Information Logging System of the National Information Technology Development Program” into operation | Ministry of Digital Transformation of Ukraine | The measure was implemented on time and in full | Implemented
2.1. | ОСР 2.2.1.2 A unified interoperable system of state databases based on a single state data center and national spatial data infrastructure has been created, and overlapping data collection processes have been eliminated | 2.2.1.2.5. Drafting and submitting to the Cabinet of Ministers of Ukraine a draft directive of the Cabinet of Ministers of Ukraine, which would approve the plan to enhance the interoperability of information systems, ensuring its performance monitoring, including the duty to publish the results of completion of a mentioned plan on a half-year basis | Ministry of Digital Transformation of Ukraine | The measure was not implemented on time and in full | Implemented | 100% 1/1 | 0.0%