## Заходи
№ п/п | Назва ОСР | Назва заходу | Головний виконавець | Результати моніторингу (останні) | Відмітка про виконання | % виконаних заходів (повністю та частково) | Оцінка досягнення ОСР
1.1. | ОСР 2.2.2.1 The implementation of the risk-based system of state oversight (control) has been finalized | 2.2.2.1.1. Supporting the consideration in the Parliament of Ukraine (particularly if the President of Ukraine vetoes the draft law) of the Draft Law of Ukraine On the Fundamental Principles of State Oversight (Control) (registration number 5837 dated August 5, 2021) | Ministry of Economy, Environment and Agriculture of Ukraine | The measure was implemented on time, but partially | Partially implemented | 50% 2/4 | 0.0%
1.2. |  | 2.2.2.1.2. Developing and submitting to the Cabinet of Ministers of Ukraine the draft Methodology of Assessment of the Effectiveness of State Oversight (Control) | Ministry of Economy, Environment and Agriculture of Ukraine | The measure has not been implemented | Not implemented
1.3. |  | 2.2.2.1.3. Developing the Electronic Risk Management System, which is a component of the Integrated Automated System of State Oversight (Control) | State Regulatory Service of Ukraine | The measure was implemented on time, but partially | Partially implemented
1.4. |  | 2.2.2.1.4. Putting into operation the Electronic Risk Management System, which is a component of the Integrated Automated System of State Oversight (Control) | State Regulatory Service of Ukraine |  | Не підлягають виконанню
2.1. | ОСР 2.2.2.2 An audit of the current status of implementation of electronic auctions and systems for accessing a limited public resource has been conducted; the key methods used to bypass their restrictions have been identified; implementation of electronic auctions and systems for accessing a limited public resource has been completed, taking into account the findings of the audit (electronic workspace of the user, Prozorro.Sale electronic auctions) | 2.2.2.2.1. Arranging an analytical study of normative legal acts that have instituted electronic auctions and the system for accessing a limited public resource as regards their actual implementation and functional capabilities, particularly in matters of access to natural resources | Ministry of Economy, Environment and Agriculture of Ukraine | The measure was implemented on time and in full | Implemented | 100% 17/17 | 0.0%
2.2. |  | 2.2.2.2.2. Holding a presentation of the report on the findings of the analytical study indicated in subclause 2.2.2.2.1, followed by its expert discussion | Ministry of Economy, Environment and Agriculture of Ukraine | The measure was implemented on time, but partially | Partially implemented
2.3. |  | 2.2.2.2.3. Arranging an analytical study of the completed electronic auctions for access to a limited public resource, which should determine the current status of implementation of such electronic auctions and systems for accessing a limited public resource, and the methods used to bypass their restrictions (sale through the e-commerce system Prozorro.Sale) | Ministry of Economy, Environment and Agriculture of Ukraine | The measure was implemented on time and in full | Implemented
2.4. |  | 2.2.2.2.4. Holding a presentation of the report on the findings of the analytical study indicated in subclause 2.2.2.2.3, followed by its expert discussion | Ministry of Economy, Environment and Agriculture of Ukraine | The measure was implemented on time, but partially | Partially implemented
2.5. |  | 2.2.2.2.5.(1) Developing and submitting to the Cabinet of Ministers of Ukraine draft acts of the Cabinet of Ministers of Ukraine on the implementation of electronic auctions and systems for accessing a limited public resource on a permanent basis, taking into account the findings of analytical studies | Ministry of Economy, Environment and Agriculture of Ukraine | The measure was implemented on time, but partially | Partially implemented
2.6. |  | 2.2.2.2.5.(3) Developing and submitting to the Cabinet of Ministers of Ukraine draft acts of the Cabinet of Ministers of Ukraine on the implementation of electronic auctions and systems for accessing a limited public resource on a permanent basis, taking into account the findings of analytical studies | State Forest Resources Agency of Ukraine | The measure was implemented on time, but partially | Partially implemented
2.7. |  | 2.2.2.2.5.(4) Developing and submitting to the Cabinet of Ministers of Ukraine draft acts of the Cabinet of Ministers of Ukraine on the implementation of electronic auctions and systems for accessing a limited public resource on a permanent basis, taking into account the findings of analytical studies | State Service of Geology and Mineral Resources of Ukraine | The measure was implemented on time and in full | Implemented
2.8. |  | 2.2.2.2.5.(5) Developing and submitting to the Cabinet of Ministers of Ukraine draft acts of the Cabinet of Ministers of Ukraine on the implementation of electronic auctions and systems for accessing a limited public resource on a permanent basis, taking into account the findings of analytical studies | State Agency of Ukraine for the Development of Melioration, Fisheries and Food Programs | The measure was implemented on time, but partially | Partially implemented
2.9. |  | 2.2.2.2.6.(2) Implementing electronic auctions and systems for accessing a limited public resource on a permanent basis and fully | State Forest Resources Agency of Ukraine | The measure was implemented on time, but partially | Partially implemented
2.10. |  | 2.2.2.2.6.(5) Implementing electronic auctions and systems for accessing a limited public resource on a permanent basis and fully | State Agency of Ukraine for the Development of Melioration, Fisheries and Food Programs | The measure was implemented on time, but partially | Partially implemented
2.11. |  | 2.2.2.2.6.(3) Implementing electronic auctions and systems for accessing a limited public resource on a permanent basis and fully | State Service of Geology and Mineral Resources of Ukraine | The measure was implemented on time and in full | Implemented
2.12. |  | 2.2.2.2.6.(1) Implementing electronic auctions and systems for accessing a limited public resource on a permanent basis and fully | Ministry of Economy, Environment and Agriculture of Ukraine | The measure was implemented on time, but partially | Partially implemented
2.13. |  | 2.2.2.2.7.(1) Opening access to current information about natural resources. | Ministry of Economy, Environment and Agriculture of Ukraine | The measure was implemented on time, but partially | Partially implemented
2.14. |  | 2.2.2.2.7.(3) Opening access to current information about natural resources. | State Forest Resources Agency of Ukraine | The measure was implemented late and partially | Partially implemented
2.15. |  | 2.2.2.2.7.(4) Opening access to current information about natural resources. | State Agency of Water Resources of Ukraine | The measure was implemented on time and in full | Implemented
2.16. |  | 2.2.2.2.7.(5) Opening access to current information about natural resources. | State Service of Geology and Mineral Resources of Ukraine | The measure was implemented on time and in full | Implemented
2.17. |  | 2.2.2.2.7.(6) Opening access to current information about natural resources. | State Agency of Ukraine for the Development of Melioration, Fisheries and Food Programs | The measure was implemented late and partially | Partially implemented
3.1. | ОСР 2.2.2.3 Following the introduction of relevant amendments to the legislation, the publication of financial statements, information on the risk levels of taxpayers in accordance with the Unified Register of Tax Invoices, license registers, and other key data sets, the publication of which has a significant anticorruption effect (in compliance with the requirements of the legislation on access to public information and personal data protection), has been ensured in the open data format | 2.2.2.3.1. Drafting and submitting to the Cabinet of Ministers of Ukraine the draft resolution of the Cabinet of Ministers of Ukraine on amendments to the resolution of the Cabinet of Ministers of Ukraine dated October 21, 2015, No. 835 On Approval of the Regulation on Data Sets Subject to Publication in the Form of Open Data with respect to the publication of information in the form of open data during martial law, which mandates the disclosure of information from the registers of the Ministry of Agrarian Policy, the Ministry of the Environment and Natural Resources, and the Ministry of the Economy during martial law | Ministry of Digital Transformation of Ukraine | The measure was not implemented on time and in full | Implemented | 42.9% 3/7 | 0.0%
3.2. |  | 2.2.2.3.4. Publishing / updating data in registers of the Ministry of the Economy during martial law (subject to restrictions imposed in the interests of national security, defense, and protection of the lives of citizens) | Ministry of Economy, Environment and Agriculture of Ukraine | The measure was implemented on time, but partially | Partially implemented
3.3. |  | 2.2.2.3.5. Renewing access to all open data sets | Ministry of Digital Transformation of Ukraine |  | Не підлягають виконанню
3.4. |  | 2.2.2.3.6.(1) Publishing in the form of open data the financial statements of legal entities submitted to the State Tax Service for at least the past three years and the financial statements of companies submitted to the State Statistics Service since November 11, 2022 | State Tax Service of Ukraine |  | Не підлягають виконанню
3.5. |  | 2.2.2.3.6.(2) Publishing in the form of open data the financial statements of legal entities submitted to the State Tax Service for at least the past three years and the financial statements of companies submitted to the State Statistics Service since November 11, 2022 | State Statistics Service of Ukraine | The measure was implemented on time and in full | Implemented
3.6. |  | 2.2.2.3.7. Drafting and submitting to the Cabinet of Ministers of Ukraine the draft resolution of the Cabinet of Ministers of Ukraine on amendments to the resolution of the Cabinet of Ministers of Ukraine dated October 21, 2015, No. 835 On Approval of the Regulation on Data Sets Subject to Publication in the Form of Open Data with respect to the publication of data on the risk level of taxpayers | Ministry of Digital Transformation of Ukraine |  | Не підлягають виконанню
3.7. |  | 2.2.2.3.8. Publishing data on the risk level of taxpayers | State Tax Service of Ukraine | Implementation of the measure has not started | Не підлягають виконанню
4.1. | ОСР 2.2.2.4 An information and analytical system for management of natural resources management has been introduced, which provides open access to up-to-date information on natural resources, contains the functionality of electronic services, electronic reporting, traceability, environmental monitoring and inspection, as well as an open software interface for creating analytical and visual (geoinformation) software based on the data of this information and analytical system (without the right to modify such data) | 2.2.2.4.1. Conducting measures towards a nationwide inventory of forests (aerial photography, digitization of information, processing of data) | State Forest Resources Agency of Ukraine | The measure was implemented on time, but partially | Partially implemented | 90.9% 10/11 | 0.0%
4.2. |  | 2.2.2.4.2. Digitizing information about natural resources (geological data, information about aquatic and forest resources) and available irrigation systems, hydraulic structures, and pump stations | Ministry of Economy, Environment and Agriculture of Ukraine | The measure was implemented late and partially | Partially implemented
4.3. |  | 2.2.2.4.3. Creating interactive virtual data rooms for all assets that are available for use | Ministry of Economy, Environment and Agriculture of Ukraine | The measure was implemented late and partially | Partially implemented
4.4. |  | 2.2.2.4.4.(1) Publishing information about electronic auctions with their dates | State Service of Geology and Mineral Resources of Ukraine | The measure was implemented on time and in full | Implemented
4.5. |  | 2.2.2.4.4.(2) Publishing information about electronic auctions with their dates | State Forest Resources Agency of Ukraine | The measure was implemented on time and in full | Implemented
4.6. |  | 2.2.2.4.4.(3) Publishing information about electronic auctions with their dates | State Agency of Ukraine for the Development of Melioration, Fisheries and Food Programs | The measure was implemented on time and in full | Implemented
4.7. |  | 2.2.2.4.5. Creation and development of existing IT systems that will be used to submit applications for permits, approvals, and issue permits, and ensure their integration with the Unified Environmental Platform “EcoSystem” | Ministry of Economy, Environment and Agriculture of Ukraine | The measure was implemented late and partially | Partially implemented
4.8. |  | 2.2.2.4.6. Creating the electronic reporting system with all the relevant forms, providing mandatory information and notices to business entities | Ministry of Economy, Environment and Agriculture of Ukraine | The measure was implemented late and partially | Partially implemented
4.9. |  | 2.2.2.4.7. Creating the natural resources accounting and traceability functionality | Ministry of Economy, Environment and Agriculture of Ukraine | The measure was implemented late and partially | Partially implemented
4.10. |  | 2.2.2.4.8. Implementation of components of the Unified electronic fishery management, where the applications for permitting documentation, approvals, issue of permitting documentation, electronic reporting shall be submitted | Ministry of Economy, Environment and Agriculture of Ukraine | The measure was implemented on time and in full | Implemented
4.11. |  | 2.2.2.4.9. Development of traceability of water bioresources and/or goods, produced from the water bioresources | Ministry of Economy, Environment and Agriculture of Ukraine | Implementation of the measure has not started | Не підлягають виконанню
5.1. | ОСР 2.2.2.5 A two-tiered information and communication system has been introduced that enables the creation, posting, publication, and exchange of information and documents in electronic form, holding concession tenders and a competitive dialog, as well as publication of documents in the course of direct negotiations with the lessee of state property being made available on the terms of a concession | 2.2.2.5.1. Developing planning and access modules based on the state company PROZZORO | Ministry of Economy, Environment and Agriculture of Ukraine | The measure has not been implemented | Not implemented | 0% 0/14 | 0.0%
5.2. |  | 2.2.2.5.2. Developing authentication module | Ministry of Economy, Environment and Agriculture of Ukraine | The measure has not been implemented | Not implemented
5.3. |  | 2.2.2.5.3. Developing auction modules and identification of a winner | Ministry of Economy, Environment and Agriculture of Ukraine | The measure has not been implemented | Not implemented
5.4. |  | 2.2.2.5.4. Developing the proposal estimation module | Ministry of Economy, Environment and Agriculture of Ukraine | The measure has not been implemented | Not implemented
5.5. |  | 2.2.2.5.5. Developing the contracting module | Ministry of Economy, Environment and Agriculture of Ukraine | The measure has not been implemented | Not implemented
5.6. |  | 2.2.2.5.7. Developing the notification, registration, and bid submission modules | Ministry of Economy, Environment and Agriculture of Ukraine | The measure has not been implemented | Not implemented
5.7. |  | 2.2.2.5.8. Implementing the encryption of bids mentioned in subclause 2.2.2.5.7 | Ministry of Economy, Environment and Agriculture of Ukraine | The measure has not been implemented | Not implemented
5.8. |  | 2.2.2.5.9. Testing the Electronic trading system | Ministry of Economy, Environment and Agriculture of Ukraine | The measure has not been implemented | Not implemented
5.9. |  | 2.2.2.5.10. Ensuring negotiations with operators on developing a platform for bidders | Ministry of Economy, Environment and Agriculture of Ukraine | The measure has not been implemented | Not implemented
5.10. |  | 2.2.2.5.11. Testing of the operator-developed platform indicated in subclause 2.2.2.5.10 | Ministry of Economy, Environment and Agriculture of Ukraine | The measure has not been implemented | Not implemented
5.11. |  | 2.2.2.5.12. Ensuring the integration of the project preparation and management system with the Electronic Trading System | Ministry of Economy, Environment and Agriculture of Ukraine | The measure has not been implemented | Not implemented
5.12. |  | 2.2.2.5.13. Testing the interoperation of the project preparation and management system with the Electronic Trading System | Ministry of Economy, Environment and Agriculture of Ukraine | The measure has not been implemented | Not implemented
5.13. |  | 2.2.2.5.14. Preparing and implementing pilot projects in the project preparation and management system and the Electronic Trading System | Ministry of Economy, Environment and Agriculture of Ukraine | The measure has not been implemented | Not implemented
5.14. |  | 2.2.2.5.15. Conducting competitive processes to select a private partner for the Electronic Trading System | Ministry of Economy, Environment and Agriculture of Ukraine | The measure has not been implemented | Not implemented