## Заходи
№ п/п | Назва ОСР | Назва заходу | Головний виконавець | Результати моніторингу (останні) | Відмітка про виконання | % виконаних заходів (повністю та частково) | Оцінка досягнення ОСР
1.1. | ОСР 2.5.1.1 The implementation of the Unified State Electronic System in Construction has been finalized | 2.5.1.1.1. Implementing measures towards systematization and public access to the entirety of the urban development documentation currently in effect, integrating it into the Urban planning cadaster on the state’s level, submitting such documentation to Urban planning cadaster on the state level, particularly by: 1) filling Urban planning cadaster on the state’s level with data and documents related to city building (except for confidential or restricted data, considered as such according to the law); 2) granting viewer access to urban development documentation in any administrative-territorial unit or territorial community with the level of detail down to a separate land plot (except for confidential or restricted data, considered as such according to the law); 3) enabling officials of the authorized city building and architecture bodies must ensure uploading of urban planning documentation to Urban planning cadaster on the state’s level; 4) provision of electronic information interaction between Urban planning cadaster on the state’s level and the national geoportal of the National infrastructure of geospatial data on receipt of basic and topical sets (types) of geospatial data and metadata (data on geospatial data and/or services), used for development of urban planning documentation | Ministry for Communities and Territories Development of Ukraine | The measure was implemented on time, but partially | Partially implemented | 100% 4/4 | 0.0%
1.2. |  | 2.5.1.1.2. Validation and public discussion services are implemented for urban planning documentation projects in Urban planning cadaster on the state’s level geoportal | Ministry for Communities and Territories Development of Ukraine | The measure was implemented on time, but partially | Partially implemented
1.3. |  | 2.5.1.1.3. Implementing measures towards integration and electronic data exchange among the Unified State Electronic System in Construction, the State Register of Real Rights to Immovable Property, and the State Land Cadaster, in particular by: 1) reflecting immovable properties in the State Land Cadaster and integrating information about immovable properties and construction projects in progress (issued construction manifests, registered urban development conditions and restrictions, current documents that authorize construction work), accessing the information of the Unified State Electronic System in Construction about construction projects in progress within the State Land Cadaster; 2) enabling state registrars of rights to immovable property to receive information from the Unified State Electronic System in Construction about the results of technical inventory of immovable properties. | Ministry for Communities and Territories Development of Ukraine | The measure was implemented on time, but partially | Partially implemented
1.4. |  | 2.5.1.1.4. Implementing measures towards integration and electronic data exchange between the Unified State Electronic System in Construction and the electronic register of cultural heritage sites not only based on the address but also based on geospatial data of properties and the registration number of the cultural heritage site | Ministry for Communities and Territories Development of Ukraine | The measure was implemented late and partially | Partially implemented
2.1. | ОСР 2.5.1.2 A unified electronic Urban Planning Cadastre has been created, which is a platform for the provision of all administrative services in the field of urban planning and a public source of urban planning information. Urban planning documentation comes into force from the moment it is entered into the unified electronic Urban Planning Cadastre and assigned a spatial index | 2.5.1.2.1. Development and submission to Cabinet of Ministers of Ukraine the draft law on amendments to some laws on development and operation of Urban planning cadaster on the state’s level to ensure the following: 1) development of Urban planning cadaster on the state’s level with unified requirements on urban planning documentation data structure; 2) identification of the holder, administration and technical administrator, responsible for Urban planning cadaster on the state’s level upkeep; 3) establishment of authorities and persons, responsible for transmission of data to fill Urban planning cadaster on the state’s level, including persons responsibility for validity and update of the entered data, it’s timely input; 4) public access to Urban planning cadaster on the state’s level (besides restricted access); 5) list and order of submission of the Urban planning cadaster on the state’s level administration services, in particular, via Unified state electronic system in building area; 6) development of urban planning documentation represented in geospatial data and enforcement of urban planning documentation validity only upon the data input to Urban planning cadaster on the state’s level; 7) informational integration of Urban planning cadaster on the state’s level and the State land cadaster, State real estate property rights register, Electronic cultural heritage objects register, State forestry cadaster, State territories and natural reserve funds cadaster, other state information resources, listed by the Cabinet of Ministers of Ukraine by making changes to Urban planning cadaster on the state’s level administration procedure (in case of availability of technical connection); 8) it’s established that urban planning conditions and limitations (including several types of permitting documents) are generated automatically by the Urban planning cadaster on the state’s level software based on the geospatial data documents | Ministry for Communities and Territories Development of Ukraine | The measure was implemented on time, but partially | Partially implemented | 100% 2/2 | 0.0%
2.2. |  | 2.5.1.2.2. Commissioning of Urban planning cadaster on the state’s level to ensure the following: 1) automation and provision of a list of administration services, regulated by urban planning legislation, to be rendered through the Urban planning cadaster on the state’s level; 2) uploading the Urban planning cadaster on the state’s level with urban planning documentation (in particular, accepted for cadaster implementation); 3) maintaining the urban planning state register monitored by Urban Planning cadaster on the state’s level, including submission of urban planning documentation to unified electronic Urban planning cadaster on the state’s level with its further publication and provision of free access (besides restricted data); 4) mutual exchange and integration of data from Urban planning cadaster on the state’s level, State land cadaster, State real estate property rights, Electronic cultural heritage objects register, State forestry cadaster, State territories and natural reserve funds cadaster; geospatial data on territories and administrative territorial units; ecological, forestry, and engineering geological databases; data on engineering transport infrastructure objects, available and planned engineering networks, energy infrastructure linear objects, distribution of engineering network capacities, available free capacities and issued technical conditions; technical inventory and real estate register geospatial data, unified address register; 5) ability of automated development of urban planning limitations and conditions after the online request via Urban planning cadaster on the state’s level geoportal, including several types of permitting documentation | Ministry for Communities and Territories Development of Ukraine | The measure was implemented on time, but partially | Partially implemented
3.1. | ОСР 2.5.1.5 It has been mandated that the requirements of urban development documentation must be considered when drafting and implementing socioeconomic development programs | 2.5.1.5.1. Drafting and submitting to the Cabinet of Ministers of Ukraine a draft law proposing amendments to select laws on the implementation of urban development documentation, which stipulates that: 1) implementation of urban planning documentation by developing, approval and implementation of appropriate plans, which are an integral of urban planning documentation are subject to publication; 2) alignment of socio-economic and budget planning documentation and the actions plans shall be the responsibility of the agency that made the decision to approve the relevant urban development documentation; 3) urban development documentation implementation measures shall be provided with funding for the relevant period; 4) list of measures and funding sources must be indicated in the socio-economic and budget planning documentation in accordance with terms, indicated in the action plan/ | Ministry for Communities and Territories Development of Ukraine | The measure has not been implemented | Not implemented | 0% 0/1 | 0.0%