## Заходи
№ п/п | Назва ОСР | Назва заходу | Головний виконавець | Результати моніторингу (останні) | Відмітка про виконання | % виконаних заходів (повністю та частково) | Оцінка досягнення ОСР
1.1. | ОСР 2.5.5.1 A pilot project has been launched to determine the amount of land tax based on the indicators of mass land appraisal, taking into account international standards of property appraisal for taxation purposes | 2.5.5.1.1. Drafting and submitting to the Cabinet of Ministers of Ukraine a draft law proposing amendments to the Law of Ukraine On Land Appraisal, which has: 1) identifies legal grounds for the central executive body responsible for state land policy to implement the pilot project on the basis of the large-scale land evaluation based on price (cost) of real estate property and the appropriate rights or cost of use of real estate property in accordance with related legal acts; 2) provision of appropriate interaction between the information systems of the State real estate property rights and the State land cadaster when implementing the pilot project on large-scale land evaluation | Ministry of Economy, Environment and Agriculture of Ukraine | The measure was implemented on time, but partially | Partially implemented | 87.5% 7/8 | 0.0%
1.2. |  | 2.5.5.1.2. Drafting and submitting to the Cabinet of Ministers of Ukraine a draft resolution of the Cabinet of Ministers of Ukraine that would define the procedure by which the State Service for Geodesy, Cartography, and Cadaster will carry out the pilot project involving mass appraisal of land based on data on prices (cost) of immovable property and real rights to immovable property or fees paid for using immovable property as part of the relevant legal transactions, and establish: 1) the procedure of operation of the geoinformation system for mass appraisal of land within the State Land Cadaster; 2) the method of building and calibrating the mathematical-statistical model of mass appraisal of land, testing the model, and the procedure for performing quality control and updating the results of appraisal; 3) the procedure of data interaction between information systems of the State Register of Real Rights to Immovable Property and the State Land Cadaster during implementation of the pilot project involving mass appraisal of land; 4) the procedure for providing stakeholders with information about the mass appraisal of land and the amount of land tax and/or rent for land under state or municipal ownership determined on the basis of such appraisal, via a public cadastral map. | Ministry of Economy, Environment and Agriculture of Ukraine | The measure was implemented on time, but partially | Partially implemented
1.3. |  | 2.5.5.1.3. Preparing a statement of work (“technical assignment”) for creation of the geoinformation system for mass appraisal of land within the State Land Cadaster | State Service of Ukraine for Geodesy, Cartography and Cadastre | The measure was not implemented on time and in full | Implemented
1.4. |  | 2.5.5.1.4. Arranging the development of software for the geoinformation system for mass appraisal of land within the State Land Cadaster | Ministry of Economy, Environment and Agriculture of Ukraine | The measure was not implemented on time and in full | Implemented
1.5. |  | 2.5.5.1.5. Arranging the launch of pilot operation of the geoinformation system for mass appraisal of land within the State Land Cadaster | Ministry of Economy, Environment and Agriculture of Ukraine | The measure was implemented on time and in full | Implemented
1.6. |  | 2.5.5.1.6. Arranging the launch of commercial operation of the geoinformation system for mass appraisal of land within the State Land Cadaster | Ministry of Economy, Environment and Agriculture of Ukraine | The measure was not implemented on time and in full | Implemented
1.7. |  | 2.5.5.1.7. Preparation of a report on implementation of the pilot project on large-scale land evaluation | Ministry of Economy, Environment and Agriculture of Ukraine | The measure was not implemented on time and in full | Implemented
1.8. |  | 2.5.5.1.8. Development nad submission of the draft law on amendments to the Law of Ukraine ‘On Land evaluation’ to Cabinet of Ministers of Ukraine with consideration of results of pilot project on large-scale land evaluation, which ensures the following: 1) establishment of large-scale land evaluation as a method of evaluation; 2) establishment of obligation to conduct an updated large-scale land evaluation no less than 2 times a year; 3) ensures an obligation to provide the stakeholders with information on large-scale land evaluation and established land tax and/or rent fee for renting the stae-owned or communal-owned land plots | Ministry of Economy, Environment and Agriculture of Ukraine | The measure has not been implemented | Not implemented
2.1. | ОСР 2.5.5.2 The Tax Code of Ukraine and the Law of Ukraine On Land Appraisal have been amended to establish the rates of rent for state-owned and municipally owned land plots based on their market value | 2.5.5.2.1. Drafting and submitting to the Cabinet of Ministers of Ukraine a draft law proposing amendments to the Tax Code of Ukraine, which provides for: 1) a transition to calculating the amount of land tax and rent for land plots under state or municipal ownership based on indicators of mass appraisal of land; 2) the procedure for calculating the rates of land tax and rent for land plots under state or municipal ownership when indicators of mass appraisal of land are used. | Ministry of Finance of Ukraine | Implementation of the measure has not started | Не підлягають виконанню | 0% 0/1 | 0.0%