## Заходи
№ п/п | Назва ОСР | Назва заходу | Головний виконавець | Результати моніторингу (останні) | Відмітка про виконання | % виконаних заходів (повністю та частково) | Оцінка досягнення ОСР
1.1. | ОСР 2.5.6.1 Mechanisms have been introduced to create incentives for local self-government bodies to quickly develop and approve planning documentation for the entire territory of territorial communities (both within population centers and outside their limits) | 2.5.6.1.1. Performing financial and economic calculations of the amount of funding required for a state budget subvention to local budget for the creation of comprehensive plans of spatial development of territories of territorial communities | Ministry for Communities and Territories Development of Ukraine | The measure was implemented on time and in full | Implemented | 45.5% 5/11 | 0.0%
1.2. |  | 2.5.6.1.2. Submitting proposals during development of the Draft Law of Ukraine On the State Budget of Ukraine for 2024, providing for the requisite amount of funding for the subvention calculated as part of the activity indicated in subclause 2.5.6.1.1 out of the state budget for local budgets for the creation of comprehensive plans of spatial development of territories of territorial communities | Ministry for Communities and Territories Development of Ukraine | The measure was implemented on time, but partially | Partially implemented
1.3. |  | 2.5.6.1.4. Drafting and submitting to the Cabinet of Ministers of Ukraine a draft resolution of the Cabinet of Ministers of Ukraine proposing amendments to the Procedure and Conditions for Granting State Budget Subventions to Local Budgets for the Creation of Comprehensive Spatial Development Plans of Territories of Territorial Communities, approved by the resolution of the Cabinet of Ministers of Ukraine dated July 28, 2021, No. 853, concerning the simplification of the conditions for the grant of the subvention by eliminating the requirement that the community must have an up-to-date cartographic substrate in digital form | Ministry for Communities and Territories Development of Ukraine | The measure has not been implemented | Not implemented
1.4. |  | 2.5.6.1.5. Performing financial and economic calculations of the amount of funding required for a state budget subvention to local budget for the creation of comprehensive plans of spatial development of territories of territorial communities | Ministry for Communities and Territories Development of Ukraine | The measure was implemented on time and in full | Implemented
1.5. |  | 2.5.6.1.6. Submitting proposals during development of the Draft Law of Ukraine On the State Budget of Ukraine for 2025, providing for the requisite amount of funding for the subvention calculated as part of the activity indicated in subclause 2.5.6.1.5 out of the state budget for local budgets for the creation of comprehensive plans of spatial development of territories of territorial communities | Ministry for Communities and Territories Development of Ukraine | The measure was implemented on time, but partially | Partially implemented
1.6. |  | 2.5.6.1.7. Monitoring of draft laws that propose amendments to the Land Code of Ukraine that would abolish the creation of comprehensive plans of spatial development of the territory of territorial communities and determination on this basis of the functional zoning of the territory and land usage restrictions as mandatory preconditions for establishing and modifying the designated purpose of land plots | Ministry of Economy, Environment and Agriculture of Ukraine | The measure was implemented on time and in full | Implemented
1.7. |  | 2.5.6.1.8. Preparing proposals regarding approval with reservations / rejection of the draft laws indicated in subclause 2.5.6.1.7 | Ministry of Economy, Environment and Agriculture of Ukraine | Implementation of the measure has not started | Не підлягають виконанню
1.8. |  | 2.5.6.1.9. Preparing critical comments and proposals, positions regarding the rejection of the draft laws indicated in subclause 2.5.6.1.7 | Ministry of Economy, Environment and Agriculture of Ukraine | Implementation of the measure has not started | Не підлягають виконанню
1.9. |  | 2.5.6.1.10. Supporting the consideration of the draft laws indicated in subclause 2.5.6.1.7 by committees of the Parliament of Ukraine | Ministry of Economy, Environment and Agriculture of Ukraine | Implementation of the measure has not started | Не підлягають виконанню
1.10. |  | 2.5.6.1.11. Preparing proposals regarding the expediency of the exercise of the president’s veto right with respect to the laws indicated in subclause 2.5.6.1.7, which have been passed by the Parliament of Ukraine | Ministry of Economy, Environment and Agriculture of Ukraine | Implementation of the measure has not started | Не підлягають виконанню
1.11. |  | 2.5.6.1.12. Provisions for development of no less than 25 comprehensive territorial communities’ spatial development plans | Ministry for Communities and Territories Development of Ukraine | The measure has not been implemented | Not implemented