## Заходи
№ п/п | Назва ОСР | Назва заходу | Головний виконавець | Результати моніторингу (останні) | Відмітка про виконання | % виконаних заходів (повністю та частково) | Оцінка досягнення ОСР
1.1. | ОСР 2.5.7.1 Amendments have been made to the land legislation, which provide for transparent mechanisms for the sale of state-owned and municipally owned land plots or rights to them through electronic auctions | 2.5.7.1.1. Drafting and submitting to the Cabinet of Ministers of Ukraine a draft law defining the maximum area of land plots under state or municipal ownership, which are occupied by immovable properties (buildings, structures) owned by individuals or legal entities, for the purposes of their sale or tenancy outside of the competitive process | Ministry for Communities and Territories Development of Ukraine | The measure was implemented on time, but partially | Partially implemented | 33.3% 2/6 | 0.0%
1.2. |  | 2.5.7.1.2. Monitoring of the draft laws that propose amendments to the Land Code of Ukraine with respect to the mechanisms of selling land plots under state or municipal ownership or rights to them through electronic auctions, particularly under martial law conditions | Ministry of Economy, Environment and Agriculture of Ukraine | The measure was implemented on time and in full | Implemented
1.3. |  | 2.5.7.1.3. Preparing proposals regarding approval with reservations / rejection of the draft laws indicated in subclause 2.5.7.1.2 | Ministry of Economy, Environment and Agriculture of Ukraine | Implementation of the measure has not started | Не підлягають виконанню
1.4. |  | 2.5.7.1.4. Preparing critical comments and proposals, positions regarding the rejection of the draft laws indicated in subclause 2.5.7.1.2 | Ministry of Economy, Environment and Agriculture of Ukraine | Implementation of the measure has not started | Не підлягають виконанню
1.5. |  | 2.5.7.1.5. Supporting the consideration of the draft laws indicated in subclause 2.5.7.1.2 by committees of the Parliament of Ukraine | Ministry of Economy, Environment and Agriculture of Ukraine | Implementation of the measure has not started | Не підлягають виконанню
1.6. |  | 2.5.7.1.6. Preparing proposals regarding the expediency of the exercise of the president’s veto right with respect to the laws indicated in subclause 2.5.7.1.2, which have been passed by the Parliament of Ukraine | Ministry of Economy, Environment and Agriculture of Ukraine | Implementation of the measure has not started | Не підлягають виконанню