## Заходи
№ п/п | Назва ОСР | Назва заходу | Головний виконавець | Результати моніторингу (останні) | Відмітка про виконання | % виконаних заходів (повністю та частково) | Оцінка досягнення ОСР
1.1. | ОСР 1.1.5.1 In the sectors of education, science, healthcare, administrative, social, and utility services as well as government regulation of the economy, the existing corrupt practices are being ousted by convenient legitimate ways of satisfying the needs of individuals or legal entities, which primarily involve: identifying the most widespread corrupt practices and the reasons why they exist; improving the legitimate ways of satisfying the needs of individuals or legal entities, which give them certainty that they are guaranteed achieve the desired and legitimate result swiftly and comfortably; providing the appropriate normative, legal, organizational, and financial framework for coordinated efforts by government agencies and local self-government bodies aimed at simplifying the procedures for providing administrative, social, utility, and other services, as well as protecting business entities against unscrupulous behavior of these agencies; aligning the system of government agencies and local self-government bodies with the administrative-territorial system; launching electronic services and enhancing the transparency and accountability of processes involved in interactions between the state and the population and business community | 1.1.5.1.1. Conducting a comprehensive study to identify 10 of the most corruption-plagued sectors (using sociological, analytical, academic, and other sources of information) | National Agency on Corruption Prevention | The measure was implemented on time and in full | Implemented | 88.9% 8/9 | 0.0%
1.2. |  | 1.1.5.1.2. Conducting a comprehensive study (studies) to identify the most widespread and most economically detrimental corrupt practices in the 10 most corruption-plagued sectors | National Agency on Corruption Prevention | The measure has not been implemented | Not implemented
1.3. |  | 1.1.5.1.3. Conducting 10 analytical studies (5 per year) dedicated to: 1) a detailed study of the most widespread or the most economically detrimental corrupt practices and causes of their existence in the 10 most corruption-plagued sectors; 2) finding and modeling the implementation of convenient and legitimate approaches to satisfying the relevant needs of individuals or legal entities as opposed to the existing corrupt practices (particularly by launching electronic services) | National Agency on Corruption Prevention | The measure was implemented on time and in full | Implemented
1.4. |  | 1.1.5.1.4. Annual discussion of the conclusions and recommendations outlined in analytical studies with the participation of representatives of government agencies, NGOs, international organizations, international technical assistance projects, and the academic community | National Agency on Corruption Prevention | The measure was implemented on time and in full | Implemented
1.5. |  | 1.1.5.1.5. Improving the legitimate approaches to satisfying the needs of individuals and legal entities, taking into account the recommendations presented in analytical studies (particularly by launching electronic services, enhancing the transparency and accountability of processes pertaining to interactions between the state and the population and businesses, using re-engineering procedures, as well as implementing technological tools for the elimination of typical corruption risks: modules for random allocation of materials for specific administrative actions, technologies that implement the principle of extraterritorial examination of specific materials and decision-making, artificial intelligence-powered expert systems for aggregation and assessment of big data arrays, etc.) | Central bodies of executive power, which form or implement state policy in the areas most affected by corruption | The measure was implemented on time, but partially | Partially implemented
1.6. |  | 1.1.5.1.6. Supporting the consideration of the Draft Law of Ukraine On the Procedure for Deciding Matters of the Administrative-Territorial System of Ukraine (registration number 4664 dated June 28, 2021) in the Parliament of Ukraine (particularly if the President of Ukraine vetoes the draft law) | Ministry for Communities and Territories Development of Ukraine | The measure was implemented on time and in full | Implemented
1.7. |  | 1.1.5.1.7. Drafting and supporting the consideration of bylaw normative legal acts needed for implementation of the law mentioned in subclause 1.1.5.1.6 | Ministry for Communities and Territories Development of Ukraine | The measure was implemented on time and in full | Implemented
1.8. |  | 1.1.5.1.8. Aligning normative legal acts with the law indicated in subclause 1.1.5.1.6 | Ministry for Communities and Territories Development of Ukraine | The measure was implemented on time and in full | Implemented
1.9. |  | 1.1.5.1.9. Conducting an analytical study into aligning the system of government agencies and local self-government bodies with the administrative-territorial system, and elaborating recommendations on how to improve the legislation | Ministry for Communities and Territories Development of Ukraine | The measure was implemented on time and in full | Implemented
2.1. | ОСР 1.1.5.2 Citizens refrain from corrupt practices owing to communications and awareness raising campaign aimed at raising awareness about the availability of electronic services, simplifying procedures, and so forth | 1.1.5.2.1. Forming an interagency working group to exchange information about initiatives and services alternative to corrupt practices, particularly electronic or streamlined services implemented by executive authorities | National Agency on Corruption Prevention | The measure was not implemented on time and in full | Implemented | 100% 6/6 | 0.0%
2.2. |  | 1.1.5.2.2. Developing informational materials as part of the launch of services and tools for individuals and/or legal entities, which serve as convenient and legitimate methods of satisfying needs as an alternative to corrupt practices, describing the procedure for using such services, in particular: 1) user guides published on the official website, on social media (if any); 2) infographics; 3) introductory videos, screen casts; 4) other thematic materials. | National Agency on Corruption Prevention | The measure was implemented late and partially | Partially implemented
2.3. |  | 1.1.5.2.3. Supporting the development of the design of the pilot communications and awareness raising campaign devoted to covering the successes of the state in combating corruption by creating convenient legitimate alternatives as opposed to corrupt practices | National Agency on Corruption Prevention | The measure was implemented on time and in full | Implemented
2.4. |  | 1.1.5.2.4. Conducting the pilot communications and awareness raising campaign devoted to covering the successes of the state in combating corruption by creating convenient legitimate alternatives as opposed to corrupt practices | National Agency on Corruption Prevention | The measure was implemented on time, but partially | Partially implemented
2.5. |  | 1.1.5.2.6. Conducting the joint communications and awareness raising campaign devoted to electronic services as an alternative to corrupt practices | Ministry of Digital Transformation of Ukraine | The measure was not implemented on time and in full | Implemented
2.6. |  | 1.1.5.2.8. Conducting the joint communications and awareness raising campaign devoted to the new principles of the administrative process, particularly through DIIA centers (administrative service centers) | Ministry of Justice of Ukraine | The measure was implemented on time and in full | Implemented
3.1. | ОСР 1.1.5.3 Representatives of the business community and the Business Ombudsman Council are active contributors to the process of minimizing corruption risks and instituting effective regulation, which promotes economic growth and mobilization of investments | 1.1.5.3.1. Amending the memorandum between the National Agency and the Institution of the Business Ombudsman dated September 22, 2016 on cooperation and information exchange, pertaining to the exchange of information about the most widespread corrupt practices in interactions between businesses and the public sector | National Agency on Corruption Prevention | The measure was implemented on time and in full | Implemented | 100% 3/3 | 0.0%
3.2. |  | 1.1.5.3.2. Periodically (at least twice a year) exchanging information about the most widespread corrupt practices in interactions between businesses and the public sector | Business Ombudsman's Council | The measure was implemented on time and in full | Implemented
3.3. |  | 1.1.5.3.3. Using the information received by the National Agency from the Business Ombudsman Council: 1) for the purposes of modeling the implementation of convenient and legitimate approaches to satisfying the relevant needs of individuals or legal entities as opposed to the existing corrupt practices (particularly by launching electronic services); 2) while developing and approving anticorruption programs; 3) while conducting anticorruption expert examinations. | National Agency on Corruption Prevention | The measure was implemented on time and in full | Implemented