## Заходи
№ п/п | Назва ОСР | Назва заходу | Головний виконавець | Результати моніторингу (останні) | Відмітка про виконання | % виконаних заходів (повністю та частково) | Оцінка досягнення ОСР
1.1. | ОСР 2.7.3.1 The electronic healthcare system is integrated with other state databases outside the healthcare sector, which ensures completeness, consistency and additional data verification, as well as functionality for automation of processes; the electronic healthcare system is the primary source of information about medical services provided in Ukraine, which serves as a basis for decisions to perform calculations for the medical guarantees program, make managerial decisions, and generate the relevant statistics | 2.7.3.1.1. Drafting and submitting to the Cabinet of Ministers of Ukraine the draft resolution of the Cabinet of Ministers of Ukraine on amendments to the procedure of operation of the electronic healthcare system to the effect that: 1) the electronic healthcare system is the primary source of information about medical services provided in Ukraine, which serves as a basis for decisions to perform calculations for the medical guarantees program, make managerial decisions, and generate the relevant statistics; 2) the electronic healthcare system is used for electronic document exchange in the field of healthcare services; 3) medical charts of patients shall be maintained through the electronic healthcare system. | Ministry of Health of Ukraine | The measure was implemented on time and in full | Implemented | 100% 2/2 | 0.0%
1.2. |  | 2.7.3.1.2. Ensuring interaction and compatibility of medical care electronic system with the following: 1) Unified state demographic register; 2) State register of register of civil status acts of citizens; 3) State register private entrepreneurs – taxpayers; 4) Unified state register of legal entities, private entrepreneurs and public organizations; 5) information systems of the Ministry of Social Policy of Ukraine; 6) Electronic verification and monitoring information analytical system; 7) State register of medical products of Ukraine. | Ministry of Health of Ukraine | The measure was implemented on time and in full | Implemented
2.1. | ОСР 2.7.3.2 The electronic healthcare system contains the results of preventative and compulsory medical checkups | 2.7.3.2.1. Developing a draft order of the Ministry of Health on amendments to the Procedure for Conducting Medical Examinations of Employees of Specific Categories, according to which the results of all previous compulsory and periodic preventative medical examinations must be recorded in the electronic healthcare system | Ministry of Health of Ukraine | The measure was implemented late and partially | Partially implemented | 100% 6/6 | 0.0%
2.2. |  | 2.7.3.2.2. Holding a public discussion of the draft order indicated in subclause 2.7.3.2.1, and ensuring its revision (if needed) | Ministry of Health of Ukraine | The measure was implemented on time, but partially | Partially implemented
2.3. |  | 2.7.3.2.3. Issuing the revised order indicated in subclause 2.7.3.2.1, supporting its state registration with the Ministry of Justice | Ministry of Health of Ukraine | The measure was implemented late and partially | Partially implemented
2.4. |  | 2.7.3.2.4. Developing and submitting to the Cabinet of Ministers of Ukraine a draft resolution of the Cabinet of Ministers of Ukraine on amendments to the Procedure for the Functioning of the Electronic Healthcare System on entering data on the results of mandatory preliminary and periodic preventive medical examinations into the electronic healthcare system. | Ministry of Health of Ukraine | The measure was implemented on time and in full | Implemented
2.5. |  | 2.7.3.2.5. Development of coding rules for conducted previous and periodic medical examinations in the electronic medica care system to ensure valid accounting of medical services, provided to patients, in particular, involving the use of national classifiers and directories | Ministry of Health of Ukraine | The measure was not implemented on time and in full | Implemented
2.6. |  | 2.7.3.2.6. Preparation and publishing of two annual analytical reports on current status of reflection of previous and periodic medical examinations in electronic medical care system | Ministry of Health of Ukraine | The measure was implemented on time and in full | Implemented
3.1. | ОСР 2.7.3.3 Tools for assessing the functional status of a person according to the adapted International Classification of Functioning, Disability and Health have been introduced into the electronic healthcare system | 2.7.3.3.1. Development and submission to Cabinet of Ministers of Ukraine a draft regulation of Cabinet of Ministers of Ukraine on amendments to the electronic medical care system operation procedure on the following: 1) electronic medical records on the system operational status involving the use of the National classified (NC) 030:2022 ‘Operation, vital functions limitations and health classifier’ are uploaded to electronic medical care system; 2) data from electronic medical care systems used by the person to obtain appropriate services based on individual rehabilitation plan with the use of the National classifier (NC) 030:2022 ‘Operation, vital functions limitations and health classifier’. | Ministry of Health of Ukraine | The measure was implemented on time and in full | Implemented | 100% 4/4 | 0.0%
3.2. |  | 2.7.3.3.4. Approving the statement of work (“technical assignment”) for the expansion of the functionality of the electronic healthcare system with respect to: 1) implementation of the National classifier NC 030:2022 ‘Operation, vital functions limitations and health classifier’; 2) uploading electronic medical records on person’s performance involving the use of the National classifier NC 030:2022 ‘Operation, vital functions limitations and health classifier’; 3) possibility to use data from electronic medical care system for the person to obtain appropriate services based on individual rehabilitation plan involving the use of the National classifier NC 030:2022 ‘Operation, vital functions limitations and health classifier’. | Ministry of Health of Ukraine | The measure was implemented on time and in full | Implemented
3.3. |  | 2.7.3.3.5. Developing software for expansion of the functionality of the electronic healthcare system in accordance with subclause 2.7.3.3.4 | Ministry of Health of Ukraine | The measure was implemented on time and in full | Implemented
3.4. |  | 2.7.3.3.6. Putting into operation the expanded functionality of the electronic healthcare system in accordance with subclause 2.7.3.3.4 | Ministry of Health of Ukraine | The measure was implemented on time and in full | Implemented
4.1. | ОСР 2.7.3.4 The functions of providing the relevant medical opinion on determining the disability group and social assistance based on such an opinion are divided between state bodies in order to reduce corruption risks | 2.7.3.4.1. Development and submission to Cabinet of Ministers of Ukraine a draft law on amendments to laws of Ukraine with consideration of proposals, submitted by the Ministry of Social Policy of Ukraine, which indicates the following: 1) status of a person with a disability or similar status can be identified on the basis of performance and personal needs, performed with the use of the National classifier NC 030:2022 ‘Operation, vital functions limitations and health classifier’; 2) status of a person with a disability or similar status can be established for a period, identified in the legislation, an in case of amendments via special procedure appropriate rights for social support can be reviewed; 3) functions of evaluation and adopting the appropriate decision on person’s conditions and any performance limitations, identification of needs and establishment of the scope of social support are distributed among the entities, conducting evaluation and identification of needs to decrease corruption risks; 4) persons status evaluations become the reason for identification of needs and scope of social support are stored in electronic form with the use of functional capabilities of software products; 5) duty to keep records in electronic form while establishing the person’s performance limitation level, identification of needs and scope of social support in accordance with the individual needs; 6) duty to perform appropriate evaluation and the subjects responsible for its performance; 7) duty to publish impersonalized reasons for making decisions on establishment of scope of support and statistic analytical data on decisions made; 8) requirements to subjects performing evaluation of the performance status and individual needs used as a basis for establishment of scope of support; 9) right of a person subject to evaluation of performance and individual needs to appeal on the decision made regarding the establishment of the status of a person with a disability of similar status and establishment of the scope of appropriate support. | Ministry of Health of Ukraine | The measure was implemented on time and in full | Implemented | 84.6% 11/13 | 0.0%
4.2. |  | 2.7.3.4.2.(1) Drafting and submitting to the Cabinet of Ministers of Ukraine the draft normative legal acts proposing amendments to the normative legal acts of the Cabinet of Ministers of Ukraine in order to align them with the law indicated in subclause 2.7.3.4.1 | Ministry of Health of Ukraine | The measure was implemented on time and in full | Implemented
4.3. |  | 2.7.3.4.2.(2) Drafting and submitting to the Cabinet of Ministers of Ukraine the draft normative legal acts proposing amendments to the normative legal acts of the Cabinet of Ministers of Ukraine in order to align them with the law indicated in subclause 2.7.3.4.1 | Ministry of Social Policy, Family and Unity of Ukraine | The measure was implemented on time and in full | Implemented
4.4. |  | 2.7.3.4.3.(1) Drafting normative legal acts that propose amendments to the normative legal acts of the Ministry of Social Policy and the Ministry of Health in order to align them with the law indicated in subclause 2.7.3.4.1 | Ministry of Health of Ukraine | The measure was implemented on time and in full | Implemented
4.5. |  | 2.7.3.4.3.(2) Drafting normative legal acts that propose amendments to the normative legal acts of the Ministry of Social Policy and the Ministry of Health in order to align them with the law indicated in subclause 2.7.3.4.1 | Ministry of Social Policy, Family and Unity of Ukraine | The measure was not implemented on time and in full | Implemented
4.6. |  | 2.7.3.4.4.(1) Holding a public discussion of the draft normative legal acts indicated in subclause 2.7.3.4.3, and ensuring their revision (if needed), issuance, and submission for state registration | Ministry of Health of Ukraine | The measure was implemented on time, but partially | Partially implemented
4.7. |  | 2.7.3.4.4.(2) Holding a public discussion of the draft normative legal acts indicated in subclause 2.7.3.4.3, and ensuring their revision (if needed), issuance, and submission for state registration | Ministry of Social Policy, Family and Unity of Ukraine | The measure has not been implemented | Not implemented
4.8. |  | 2.7.3.4.5.(1) Supporting the state registration of draft normative legal acts indicated in subclause 2.7.3.4.3 and their official publication | Ministry of Health of Ukraine | The measure was implemented on time and in full | Implemented
4.9. |  | 2.7.3.4.5.(2) Supporting the state registration of draft normative legal acts indicated in subclause 2.7.3.4.3 and their official publication | Ministry of Social Policy, Family and Unity of Ukraine | The measure has not been implemented | Not implemented
4.10. |  | 2.7.3.4.6. Development and adoption of normative legislative act on electronic information system operation under the establishment of disability status and support of people with limited daily functioning as a component of Unified social support information system: 1) additional person verification function; 2) identification and assignment of required social support to a person; 3) reproduction of unique record number in the Unified state demographic register; 4) deactivation of personal data in case of person’s death, departure, etc.; 5) interaction with other state registers and databases. | Ministry of Social Policy, Family and Unity of Ukraine | The measure was implemented on time, but partially | Partially implemented
4.11. |  | 2.7.3.4.7. Drafting and approving the statement of work (“technical assignment”) for the expansion of the functionality of the electronic healthcare system indicated in subclause 2.7.3.4.6 | Ministry of Social Policy, Family and Unity of Ukraine | The measure was implemented on time, but partially | Partially implemented
4.12. |  | 2.7.3.4.8. Developing software for expansion of the functionality of the electronic healthcare system indicated in subclause 2.7.3.4.6 | Ministry of Social Policy, Family and Unity of Ukraine | The measure was implemented on time, but partially | Partially implemented
4.13. |  | 2.7.3.4.9. Putting into test operation electronic healthcare system indicated in subclause 2.7.3.4.6 | Ministry of Social Policy, Family and Unity of Ukraine | The measure was implemented on time, but partially | Partially implemented
5.1. | ОСР 2.7.3.5 The electronic register of sick leaves has been put into commercial operation | 2.7.3.5.1. Holding a semiannual monitoring of the proper functioning of the electronic register of sick leaves, which must necessarily involve studying the status of compliance with the requirements pertaining to: 1) issuance of sick leaves of insured persons in electronic form only; 2) issuance of an extract from the electronic register of sick leaves as the sole proof of the insured person’s incapacity for work. | Pension Fund of Ukraine | The measure was implemented on time and in full | Implemented | 100% 1/1 | 0.0%