## Заходи
№ п/п | Назва ОСР | Назва заходу | Головний виконавець | Результати моніторингу (останні) | Відмітка про виконання | % виконаних заходів (повністю та частково) | Оцінка досягнення ОСР
1.1. | ОСР 2.7.4.1 A publicly accessible single web portal of vacancies at state and municipal healthcare institutions is functioning | 2.7.4.1.1. Drafting and submitting to the Cabinet of Ministers of Ukraine a draft resolution of the Cabinet of Ministers of Ukraine on approval of the Regulation on the single website of vacancies at state and municipal healthcare institutions, which stipulates that: 1) open access to the website shall be granted in keeping with the requirements of legislation on the protection of personal data; 2) the website must contain complete information about all available vacancies along with the names and addresses of the relevant healthcare institutions; 3) the website must publish information about the dates of the competitive selection process, the deadline and address for submission of the application for the position; 4) recruitment for vacant positions (including managerial positions) at state and municipal healthcare institutions is carried out exclusively through the website; | Ministry of Health of Ukraine | The measure was implemented on time and in full | Implemented | 100% 4/4 | 0.0%
1.2. |  | 2.7.4.1.2. Developing and approving a statement of work (“technical assignment”) for the creation of the single website of vacancies at state and municipal healthcare institutions | Ministry of Health of Ukraine | The measure was implemented on time and in full | Implemented
1.3. |  | 2.7.4.1.3. Developing the design of the single web portal of vacancies at state and municipal healthcare institutions | Ministry of Health of Ukraine | The measure was implemented on time and in full | Implemented
1.4. |  | 2.7.4.1.4. Launching the single web portal of vacancies at state and municipal healthcare institutions | Ministry of Health of Ukraine | The measure was implemented on time and in full | Implemented
2.1. | ОСР 2.7.4.2 Recruitment for managerial positions at state and municipal healthcare institutions shall be carried out by competitive selection committees that must include representatives of the public, in accordance with the established list of essential skills, competencies, and evaluation criteria; the range of public associations that can delegate their representatives to the competitive selection committees has been expanded, and the principles of transparency and openness in their work have been ensured | 2.7.4.2.1. Drafting and submitting to the Cabinet of Ministers of Ukraine a draft resolution of the Cabinet of Ministers of Ukraine on amendments to the Procedure for conducting a competitive selection process to fill the position of the manager of a state or municipal healthcare institution, which stipulates that: 1) one half of the seats on competitive selection committees shall be taken by representatives of NGOs in matters relating to healthcare and/or prevention of corruption and anticorruption activities; 2) the qualification requirements for managerial positions at state and municipal healthcare institutions shall be established by said Procedure; 3) there shall be a clear list of qualification criteria for applicants for managerial positions at state and municipal healthcare institutions, which must include professional competency, managerial skills, and integrity; 4) professional competency and managerial skills must be evaluated using a scoring system by each member of the competitive selection committee; 5) conformity to the criterion of integrity shall be assessed according to the standard of “reasonable doubt”; 6) a decision of the competitive selection committee to the effect that an applicant meets the criterion of integrity shall be deemed approved if the majority of committee members representing the community have voted in favor of this decision, and where the votes have tied the votes of committee members representing the community shall prevail. | Ministry of Health of Ukraine | The measure was not implemented on time and in full | Implemented | 100% 1/1 | 0.0%