## Заходи
№ п/п | Назва ОСР | Назва заходу | Головний виконавець | Результати моніторингу (останні) | Відмітка про виконання | % виконаних заходів (повністю та частково) | Оцінка досягнення ОСР
1.1. | ОСР 2.7.6.1 The functions of formulation and implementation of state policy in the sector of education and science, in particular as regards management of state-owned facilities, inspection and supervision activities, and provision of administrative services are segregated among different institutions | 2.7.6.1.1. Drafting and submitting to the Cabinet of Ministers of Ukraine the draft law on amendments to the Laws of Ukraine On Education, On Complete General Secondary Education, On Higher Education, On Professional (Vocational) Education, On Professional Pre-university Education, which: 1) stipulates that the powers of licensing of educational activities in higher education and state oversight (control) over compliance with the licensing conditions have been delegated from the Ministry of Education and Science to the State Education Quality Service; 2) stipulates that licensing requirements apply only to educational activities under educational programs that envisage the awarding of a professional qualification in occupations that are subject to additional regulation according to the list approved by the Ministry of Education and Science. | Ministry of Education and Science of Ukraine | The measure was implemented on time, but partially | Partially implemented | 100% 4/4 | 0.0%
1.2. |  | 2.7.6.1.2. Drafting and submitting to the Cabinet of Ministers of Ukraine a draft law that proposes removing Part 2 of Article 75 of the Fundamentals of Ukrainian Healthcare Legislation on the approval of curricula and programs of training, reskilling, and professional development for medical and pharmaceutical professional and rehabilitation specialists of the Ministry of Health | Ministry of Health of Ukraine | The measure was not implemented on time and in full | Implemented
1.3. |  | 2.7.6.1.3. Drafting and submitting to the Cabinet of Ministers of Ukraine a draft law that proposes removing Section VI of the Law of Ukraine On the Prioritization of Social Development of Villages and the Agribusiness Sector in the National Economy pertaining to academic and human resources | Ministry of Education and Science of Ukraine | The measure was not implemented on time and in full | Implemented
1.4. |  | 2.7.6.1.4. Conducting an analytical study to identify instances of overlapping functions of government agencies in the sector of education under the Law of Ukraine On Complete General Secondary Education, including the powers of the National Agency for Higher Education Quality Assurance, its territorial offices, and local state administrations to analyze the work of local self-government agencies in the sector of education and make amendments to legislation (if needed) | Ministry of Education and Science of Ukraine | The measure was not implemented on time and in full | Implemented
2.1. | ОСР 2.7.6.2 Public funds are allocated among institution of higher education and research institutions in a transparent and effective manner based on objective, pre-determined procedures and performance indicators | 2.7.6.2.1. Drafting and submitting to the Cabinet of Ministers of Ukraine a draft law proposing to amend the Budget Code of Ukraine, specifically by: 1) amending subclause “c” of Clause 7 of Part 1 of Article 87 of the Budget Code of Ukraine to the effect that expenditures out of the state budget include expenditures for the pursuit of higher education by individuals who earned the right to obtain a higher education at the expense of the state budget (including on the conditions of a government contract) on a competitive basis; the allocation of expenditures among institutions of higher education shall be carried out according to the formula developed by the Ministry of Education and Science and approved by the Cabinet of Ministers of Ukraine; 2) amending Clause 46 of Section VI “Final and Transitional Provisions” of the Budget Code of Ukraine with respect to the list of parameters of the formula of allocation of state budget expenditures for higher education among institutions of higher education; 3) providing for an exhaustive list of cases of allocation of expenditures out of the state budget and local budgets for the funding of academic and engineering research and projects without the use of competitive processes. | Ministry of Education and Science of Ukraine | The measure has not been implemented | Not implemented | 40% 2/5 | 0.0%
2.2. |  | 2.7.6.2.2. Drafting and submitting to the Cabinet of Ministers of Ukraine a draft law proposing amendments to the Law of Ukraine On Higher Education, which stipulates that: 1) expenditures out of the state budget for higher education shall be allocated for institutions of higher education where the cost of educational services is established in keeping with the legislation on the indicative prime cost; 2) the amount of expenditures out of the state budget for higher education shall be allocated among institutions of higher education according to the formula developed by the Ministry of Education and Science and approved by the Cabinet of Ministers of Ukraine. | Ministry of Education and Science of Ukraine | The measure was not implemented on time and in full | Implemented
2.3. |  | 2.7.6.2.3. Arranging an analytical study to update specific performance indicators used in the formula of allocation of the amount expenditures out of the state budget for higher education among institutions of higher education | Ministry of Education and Science of Ukraine | The measure has not been implemented | Not implemented
2.4. |  | 2.7.6.2.4. Holding a presentation of the report on the findings of the analytical study indicated in subclause 2.7.6.2.3, followed by its expert discussion | Ministry of Education and Science of Ukraine | The measure has not been implemented | Not implemented
2.5. |  | 2.7.6.2.5. Drafting and submitting to the Cabinet of Ministers of Ukraine a draft resolution of the Cabinet of Ministers of Ukraine on amendments to the Formula of allocation of expenditures out of the state budget for higher education among institutions of higher education, to the extent of updating the specific performance indicators used within the Formula, taking into account the findings of the analytical study indicated in subclause 2.7.6.2.3 | Ministry of Education and Science of Ukraine | The measure was implemented on time, but partially | Partially implemented