## Заходи
№ Напрямку | Напрямок | Проблема | № ОСР | Назва ОСР | № Заходу | Назва заходу | Дата початку | Дата завершення | Головний виконавець | Співвиконавці | Джерела фінансування | Обсяги фінансування, тис.грн. | Показник (індикатор) виконання | Стан виконання | Статус виконання | Оцінка досягнення ОСР
1.3 | Resolution of the conflicts of interest, observance of general restrictions and bans, rules of ethical conduct | 1.3.1 Flaws of legislation and the lack of effective risk-based mechanisms for detecting conflicts of interest limit the ability to minimize corruption by preventing and resolving conflicts of interest. | 1.3.1.1 | The legislative definitions of the terms "real conflict of interest", "potential conflict of interest", and "private interest" have been clarified to simplify their understanding and application. | 1.3.1.1.1 | Drafting and submitting to the Cabinet of Ministers of Ukraine a draft law that proposing to introduce a new approach to defining the terms “potential conflicts of interest” and “real conflict of interest”, which makes it possible to clearly differentiate between the two concepts (specifically by updating or modifying such an attribute as the conflict between a private interest and official duties), refine the concept of “private interest”, and introduce the definition of the concept of “public interest” | 01.03.2023 | 31.08.2023 | National Agency on Corruption Prevention |  | state budget | within the established budget allocations for the relevant year | The draft law has been submitted to the Parliament of Ukraine. | На виконання заходів, передбачених п. п. 1.3.1.1.1 та п. п. 1.3.1.4.1 додатка 2 до Державної антикорупційної програми на 2023 - 2025 роки, НАЗК розробило законопроекти: 1) "Про внесення змін до Закону України «Про запобігання корупції» щодо спрощення розуміння та застосування визначень «реальний конфлікт інтересів», «потенційний конфлікт інтересів», «приватний інтерес» та удосконалення інших положень Закону"; 2) "Про внесення змін до статті 172-7 Кодексу України про адміністративні правопорушення щодо встановлення відповідальності за порушення обмеження щодо реалізації повноважень стосовно себе та пов’язаних осіб". Зазначені законопроекти були погоджені із заінтересованими органами, а згодом були направлені до Мін’юсту для проведення правової експертизи, за результатами якої НАЗК отримало висновки до зазначених законопроектів із загальною підсумковою оцінкою – відповідні. 29.11.2023 законопроекти були подані КМУ. КМУ 27.12.2023 повернув законопроекти на доопрацювання у тижневий строк разом з Мін’юстом. З огляду на те, що НАЗК не було запрошено та не брало участі в засіданні КМУ, на якому розглядались законопроекти, та, відповідно, не володіло інформацією про зміст пропозицій Міністра юстиції, то 05.01.2024 НАЗК направило відповідний запит до Мін’юсту. 18.01.2024 Мін’юстом повідомлено про необхідність врахування застережень, висловлених у висновках за результатами проведення правової експертизи. З огляду на зазначене, НАЗК 23.02.2024 направило до Мін’юсту лист з пропозиціями стосовно положень законопроекту, щодо яких Мін’юстом були висловлені застереження у своїх висновках (стосовно визначень понять «дискреційні службові /представницькі повноваження» та «приватний інтерес»). Поряд із пропозиціями НАЗК в додатку до листа зазначило обґрунтування своєї позиції та запропонувало доопрацьовані визначення вищезгаданих термінів. 04.03.2024 було отримано відповідь від Мін’юсту, якою повідомлено, що доопрацьована редакція законопроекту в частині визначення «приватний інтерес» не враховує їх застережень. Станом на 31.03.2026 НАЗК здійснює пошук шляхів узгодження відповідних редакцій з Мін’юстом. З огляду на обсяг вжитих дій (законопроект розроблено і забезпечено його подання Кабінетові Міністрів України) водночас у зв’язку недосягненням показника (індикатора) виконання (законопроект не подано до Верховної Ради України), відповідний захід не може вважатись таким, що виконаний повністю. | Partially implemented | 0.0
1.3 | Resolution of the conflicts of interest, observance of general restrictions and bans, rules of ethical conduct | 1.3.1 Flaws of legislation and the lack of effective risk-based mechanisms for detecting conflicts of interest limit the ability to minimize corruption by preventing and resolving conflicts of interest. | 1.3.1.2 | Improvements have been made to legislative procedures for reporting a conflict of interest and the mechanisms used to resolve it, particularly in relation to officials who do not have an immediate superior or occupy elective positions | 1.3.1.2.1 | Drafting and submitting to the Cabinet of Ministers of Ukraine a draft law that: 1) establishes requirements with respect to the form of the conflict of interest statement; 2) provides for the algorithm of actions of the immediate superior of the person who has a conflict of interest, where the superior has no powers to apply a specific method of external resolution of the conflict of interest (such as transfer or dismissal); 3) aligns the provisions of the Law of Ukraine On Prevention of Corruption, specifically with respect to the person who must be informed about the conflict of interest and the person who must resolve the conflict of interest; 4) improves the mechanism of resolution of the conflict of interest for individuals who do not have an immediate superior, particularly those filling elective positions; 5) extends the term for making a decision on the resolution of the conflict of interest. | 01.07.2023 | 31.03.2025 | National Agency on Corruption Prevention |  | state budget | within the established budget allocations for the relevant year | The draft law has been submitted to the Parliament of Ukraine. | Продовжується підготовка законопроекту на підставі концепції, яку розробило Національне агентство. З огляду на те, що настала дата завершення строку виконання відповідного заходу, а законопроект станом на момент звітування не розроблено та не забезпечено його подання Кабінетові Міністрів України, такий захід вважається не виконаним. | Not implemented | 0.0
1.3 | Resolution of the conflicts of interest, observance of general restrictions and bans, rules of ethical conduct | 1.3.1 Flaws of legislation and the lack of effective risk-based mechanisms for detecting conflicts of interest limit the ability to minimize corruption by preventing and resolving conflicts of interest. | 1.3.1.3 | Improvements have been made to the rules of independent and external resolution of a conflict of interest | 1.3.1.3.1 | Drafting and submitting to the Cabinet of Ministers of Ukraine a draft law that: 1) expands the list of possible methods of independent resolution of the conflict of interest; 2) aligns the procedures of external and independent resolution of the conflict of interest, particularly in terms of the term for making a conflict of interest statement, the term for its resolution, and the term for its independent resolution | 01.07.2023 | 31.03.2025 | National Agency on Corruption Prevention |  | state budget | within the established budget allocations for the relevant year | The draft law has been submitted to the Parliament of Ukraine. | Продовжується підготовка законопроекту на підставі концепції, яку розробило Національне агентство. З огляду на те, що настала дата завершення строку виконання відповідного заходу, а законопроект станом на момент звітування не розроблено та не забезпечено його подання Кабінетові Міністрів України, такий захід вважається не виконаним. | Not implemented | 0.0
1.3 | Resolution of the conflicts of interest, observance of general restrictions and bans, rules of ethical conduct | 1.3.1 Flaws of legislation and the lack of effective risk-based mechanisms for detecting conflicts of interest limit the ability to minimize corruption by preventing and resolving conflicts of interest. | 1.3.1.4 | A list of prohibitions on decision-making, actions or legal transactions has been established as a way to prevent conflicts of interest | 1.3.1.4.1 | Drafting and submitting to the Cabinet of Ministers of Ukraine a draft law that proposes prohibiting an official from making decisions, performing acts, or effecting legal transactions as a way to prevent a conflict of interest, particularly with respect to themselves and their next of kin, legal entities in which the official or their close relative is the founder, ultimate beneficial owner (controller) or manager of this legal entity | 01.04.2023 | 30.11.2023 | National Agency on Corruption Prevention |  | state budget | within the established budget allocations for the relevant year | The draft law has been submitted to the Parliament of Ukraine. | На виконання заходів, передбачених п. п. 1.3.1.1.1 та п. п. 1.3.1.4.1 додатка 2 до Державної антикорупційної програми на 2023 - 2025 роки, НАЗК розробило законопроекти: 1) "Про внесення змін до Закону України «Про запобігання корупції» щодо спрощення розуміння та застосування визначень «реальний конфлікт інтересів», «потенційний конфлікт інтересів», «приватний інтерес» та удосконалення інших положень Закону"; 2) "Про внесення змін до статті 172-7 Кодексу України про адміністративні правопорушення щодо встановлення відповідальності за порушення обмеження щодо реалізації повноважень стосовно себе та пов’язаних осіб". Зазначені законопроекти були погоджені із заінтересованими органами, а згодом були направлені до Мін’юсту для проведення правової експертизи, за результатами якої НАЗК отримало висновки до зазначених законопроектів із загальною підсумковою оцінкою – відповідні. 29.11.2023 законопроекти були подані КМУ. КМУ 27.12.2023 повернув законопроекти на доопрацювання у тижневий строк разом з Мін’юстом. З огляду на те, що НАЗК не було запрошено та не брало участі в засіданні КМУ, на якому розглядались законопроекти, та, відповідно, не володіло інформацією про зміст пропозицій Міністра юстиції, то 05.01.2024 НАЗК направило відповідний запит до Мін’юсту. 18.01.2024 Мін’юстом повідомлено про необхідність врахування застережень, висловлених у висновках за результатами проведення правової експертизи. З огляду на зазначене, НАЗК 23.02.2024 направило до Мін’юсту лист з пропозиціями стосовно положень законопроекту, щодо яких Мін’юстом були висловлені застереження у своїх висновках (стосовно визначень понять «дискреційні службові /представницькі повноваження» та «приватний інтерес»). Поряд із пропозиціями НАЗК в додатку до листа зазначило обґрунтування своєї позиції та запропонувало доопрацьовані визначення вищезгаданих термінів. 04.03.2024 було отримано відповідь від Мін’юсту, якою повідомлено, що доопрацьована редакція законопроекту в частині визначення «приватний інтерес» не враховує їх застережень. Станом на 31.03.2026 НАЗК здійснює пошук шляхів узгодження відповідних редакцій з Мін’юстом. З огляду на обсяг вжитих дій (законопроект розроблено і забезпечено його подання Кабінетові Міністрів України) водночас у зв’язку недосягненням показника (індикатора) виконання (законопроект не подано до Верховної Ради України), відповідний захід не може вважатись таким, що виконаний повністю. | Partially implemented | 0.0
1.3 | Resolution of the conflicts of interest, observance of general restrictions and bans, rules of ethical conduct | 1.3.1 Flaws of legislation and the lack of effective risk-based mechanisms for detecting conflicts of interest limit the ability to minimize corruption by preventing and resolving conflicts of interest. | 1.3.1.5 | The mechanisms for preventing conflicts of interest, in particular in connection with corporate rights, have been improved, in particular by instituting a ban on making decisions or taking actions in relation to legal entities in which a person has corporate rights | 1.3.1.5.1 | Drafting and submitting to the Cabinet of Ministers of Ukraine a draft law that: 1) establishes the obligation to hand over businesses and corporate rights for management, where they have been acquired by the official after their appointment (election) to the position; 2) prohibits the official from handing over their businesses or corporate rights for management to their next of kin; 3) prohibits decision making or transactions involving legal entities, where a civil servant or their next of kin are founders, beneficiaries, or managers of such legal entities. | 01.09.2023 | 31.03.2025 | National Agency on Corruption Prevention |  | state budget | within the established budget allocations for the relevant year | The draft law has been submitted to the Parliament of Ukraine. | Продовжується підготовка законопроекту на підставі концепції, яку розробило Національне агентство. З огляду на те, що настала дата завершення строку виконання відповідного заходу, а законопроект станом на момент звітування не розроблено та не забезпечено його подання Кабінетові Міністрів України, такий захід вважається не виконаним. | Not implemented | 0.0
1.3 | Resolution of the conflicts of interest, observance of general restrictions and bans, rules of ethical conduct | 1.3.1 Flaws of legislation and the lack of effective risk-based mechanisms for detecting conflicts of interest limit the ability to minimize corruption by preventing and resolving conflicts of interest. | 1.3.1.6 | Effective, complete, objective, and impartial risk-based monitoring and control over compliance with the requirements for preventing and resolving conflicts of interest and related restrictions set forth in Sections IV-V of the Law of Ukraine On Prevention of Corruption is ensured, in particular with the use of IT tools that effectively identify decisions and legal transactions made in conditions of a conflict of interest, ensure proper response to violations identified, as well as to decisions made in violation of the requirements of this Law | 1.3.1.6.1 | Drafting and submitting to the Cabinet of Ministers of Ukraine a draft law that: 1) defines the powers of the National Agency to carry out monitoring focusing, among other things, on compliance with other requirements and restrictions prescribed by Sections IV-V of the Law, which are aimed at preventing a conflict of interest; 2) corrects inaccuracies in the wording of the rights of the National Agency in Article 12 of the Law with respect to obtaining information and documents and responding to any detected violations of the requirements of the Law; 3) eliminates the discrepancy between the provisions of the Law and provisions of other laws, which makes it impossible to obtain certain classified information, particularly information that contains a secret of a pretrial investigation or concerns a customs case; 4) revokes the powers of the Council of Judges of Ukraine to monitor compliance with the law pertaining to the resolution of conflicts of interest in the work of judges, and instead grant the powers of the Council of Judges of Ukraine to resolve conflicts of interest of judges. | 01.07.2023 | 31.03.2025 | National Agency on Corruption Prevention |  | state budget | within the established budget allocations for the relevant year | The draft law has been submitted to the Parliament of Ukraine. | Продовжується підготовка законопроекту на підставі концепції, яку розробило Національне агентство. З огляду на те, що настала дата завершення строку виконання відповідного заходу, а законопроект станом на момент звітування не розроблено та не забезпечено його подання Кабінетові Міністрів України, такий захід вважається не виконаним. | Not implemented | 0.0
1.3 | Resolution of the conflicts of interest, observance of general restrictions and bans, rules of ethical conduct | 1.3.1 Flaws of legislation and the lack of effective risk-based mechanisms for detecting conflicts of interest limit the ability to minimize corruption by preventing and resolving conflicts of interest. | 1.3.1.6 | Effective, complete, objective, and impartial risk-based monitoring and control over compliance with the requirements for preventing and resolving conflicts of interest and related restrictions set forth in Sections IV-V of the Law of Ukraine On Prevention of Corruption is ensured, in particular with the use of IT tools that effectively identify decisions and legal transactions made in conditions of a conflict of interest, ensure proper response to violations identified, as well as to decisions made in violation of the requirements of this Law | 1.3.1.6.2 | Creating a system for ranking and analysis of information contained in the IT system Unified State Register of Declarations of Officials Authorized to Carry out Functions of State or Local Self-Government, which will identify risks of violations of the requirements of legislation on the prevention and resolution of conflicts of interest by declarants | 01.03.2023 | 30.11.2023 | National Agency on Corruption Prevention |  | state budget | within the established budget allocations for the relevant year | The system has been created, and the data obtained is used to identify risks. | According to the National Agency on Corruption Prevention, as of December 31, 2023, the system was created, the data obtained is used to identify risks, in particular, "the memo of the Department for Monitoring and Control over the Implementation of Legislation on Conflict of Interest and Prevention of Corruption dated October 02, 2023 No. 30-04/7489-23 to the Department of Information Systems, Analytical Work and Information Protection provides a description of the rules for establishing possible facts of violations of Articles 23, 25, 27 of the Law of Ukraine On Corruption Prevention to ensure their technical implementation. Analytical information on possible violations of Articles 23, 25, 27 of the Law of Ukraine On Corruption Prevention is generated using state registers by implementing 10 rules for selecting and processing the necessary information, which is then ranked. The ranking of the information received is based on the general rule: if any rule of selection and processing of information to establish a single possible violation of the requirements of the Law of Ukraine On Corruption Prevention is triggered, the relevant declaration receives a risk weighing coefficient of "1" for each such triggered rule. Subsequently, an employee of the National Agency on Corruption Prevention has the opportunity to sort the information received, set appropriate filters for further processing the information received and take response measures within the framework of the current legislation." | Implemented | 0.0
1.3 | Resolution of the conflicts of interest, observance of general restrictions and bans, rules of ethical conduct | 1.3.1 Flaws of legislation and the lack of effective risk-based mechanisms for detecting conflicts of interest limit the ability to minimize corruption by preventing and resolving conflicts of interest. | 1.3.1.6 | Effective, complete, objective, and impartial risk-based monitoring and control over compliance with the requirements for preventing and resolving conflicts of interest and related restrictions set forth in Sections IV-V of the Law of Ukraine On Prevention of Corruption is ensured, in particular with the use of IT tools that effectively identify decisions and legal transactions made in conditions of a conflict of interest, ensure proper response to violations identified, as well as to decisions made in violation of the requirements of this Law | 1.3.1.6.3 | Developing the “Hidden Interests” IT product | 01.03.2023 | 31.12.2025 | National Agency on Corruption Prevention |  | state budget and/or international technical assistance funds | within the established budget allocations for the relevant year and/or international technical assistance funds | The IT product has been improved by enhancing the existing algorithm used to track down ties and by adding new risk identification algorithms. | За повідомленням Національного агентства з питань запобігання корупції станом на 31.12.2024 проведено комунікацію з розробниками ІТ-продукту, обговорено зауваження та рекомендації щодо внесення подальших змін до ІТ-продукту. Станом на 31.03.2025, 30.06.2025, 30.09.2025, 31.12.2025 та 31.03.2026 інформація, що надавалася за IV квартал 2024 року, залишається актуальною. З огляду на зазначене констатуємо, що станом на 31.03.2026 захід не виконано. | Not implemented | 0.0
1.3 | Resolution of the conflicts of interest, observance of general restrictions and bans, rules of ethical conduct | 1.3.1 Flaws of legislation and the lack of effective risk-based mechanisms for detecting conflicts of interest limit the ability to minimize corruption by preventing and resolving conflicts of interest. | 1.3.1.7 | Systemic amendments have been made to the Laws of Ukraine On Service at Local Self-Government Bodies and On Local Self-Government in Ukraine in matters of prevention of conflicts of interest and the possibility of combining a position at local self-government bodies with the status of a people’s representative at a local council | 1.3.1.7.1 | Preparing an analytical report on the current status of the issue of application of the requirements of the Laws of Ukraine On Prevention of Corruption, On Service at Local Self-Government Bodies, On Local Self-Government in Ukraine, and On the Status of People’s Representatives at Local Councils in matters of prevention of conflicts of interest, the possibility of combining a position at local self-government bodies with the status of a people’s representative at a local council | 01.06.2023 | 31.08.2023 | National Agency on Corruption Prevention |  | state budget | within the established budget allocations for the relevant year | The analytical study has been conducted. |  | Implemented | 0.0
1.3 | Resolution of the conflicts of interest, observance of general restrictions and bans, rules of ethical conduct | 1.3.1 Flaws of legislation and the lack of effective risk-based mechanisms for detecting conflicts of interest limit the ability to minimize corruption by preventing and resolving conflicts of interest. | 1.3.1.7 | Systemic amendments have been made to the Laws of Ukraine On Service at Local Self-Government Bodies and On Local Self-Government in Ukraine in matters of prevention of conflicts of interest and the possibility of combining a position at local self-government bodies with the status of a people’s representative at a local council | 1.3.1.7.2 | Discussing the conclusions and recommendations outlined in the analytical report indicated in subclause 1.3.1.7.1 with the participation of representatives of government agencies, local self-government bodies, other state agencies, NGOs, international organizations, international technical assistance projects, and the academic community | 01.09.2023 | 31.10.2023 | National Agency on Corruption Prevention |  | state budget | within the established budget allocations for the relevant year | The conclusions and recommendations outlined in the analytical report have been discussed with the participation of representatives of government agencies, local self-government bodies, NGOs, international organizations, international technical assistance projects, and the academic community. | On October 27, 2023, the conclusions and recommendations contained in the analytical report were discussed during a working meeting of representatives of the National Agency on Corruption Prevention with the officials responsible for implementing the Declaration on Building Integrity in Local Self-Government (Minutes No. 1/2023). The present representatives of local self-government bodies were acquainted with the findings of the analytical report. Following the discussion, the analytical report was taken into consideration (without any proposals). | Implemented | 0.0
1.3 | Resolution of the conflicts of interest, observance of general restrictions and bans, rules of ethical conduct | 1.3.1 Flaws of legislation and the lack of effective risk-based mechanisms for detecting conflicts of interest limit the ability to minimize corruption by preventing and resolving conflicts of interest. | 1.3.1.7 | Systemic amendments have been made to the Laws of Ukraine On Service at Local Self-Government Bodies and On Local Self-Government in Ukraine in matters of prevention of conflicts of interest and the possibility of combining a position at local self-government bodies with the status of a people’s representative at a local council | 1.3.1.7.3 | Drafting and submitting to the Cabinet of Ministers of Ukraine a draft law that proposing to improve the legal regulation of the issues of prevention of conflicts of interest, the possibility of combining service positions at local self-government bodies with the status of a people’s representative at a local council, taking into account the findings of the analytical report indicated in subclause 1.3.1.7.1 | 01.11.2023 | 31.03.2025 | National Agency on Corruption Prevention |  | state budget | within the established budget allocations for the relevant year | The draft law has been submitted to the Parliament of Ukraine. | У аналітичному звіті, підготовленому на виконання пп. 1.3.2.7.1 додатка 2 до Державної антикорупційної програми на 2023 – 2025 роки (далі – ДАП), висловлено про існування ризику виникнення конфлікту інтересів при поєднанні особою двох статусів – посадової особи місцевого самоврядування та депутата місцевої ради. Прийнятий Верховною Радою України Закон України «Про службу в органах місцевого самоврядування» (далі Закон № 3077-IX від 02.05.2023) усуває вказаний ризик шляхом: - розмежування виборної посадової особи місцевого самоврядування (обрані на виборах чи призначені місцевою радою) та службовця місцевого самоврядування; - заборони службовцям місцевого самоврядування суміщати службову діяльність зі статусом депутата місцевої ради;<br> - заборони для заступників сільського, селищного, міського голови суміщати свою службову діяльність з іншою посадою, у тому числі на громадських засадах, займатися іншою оплачуваною або підприємницькою діяльністю передбачено (викладена у Прикінцевих та перехідних положеннях Закону № 3077-IX від 02.05.2023). Оскільки показником виконання заходу є внесення проекту закону до Верховної Ради України, а відповідна законодавча ініціатива уже прийнята, то заходу 1.3.2.7.3 ДАП присвоєно статус «виконано». | Implemented | 0.0
1.3 | Resolution of the conflicts of interest, observance of general restrictions and bans, rules of ethical conduct | 1.3.2 Legal regulation of prohibitions and restrictions on receiving gifts and being a party to certain legal relationships is flawed, and not all prohibitions are enforced by legal liability measures. | 1.3.2.1 | The legislative definition of the concept of other paid activity for the purposes of the Law has been introduced | 1.3.2.1.1 | Drafting and submitting to the Cabinet of Ministers of Ukraine a draft law proposing to define the term “other paid work” for the purposes of the Law | 01.05.2023 | 31.01.2024 | National Agency on Corruption Prevention |  | state budget | within the established budget allocations for the relevant year | The draft law has been submitted to the Parliament of Ukraine. | На виконання заходу Національне агентство розробило законопроекти: 1.Про внесення змін до Закону України «Про запобігання корупції» щодо удосконалення положень стосовно обмеження щодо зайняття окремими видами діяльності"; 2.Про внесення зміни до статті 172-4 Кодексу України про адміністративні правопорушення щодо узгодження її назви із термінологією Закону України «Про запобігання корупції». Національне агентство здійснило усі узгоджувальні процедури щодо вищевказаних законопроектів та листом від 25.06.2024 № 10-03/46563-24 подало їх Кабінету Міністрів України. Разом з тим, Кабінет Міністрів України листом від 05.11.2024 №26465/0/2-24 повернув зазначені законопроекти відповідно до пункту 2 розділу 6 протоколу № 109 засідання Кабінету Міністрів України від 29.10.2024. З огляду на обсяг вжитих дій (законопроект розроблено і забезпечено його подання Кабінетові Міністрів України) водночас у зв’язку недосягненням показника (індикатора) виконання (законопроект не подано до Верховної Ради України), відповідний захід не може вважатись таким, що виконаний повністю. | Partially implemented | 0.0
1.3 | Resolution of the conflicts of interest, observance of general restrictions and bans, rules of ethical conduct | 1.3.2 Legal regulation of prohibitions and restrictions on receiving gifts and being a party to certain legal relationships is flawed, and not all prohibitions are enforced by legal liability measures. | 1.3.2.2 | The list of cases exempted from the prohibition on receiving gifts has been updated, and the restrictions related to them have been improved (in particular, rules have been introduced for determine the period during which a person is prohibited from making decisions or acting in favor of the person who provided the gift) | 1.3.2.2.1 | Drafting and submitting to the Cabinet of Ministers of Ukraine a draft law proposing to: 1) improve the substance of the restriction pertaining to the acceptance of gifts, taking into account the need to maintain a fair balance between private interest and public interest; 2) expand the list of cases exempted from the prohibition on receiving gifts; 3) stipulate a limitation period during which a person is prohibited from making decisions or performing actions that benefit the gift giver. | 01.09.2023 | 28.02.2025 | National Agency on Corruption Prevention |  | state budget | within the established budget allocations for the relevant year | The draft law has been submitted to the Parliament of Ukraine. | Національне агентство розробило відповідний законопроект та 27.10.2023 провело його громадські обговорення. Національне агентство листом від 11.12.2023 № 10-03/30726-23 надіслало законопроект на погодження до Міністерства фінансів України, Міністерства економіки України, Міністерства цифрової трансформації України, Національної поліції України, Бюро економічної безпеки України, Державного бюро розслідувань, Національного антикорупційного бюро України, Офісу Генерального прокурора та листом від 11.12.2023 № 10-03/30729-23 Урядовому офісу координації європейської та євроатлантичної інтеграції Секретаріату Кабінету Міністрів для проведення експертизи на відповідність зобов’язанням України у сфері європейської інтеграції, у тому числі міжнародно-правовим, та праву Європейського Союзу (acquis ЄС). Заінтересовані органи державної влади погодили законопроект без зауважень, крім Національного антикорупційного бюро України та Національної поліції України, з якими в червні 2024 року було організовано та проведено узгоджувальні наради. Станом на 31.03.2026 триває доопрацювання законопроекту за результатами проведених узгоджувальних нарад. Водночас варто зауважити, що положення Закону України від 20.09.2023 № 3384-ІХ «Про внесення змін до деяких законів України про визначення порядку подання декларацій осіб, уповноважених на виконання функцій держави або місцевого самоврядування, в умовах воєнного стану» доповнили, зокрема, ст. 23 Закону України «Про запобігання корупції» нормами, якими розширено перелік випадків, на які не поширюється заборона щодо одержання подарунків, і якими визначено період дії обмеження, протягом якого особі забороняється приймати рішення чи вчиняти дії на користь особи, яка надала подарунок. З огляду на це можна вважати, що захід 1.3.2.2.1 є виконаним частково. | Partially implemented | 0.0
1.3 | Resolution of the conflicts of interest, observance of general restrictions and bans, rules of ethical conduct | 1.3.2 Legal regulation of prohibitions and restrictions on receiving gifts and being a party to certain legal relationships is flawed, and not all prohibitions are enforced by legal liability measures. | 1.3.2.3 | The rules for handling unjust enrichment or gift have been improved taking into account ways in which they can be received in intangible form | 1.3.2.3.1 | Drafting and submitting to the Cabinet of Ministers of Ukraine a draft law containing provisions that propose to improve: 1) the rules for handling a gift or unjust enrichment, particularly those received in intangible form; 2) the particulars of handling unjust enrichment or gift received in intangible form. | 01.08.2023 | 28.02.2025 | National Agency on Corruption Prevention | National Police of Ukraine, Prosecutor General’s Office of Ukraine , State Bureau of Investigation , National Anti-Corruption Bureau of Ukraine | state budget | within the established budget allocations for the relevant year | The draft law has been submitted to the Parliament of Ukraine. | Національне агентство розробило відповідний законопроект та 27.10.2023 провело його громадські обговорення. Національне агентство листом від 11.12.2023 № 10-03/30726-23 надіслало законопроект на погодження до Міністерства фінансів України, Міністерства економіки України, Міністерства цифрової трансформації України, Національної поліції України, Бюро економічної безпеки України, Державного бюро розслідувань, Національного антикорупційного бюро України, Офісу Генерального прокурора та листом від 11.12.2023 №10-03/30729-23 Урядовому офісу координації європейської та євроатлантичної інтеграції Секретаріату Кабінету Міністрів для проведення експертизи на відповідність зобов’язанням України у сфері європейської інтеграції, у тому числі міжнародно-правовим, та праву Європейського Союзу (acquis ЄС). Заінтересовані органи державної влади погодили законопроект без зауважень, крім Національного антикорупційного бюро України та Національної поліції України, з якими в червні 2024 року було організовано та проведено узгоджувальні наради. Станом на 31.03.2026 триває доопрацювання законопроекту за результатами проведених узгоджувальних нарад. З огляду на те, що настала дата завершення строку виконання відповідного заходу, а законопроект станом на момент звітування не фіналізовано та не забезпечено його подання Кабінетові Міністрів України, такий захід вважається не виконаним. | Not implemented | 0.0
1.3 | Resolution of the conflicts of interest, observance of general restrictions and bans, rules of ethical conduct | 1.3.2 Legal regulation of prohibitions and restrictions on receiving gifts and being a party to certain legal relationships is flawed, and not all prohibitions are enforced by legal liability measures. | 1.3.2.4 | The list of persons subject to limitations, particularly those pertaining to combination of positions or part-time jobs, serving on management boards, other executive or controlling bodies, the supervisory board of a for-profit organization has been expanded | 1.3.2.4.1 | Drafting and submitting to the Cabinet of Ministers of Ukraine a draft law proposing to expand the list of persons subject to limitations, particularly those pertaining to combination of positions or part-time jobs, serving on management boards, other executive or controlling bodies, the supervisory board of a for-profit organization | 01.02.2024 | 31.12.2024 | National Agency on Corruption Prevention |  | state budget | within the established budget allocations for the relevant year | The draft law has been submitted to the Parliament of Ukraine. | Продовжується підготовка законопроекту на підставі концепції, яку розробило Національне агентство. З огляду на те, що настала дата завершення строку виконання відповідного заходу, а законопроект станом на момент звітування не розроблено та не забезпечувалось його подання Кабінетові Міністрів України, такий захід вважається не виконаним. | Not implemented | 0.0
1.3 | Resolution of the conflicts of interest, observance of general restrictions and bans, rules of ethical conduct | 1.3.3 The activities of entities that influence (lobby) the parliamentary decision-making process are non-transparent and non-public. | 1.3.3.1 | Owing to regulatory and legal regulation, the activities of agents influence (lobbying) are carried out within the legal framework and have become understandable and transparent for the whole society | 1.3.3.1.1 | Conducting an analytical study of the legal mechanisms of lobbying employed in other countries in order to determine the model that could be applied in the legal system of Ukraine and would ensure a procedure of transparent influence on the process of administrative decision making exerted by the concerned commercial entities, NGOs, public associations, or separate individuals | 01.03.2023 | 31.08.2023 | National Agency on Corruption Prevention |  | state budget | within the established budget allocations for the relevant year | The analytical study has been conducted. | Based on the results of the analytical study, the concept of the Draft Law On Transparency of Lobbying was prepared | Implemented | 0.0
1.3 | Resolution of the conflicts of interest, observance of general restrictions and bans, rules of ethical conduct | 1.3.3 The activities of entities that influence (lobby) the parliamentary decision-making process are non-transparent and non-public. | 1.3.3.1 | Owing to regulatory and legal regulation, the activities of agents influence (lobbying) are carried out within the legal framework and have become understandable and transparent for the whole society | 1.3.3.1.2 | Drafting and submitting to the Cabinet of Ministers of Ukraine a draft law proposing to define: 1) the rules to be followed by officials of government agencies and local self-government bodies in interacting with stakeholders and agents of influence (lobbyists); 2) transparent mechanisms for influencing officials of government agencies and local self-government bodies; 3) mechanisms used to control lobbying activities and the agency authorized to exercise such control; 4) liability of the parties to lobbyist relationships for violation of rules governing their interaction and transparency of the lobbying process | 01.09.2023 | 30.04.2024 | National Agency on Corruption Prevention |  | state budget | within the established budget allocations for the relevant year | The draft law has been submitted to the Parliament of Ukraine. | The National Agency on Corruption Prevention has developed Draft Laws On Amendments to the Code of Ukraine on Administrative Offences on Violation of Legislation in the Area of Lobbying and On Fair Lobbying and Advocacy in Ukraine. Public discussions of the respective draft laws were held on November 10 and 23, 2023. The Draft Laws were sent to the Cabinet of Ministers of Ukraine by letter dated December 01, 2023 No. 27-02/29325-23. By letter dated December 08, 2023, No. 31651/0/2-23, the Secretariat of the Cabinet of Ministers of Ukraine returned the Draft Laws. The Draft Laws were resubmitted to the Cabinet of Ministers of Ukraine by letter dated December 11, 2023 No. 27-02/30801-23. On December 13, 2023, the Draft Law was received by the Verkhovna Rada of Ukraine. The Law of Ukraine On Lobbying (hereinafter referred to as the Law of February 23, 2024 No. 3606-IX) was adopted on February 23, 2024. On March 12, 2024, the President of Ukraine signed the Law of February 23, 2024 No. 3606-IX. | Implemented | 0.0
1.3 | Resolution of the conflicts of interest, observance of general restrictions and bans, rules of ethical conduct | 1.3.4 There are no legislative standards for ethical conduct of MPs, members of local councils, and elected local self-government officials. The existing rules of ethical conduct are not properly implemented due to the failure of managers to exercise their powers to hold violators of such rules liable. | 1.3.4.1 | The rules of ethical conduct of members of the Parliament of Ukraine, members of local councils, and elected local self-government officials have been established at the legislative level with the implementation of mechanisms of holding violators liable; members of the Parliament of Ukraine, members of local councils, and elected local self-government officials are familiar with the rules of ethical conduct | 1.3.4.1.1 | Supporting the consideration of the Draft Law of Ukraine On Amendments to Select Legislative Acts of Ukraine Pertaining to the Rules of Ethical Conduct of the Parliament Members of Ukraine (Ethical Code of Conduct) (registration number 8327 dated December 30, 2022) in the Parliament of Ukraine (particularly if the President of Ukraine vetoes the draft law) | 01.03.2023 | 31.12.2025 | National Agency on Corruption Prevention |  | state budget | within the established budget allocations for the relevant year | The law has been signed by the President of Ukraine. | Проект Закону України “Про внесення змін до деяких законодавчих актів України щодо правил етичної поведінки народних депутатів України (Етичного кодексу)” (реєстраційний номер 8327 від 30 грудня 2022 р.) знаходиться на розгляді Комітету Верховної Ради України з питань Регламенту, депутатської етики та організації роботи Верховної Ради України. 10.03.2026 надано доопрацьований законопроект на заміну. 07.04.2026 надано висновок Комітету про розгляд зазначеного проекту Закону України, згідно з яким його рекомендовано прийняти за основу. З огляду на відсутність дій, спрямованих на супроводження відповідного законопроекту, захід вважається невиконаним. | Not implemented | 0.0
1.3 | Resolution of the conflicts of interest, observance of general restrictions and bans, rules of ethical conduct | 1.3.4 There are no legislative standards for ethical conduct of MPs, members of local councils, and elected local self-government officials. The existing rules of ethical conduct are not properly implemented due to the failure of managers to exercise their powers to hold violators of such rules liable. | 1.3.4.1 | The rules of ethical conduct of members of the Parliament of Ukraine, members of local councils, and elected local self-government officials have been established at the legislative level with the implementation of mechanisms of holding violators liable; members of the Parliament of Ukraine, members of local councils, and elected local self-government officials are familiar with the rules of ethical conduct | 1.3.4.1.2 | Conducting an analytical study and preparing an analytical report on the current status of issues concerning the observance of the ethical code of conduct by members of local councils and elected officials of local self-government bodies, as well as the possible mechanisms for holding such officials liable for violations of this code | 01.04.2023 | 31.12.2023 | National Agency on Corruption Prevention | National Agency of Ukraine on Civil Service, Ministry for Communities and Territories Development of Ukraine | state budget | within the established budget allocations for the relevant year | The analytical study has been conducted and the report has been prepared. | According to the National Agency on Corruption Prevention, "on October 20, 2023, the results of a survey that is part of an analytical study on the corruption prevention and compliance with the rules of ethical behavior in local governments were presented. The survey involved 679 representatives of urban, rural and settlement territorial communities, which covers almost half of the territorial communities of Ukraine. By the end of the reporting period, the analytical study was completed." The text of the Analytical Study on Compliance with Ethical Standards by People's Representatives, Elected Officials, and Officials of Local Self-Government Bodies will be added in the first quarter of 2024. | Implemented | 0.0
1.3 | Resolution of the conflicts of interest, observance of general restrictions and bans, rules of ethical conduct | 1.3.4 There are no legislative standards for ethical conduct of MPs, members of local councils, and elected local self-government officials. The existing rules of ethical conduct are not properly implemented due to the failure of managers to exercise their powers to hold violators of such rules liable. | 1.3.4.1 | The rules of ethical conduct of members of the Parliament of Ukraine, members of local councils, and elected local self-government officials have been established at the legislative level with the implementation of mechanisms of holding violators liable; members of the Parliament of Ukraine, members of local councils, and elected local self-government officials are familiar with the rules of ethical conduct | 1.3.4.1.3 | Drafting and submitting to the Cabinet of Ministers of Ukraine the draft law that incorporates the findings of the analytical report indicated in subclause 1.3.4.1.2, which will make it possible to: 1) improve the existing ethical code of conduct of members of local councils; 2) establish the procedure and time frame for holding liable the members of local councils and elected officials of local self-government bodies for violating the standards (rules) of ethical conduct; 3) designate the agency to monitor observance of standards (rules) of ethical conduct by members of local councils and elected officials of local self-government bodies; 4) implement a procedure by which citizens could report unethical conduct by members of local councils and elected officials of local self-government bodies. | 01.04.2025 | 31.12.2025 | National Agency on Corruption Prevention | National Agency of Ukraine on Civil Service, Ministry for Communities and Territories Development of Ukraine | state budget | within the established budget allocations for the relevant year | The draft law has been submitted to the Parliament of Ukraine. | Національне агентство здійснює розробку зазначеного у заході законопроекту. З огляду на те, що настала дата завершення строку виконання відповідного заходу, а законопроект станом на момент звітування не розроблено та не забезпечувалось його подання Кабінетові Міністрів України, такий захід вважається не виконаним. | Not implemented | 0.0
1.3 | Resolution of the conflicts of interest, observance of general restrictions and bans, rules of ethical conduct | 1.3.4 There are no legislative standards for ethical conduct of MPs, members of local councils, and elected local self-government officials. The existing rules of ethical conduct are not properly implemented due to the failure of managers to exercise their powers to hold violators of such rules liable. | 1.3.4.2 | Measures for holding managers liable for failing to respond as mandated by law to instances of gross violations of anticorruption legislation have been implemented | 1.3.4.2.1 | Drafting and submitting to the Cabinet of Ministers of Ukraine a draft law proposing to establish a mechanism for holding liable all categories of managers for failing to respond to confirmed facts of gross violations of anticorruption legislation by their subordinates | 01.03.2024 | 31.12.2024 | National Agency on Corruption Prevention |  | state budget | within the established budget allocations for the relevant year | The draft law has been submitted to the Parliament of Ukraine. | На виконання заходу Національне агентство розробило відповідний проект Закону України. 17.12.2024 Національне агентство провело громадське обговорення зазначеного законопроекту та здійснило його доопрацювання. Протягом І кварталу 2025 року законопроект був направлений на погодження до заінтересованих органів, за результатами якого положення законопроекту було доопрацьовано. Листом від 12.03.2025 № 10-03/21423-25 Національне агентство надіслало зазначений законопроект на правову експертизу до Мін'юсту. Отримавши висновки Мін'юсту та провівши необхідні узгоджувальні процедури, Національне агентство 18.04.2025 листом № 10-03/34013-25 подало законопроект на розгляд Кабінету Міністрів України. На засіданні профільного Урядового комітету від 09.06.2025 проект був повернутий для узгодження позицій Національного агентства та Міндовкілля. На виконання рішення Урядового комітету Національне агентство провело узгоджувальну нараду з керівництвом Міндовкілля 27.06.2025, за результатами якої розбіжності з Міністерством були врегульовані. Національне агентство листом від 11.07.2025 № 43244/4/1-24 направило на розгляд Кабінету Міністрів України проект Закону України «Про внесення змін до Кодексу України про адміністративні правопорушення щодо встановлення адміністративної відповідальності за порушення окремих вимог, заборон та обмежень, встановлених Законом України “Про запобігання корупції”, та деяких інших питань удосконалення законодавства про адміністративні правопорушення, пов’язані з корупцією». Зазначений проект Закону України згідно з абз. 3 п. 2 § 40 Регламенту Кабінету Міністрів України, затвердженого постановою Кабінету Міністрів України від 18.07.2007 № 950, у зв’язку з відставкою Уряду повернуто Національному агентству (лист Секретаріату Кабінету Міністрів України від 17.07.2025 № 17781/0/2-25). Станом на 31.03.2026 Національне агентство готує вказаний проект Закону України для здійснення повторного погодження та проведення низки інших регламентних процедур з метою подання його на розгляд Кабінету Міністрів України. З огляду на обсяг вжитих дій (законопроект розроблено і забезпечено його подання Кабінетові Міністрів України) водночас у зв’язку недосягненням показника (індикатора) виконання (законопроект не подано до Верховної Ради України), відповідний захід не може вважатись таким, що виконаний повністю. | Partially implemented | 0.0