## Заходи
№ Напрямку | Напрямок | Проблема | № ОСР | Назва ОСР | № Заходу | Назва заходу | Дата початку | Дата завершення | Головний виконавець | Співвиконавці | Джерела фінансування | Обсяги фінансування, тис.грн. | Показник (індикатор) виконання | Стан виконання | Статус виконання | Оцінка досягнення ОСР
2.1 | Fair courts, prosecutorial and law enforcement authorities | 2.1.3 Lack of effective mechanisms for maintaining the integrity of the judiciary and responding to established facts of influence, pressure on judges and interference in their activities | 2.1.3.3 | The disciplinary practice with respect to judges is consistent, predictable, stable, and open; all decisions of the disciplinary authority are made public on time; disciplinary proceedings against judges are generally open and broadcast in real time | 2.1.3.3.1 | Drafting and submitting to the Cabinet of Ministers of Ukraine a draft law that: 1) stipulates that sessions of Disciplinary Chambers of the High Council of Justice shall be public with real-time video broadcasts; 2) stipulates that the sessions of the High Council of Justice convened to examine complaints against decisions of Disciplinary Chambers following the review of disciplinary proceedings against a judge shall be public with real-time video broadcasts; 3) defines the exhaustive list of grounds for an examination behind closed doors during a session of Disciplinary Chambers of the High Council of Justice without real-time video broadcasts; 4) establishes the exhaustive list of grounds for holding an examination behind closed doors during the session of the High Council of Justice convened to examine complaints against decisions of Disciplinary Chambers following the review of disciplinary proceedings against a judge without real-time video broadcasts; 5) stipulates that an examination behind closed doors during a session of Disciplinary Chambers of the High Council of Justice without real-time video broadcasts is possible only based on a well-reasoned decision of the Disciplinary Chambers of the High Council of Justice with the substantiation of the existence of the relevant grounds prescribed by law; 6) stipulates that an examination behind closed doors during a session of the High Council of Justice convened to examine complaints against decisions of Disciplinary Chambers of the High Council of Justice without real-time video broadcasts is possible only based on a well-reasoned decision of the High Council of Justice with the substantiation of the existence of the relevant grounds prescribed by law; 7) defines a clear time frame for each stage of the disciplinary proceeding, which would rule out the possibility of unreasonable delays in the review of disciplinary complaints; 8) provides for open and roll-call voting by members of the Disciplinary Chambers of the High Council of Justice and by the High Council of Justice on decisions in disciplinary cases. | 01.06.2023 | 30.11.2023 | Ministry of Justice of Ukraine |  | state budget | within the established budget allocations for the relevant year | The draft law has been submitted to the Parliament of Ukraine. | Implemented in a different way. On October 19, 2023, the Law of Ukraine dated September 06, 2023 No. 3378-IX On Amendments to the Law of Ukraine On the Judiciary and the Status of Judges and Certain Laws of Ukraine on Amending the Status and Procedure for Forming the Service of Disciplinary Inspectors of the High Council of Justice (hereinafter - the Law No. 3378-IX) came into force. The Law No. 3378-IX amends, in particular, Articles 49-51 of the Law of Ukraine On the High Council of Justice, which regulate the procedure for considering disciplinary proceedings against judges and appeals against decisions to bring them to disciplinary liability. The draft law was submitted to the Verkhovna Rada of Ukraine by Parliament Members. The Law No. 3378-IX sets out in a new version part one of Article 49 of the Law of Ukraine On the High Council of Justice and provides that proceedings of a meeting shall be broadcast in real time on the official website of the High Council of Justice, except as provided for in part two of this article. According to part two of Article 49 of the Law of Ukraine On the High Council of Justice, consideration of a disciplinary case in a closed session of the Disciplinary Chamber takes place 1) if consideration in an open session may lead to disclosure of secrets protected by law, and 2) to prevent the disclosure of information about intimate or other personal aspects of the lives of persons participating in the disciplinary proceedings. Based on a reasoned request of the disciplinary inspector of the High Council of Justice, who is a speaker, judge, complainant, their representatives, or on its own initiative, the Disciplinary Chamber may not broadcast such a meeting by adopting a respective decision. These provisions also apply when considering an appeal against a decision of the Disciplinary Chamber to bring a judge to disciplinary liability. The Law No. 3378-IX sets out in a new version part four of Article 50 of the Law of Ukraine On the High Council of Justice and provides that the decision in a disciplinary case is made by open roll-call vote by a simple majority of votes, as well as part eleven of Article 51 and establishes that the decision on the results of consideration of an appeal against the decision of the Disciplinary Chamber in a disciplinary case is made by the High Council of Justice by open roll-call vote. In addition, the Law No. 3378-IX established time limits for each stage of disciplinary proceedings. Thus, the provisions of the Law of Ukraine No. 3378-IX On Amendments to the Law of Ukraine On the Judiciary and the Status of Judges and Certain Laws of Ukraine on Amending the Status and Procedure for Forming the Service of Disciplinary Inspectors of the High Council of Justice ensure the implementation of measure 2.1.3.3.1. | Implemented | 0.0
2.1 | Fair courts, prosecutorial and law enforcement authorities | 2.1.3 Lack of effective mechanisms for maintaining the integrity of the judiciary and responding to established facts of influence, pressure on judges and interference in their activities | 2.1.3.3 | The disciplinary practice with respect to judges is consistent, predictable, stable, and open; all decisions of the disciplinary authority are made public on time; disciplinary proceedings against judges are generally open and broadcast in real time | 2.1.3.3.2 | Preparing and annually publishing summaries of the disciplinary practice of Disciplinary Chambers of the High Council of Justice for the previous calendar year | 01.04.2024 | 31.12.2025 | High Council of Justice |  | state budget | within the established budget allocations for the relevant year | The summary of the disciplinary practice has been publicized. | Рішенням Вищої ради правосуддя від 22 лютого 2024 року № 545/0/15-24 утворено робочу групу Вищої ради правосуддя з питань узагальнення дисциплінарної практики щодо суддів, до складу якої увійшли члени Вищої ради правосуддя та працівники секретаріату Вищої ради правосуддя. Робочою групою з питань узагальнення дисциплінарної практики щодо суддів у 2024 році підготовлені: - узагальнення дисциплінарної практики Дисциплінарних палат Вищої ради правосуддя (щодо постановлення ухвал про відмову у відкритті дисциплінарних справ стосовно суддів за 2023 рік); - узагальнення дисциплінарної практики Дисциплінарних палат Вищої ради правосуддя (щодо розгляду дисциплінарних справ стосовно суддів за 2023 рік); - узагальнення дисциплінарної практики Вищої ради правосуддя із перегляду рішень Дисциплінарних палат Вищої ради правосуддя за 2023 рік. Відповідно до рішення Вищої ради правосуддя від 27 червня 2024 року № 1998/0/15-24 вказані узагальнення оприлюднені на офіційному веб-сайті Ради. Крім того, на веб-сайті Вищої ради правосуддя було оприлюднено узагальнення практики розгляду Вищою радою правосуддя та її дисциплінарними органами дисциплінарних справ щодо суддів (за матеріалами справ 2017–2021 років). У 4 кварталі 2025 року головним виконавцем повідомлено, що відповідно до рішення Вищої ради правосуддя від 23.12.2025 № 2795/0/15-25 оприлюднено на офіційному вебсайті Вищої ради правосуддя: - узагальнення дисциплінарної практики Вищої ради правосуддя (щодо постановлення ухвал про залишення без розгляду дисциплінарних скарг та про відмову у відкритті дисциплінарних справ стосовно суддів за 2024 рік); - узагальнення практики розгляду Дисциплінарними палатами Вищої ради правосуддя дисциплінарних справ стосовно суддів за 2024 рік; - узагальнення дисциплінарної практики Вищої ради правосуддя з перегляду рішень Дисциплінарних палат Вищої ради правосуддя за 2024 рік. Таким чином, Вищою радою правосуддя було підготовлено та оприлюднено узагальнення дисциплінарної практики за 2023 і 2024 роки. З огляду на зазначене, у межах щоквартального моніторингу за 4 квартал 2025 року, констатуємо, що захід виконано. | Implemented | 0.0
2.1 | Fair courts, prosecutorial and law enforcement authorities | 2.1.3 Lack of effective mechanisms for maintaining the integrity of the judiciary and responding to established facts of influence, pressure on judges and interference in their activities | 2.1.3.3 | The disciplinary practice with respect to judges is consistent, predictable, stable, and open; all decisions of the disciplinary authority are made public on time; disciplinary proceedings against judges are generally open and broadcast in real time | 2.1.3.3.3 | Preparing and annually publishing summaries of the disciplinary practice of the High Council of Justice in revising the decisions of Disciplinary Chambers of the High Council of Justice for the previous calendar year | 01.04.2024 | 31.12.2025 | High Council of Justice |  | state budget | within the established budget allocations for the relevant year | The summary of the disciplinary practice has been publicized. | Рішенням Вищої ради правосуддя від 22 лютого 2024 року № 545/0/15-24 утворено робочу групу Вищої ради правосуддя з питань узагальнення дисциплінарної практики щодо суддів, до складу якої увійшли члени Вищої ради правосуддя та працівники секретаріату Вищої ради правосуддя. Робочою групою з питань узагальнення дисциплінарної практики щодо суддів у 2024 році підготовлені: - узагальнення дисциплінарної практики Дисциплінарних палат Вищої ради правосуддя (щодо постановлення ухвал про відмову у відкритті дисциплінарних справ стосовно суддів за 2023 рік); - узагальнення дисциплінарної практики Дисциплінарних палат Вищої ради правосуддя (щодо розгляду дисциплінарних справ стосовно суддів за 2023 рік); - узагальнення дисциплінарної практики Вищої ради правосуддя із перегляду рішень Дисциплінарних палат Вищої ради правосуддя за 2023 рік. Відповідно до рішення Вищої ради правосуддя від 27 червня 2024 року № 1998/0/15-24 вказані узагальнення оприлюднені на офіційному веб-сайті Ради. Крім того, на веб-сайті Вищої ради правосуддя було оприлюднено узагальнення практики розгляду Вищою радою правосуддя та її дисциплінарними органами дисциплінарних справ щодо суддів (за матеріалами справ 2017–2021 років). У 4 кварталі 2025 року головним виконавцем повідомлено, що відповідно до рішення Вищої ради правосуддя від 23.12.2025 № 2795/0/15-25 оприлюднено на офіційному вебсайті Вищої ради правосуддя: - узагальнення дисциплінарної практики Вищої ради правосуддя (щодо постановлення ухвал про залишення без розгляду дисциплінарних скарг та про відмову у відкритті дисциплінарних справ стосовно суддів за 2024 рік); - узагальнення практики розгляду Дисциплінарними палатами Вищої ради правосуддя дисциплінарних справ стосовно суддів за 2024 рік; - узагальнення дисциплінарної практики Вищої ради правосуддя з перегляду рішень Дисциплінарних палат Вищої ради правосуддя за 2024 рік. Таким чином, Вищою радою правосуддя було підготовлено та оприлюднено узагальнення дисциплінарної практики за 2023 і 2024 роки. З огляду на зазначене, у межах щоквартального моніторингу за 4 квартал 2025 року, констатуємо, що захід виконано. | Implemented | 0.0
2.1 | Fair courts, prosecutorial and law enforcement authorities | 2.1.3 Lack of effective mechanisms for maintaining the integrity of the judiciary and responding to established facts of influence, pressure on judges and interference in their activities | 2.1.3.3 | The disciplinary practice with respect to judges is consistent, predictable, stable, and open; all decisions of the disciplinary authority are made public on time; disciplinary proceedings against judges are generally open and broadcast in real time | 2.1.3.3.4 | Holding annual discussions of the summaries of disciplinary practice prepared by Disciplinary Chambers of the High Council of Justice and by the High Council of Justice, with the participation of representatives of government agencies, NGOs, international organizations, participants of international technical assistance projects, and the academic community | 01.06.2024 | 31.12.2025 | High Council of Justice |  | state budget | within the established budget allocations for the relevant year | The summaries of disciplinary practice have been discussed with the participation of representatives of government agencies, NGOs, international organizations, participants of international technical assistance projects, and the academic community. | За інформацією, наданою Вищою радою правосуддя, 4 жовтня 2024 року проведено обговорення узагальнень практики у дисциплінарних провадженнях щодо суддів за 2023 рік за участю членів Вищої ради правосуддя, секретаря Великої Палати Верховного Суду, Уповноваженого у справах Європейського суду з прав людини, представників Ради суддів України, Вищої кваліфікаційної комісії суддів України, Національної школи суддів України, Проекту ЄС «ПРАВО – JUSTICE», Програми USAID «Справедливість для всіх», Проекту РЄ «Підтримка судової влади України в умовах війни та післявоєнного періоду», громадської організації «Лабораторія законодавчих ініціатив», Громадської ради доброчесності, всеукраїнського об’єднання «Автомайдан». За інформацією, наданою головним виконавцем, 25 грудня 2025 року Вищою радою правосуддя проведено обговорення узагальнень практики у дисциплінарних провадженнях щодо суддів за 2024 рік. В обговоренні взяли участь члени Вищої ради правосуддя, дисциплінарні інспектори ВРП, судді Верховного Суду, члени Вищої кваліфікаційної комісії суддів України, Ради суддів України, представники Міністерства юстиції України, Національної школи суддів України, представники секретаріату ВРП, наукової спільноти, громадських організацій. З огляду на зазначене, констатуємо, що захід виконано повністю. | Implemented | 0.0