## Заходи
№ Напрямку | Напрямок | Проблема | № ОСР | Назва ОСР | № Заходу | Назва заходу | Дата початку | Дата завершення | Головний виконавець | Співвиконавці | Джерела фінансування | Обсяги фінансування, тис.грн. | Показник (індикатор) виконання | Стан виконання | Статус виконання | Оцінка досягнення ОСР
2.1 | Fair courts, prosecutorial and law enforcement authorities | 2.1.3 Lack of effective mechanisms for maintaining the integrity of the judiciary and responding to established facts of influence, pressure on judges and interference in their activities | 2.1.3.5 | An effective mechanism has been introduced for verifying the legality of the origin of a judge’s property; judges who have violated the obligation to prove the legality of the source of their property have been dismissed pursuant to Article 126 of the Constitution of Ukraine | 2.1.3.5.1 | Drafting and submitting to the Cabinet of Ministers of Ukraine a draft law that: 1) institutes a separate procedure for checking the legitimacy of the sources of origin of the judge’s assets (outside the scope of the disciplinary proceedings), which will be carried out by the National Agency; 2) institutes a separate procedure by which the High Council of Justice would review petitions for the dismissal of the judge on account of the violation of the obligation to prove the legitimacy of the origin of assets; 3) institutes a separate procedure by which the judge or plaintiff (complainant) can appeal decisions, actions, or omissions to act as part of the process of verifying the legitimacy of the origin of the judge’s assets, and dismiss the judge on account of the violation of the obligation to prove the legitimacy of the origin of assets. | 01.01.2025 | 31.12.2025 | National Agency on Corruption Prevention |  | state budget | within the established budget allocations for the relevant year | The draft law has been submitted to the Parliament of Ukraine. | Здійснюється підготовка зазначеного законопроекту. З огляду на те, що настала дата завершення строку виконання відповідного заходу, а законопроект станом на момент звітування не розроблено та не забезпечувалось його подання Кабінетові Міністрів України, такий захід вважається не виконаним. | Not implemented | 0.0