## Заходи
№ Напрямку | Напрямок | Проблема | № ОСР | Назва ОСР | № Заходу | Назва заходу | Дата початку | Дата завершення | Головний виконавець | Співвиконавці | Джерела фінансування | Обсяги фінансування, тис.грн. | Показник (індикатор) виконання | Стан виконання | Статус виконання | Оцінка досягнення ОСР
2.1 | Fair courts, prosecutorial and law enforcement authorities | 2.1.6 Lack of an effective model of appointment to positions, remuneration, career promotion, and review of disciplinary complaints within the system of the National Police | 2.1.6.2 | The practice of application of provisions of the Disciplinary Regulations of the National Police has been studied, and amendments to the Regulations have been proposed | 2.1.6.2.1 | Arranging an analytical study to analyze the effectiveness of application of the provisions of the Disciplinary Regulations of the National Police of Ukraine between 2018 and 2022, specifying (with data grouped separately for junior, middle, and senior positions with the police): 1) the total number of internal investigations conducted; 2) the number of recorded statements, complaints, and reports from citizens, officials, and other police officers, the media about offenses committed by police officers showing signs of disciplinary misconduct; 3) the number of internal investigations based on reports about violations of constitutional human and civil rights and freedoms by police officers; 4) the number of disciplinary committees that included representatives of the public; 5) the number of disciplinary sanctions imposed (broken down by kinds of sanctions); 6) a description and assessment of the most widespread problems relating to the effectiveness and transparency of the procedure by which police officers are brought to disciplinary liability; 7) the prospects of creation of a disciplinary authority having status as an interregional territorial body of the National Police; 8) recommendations on ways to improve the effectiveness and quality of the procedure of internal investigations and the independence of the work of the disciplinary committee. | 01.05.2023 | 30.09.2023 | Ministry of Internal Affairs of Ukraine | National Police of Ukraine | state budget and/or international technical assistance funds | within the established budget allocations for the relevant year | The analytical study has been conducted and a report on its findings has been published. | The National Police of Ukraine conducted the analytical study to analyze the effectiveness of application of the provisions of the Disciplinary Regulations of the National Police of Ukraine between 2018 and February 2022, and prepared the report based on its findings. | Implemented | 0.0
2.1 | Fair courts, prosecutorial and law enforcement authorities | 2.1.6 Lack of an effective model of appointment to positions, remuneration, career promotion, and review of disciplinary complaints within the system of the National Police | 2.1.6.2 | The practice of application of provisions of the Disciplinary Regulations of the National Police has been studied, and amendments to the Regulations have been proposed | 2.1.6.2.2 | Holding a presentation of the report on the findings of the analytical study indicated in subclause 2.1.6.2.1, followed by its expert discussion | 01.10.2023 | 30.11.2023 | Ministry of Internal Affairs of Ukraine | National Police of Ukraine | state budget and/or international technical assistance funds | within the established budget allocations for the relevant year | The expert discussion has been conducted and its results have been published. | On November 30, 2023, an expert discussion of the report on the findings of the analytical study analyzing the effectiveness of the application of the Disciplinary Regulations of the National Police of Ukraine from 2018 to February 2022 took place, and a report was prepared and published on the website of the Ministry of Internal Affairs of Ukraine. | Implemented | 0.0
2.1 | Fair courts, prosecutorial and law enforcement authorities | 2.1.6 Lack of an effective model of appointment to positions, remuneration, career promotion, and review of disciplinary complaints within the system of the National Police | 2.1.6.2 | The practice of application of provisions of the Disciplinary Regulations of the National Police has been studied, and amendments to the Regulations have been proposed | 2.1.6.2.3 | Drafting and submitting to the Cabinet of Ministers of Ukraine a draft law providing for: 1) development and operation of 2 types of disciplinary committees: conducting official investigation based on information regarding the policemen’s violation of the service discipline; consideration of issues regarding the policemen’s violation of huma/citizen rights; 2) inclusion of no less than 50% of influential and famous representatives of the public and/or human rights organizations to the disciplinary committees investigating issues regarding the policemen’s violation of human/citizen rights; 3) mandating that the number and composition of disciplinary committees of the central administrative agency of the police shall be approved by the Minister of Internal Affairs, and the number and composition of disciplinary committees of territorial (in particular, including interregional) agencies of the police shall be approved by the Chief of the National Police; 4) the right of the disciplinary committee to submit—while exercising its powers—queries to agencies (units) of the police, other government agencies, local self-government bodies, and legal entities and request materials required for the internal investigation; the timeframes, grounds, and forms of disclosure of information by agencies (units) of the police, other government agencies, local self-government bodies, and legal entities to the disciplinary committees, as well as grounds for withholding such information; 5) that the disciplinary committee’s decision based on results of official investigation shall be approved by the authority who ordered to conduct the official investigation; 6) that the policeman’s manager authorized to impose disciplinary action, speculating whether or not to impose the disciplinary action, shall be governed by the disciplinary committee’s decision on the policemen’s violation of human/citizen rights, and in case of disagreement with its decision the committee shall add the written separate opinion with justification of such legal position, it also reserves the right to impose the disciplinary action, contrary to the one suggested by the disciplinary committee on the policemen’s violation of human/citizen rights, but no greater than 1 stage; 7) Policemen signs and list of disciplinary offenses violating human/citizen rights and freedoms; the disciplinary committee on the policemen’s violation of human/citizen rights, may recommend to apply the disciplinary action, such as dismissal from the position with remaining in service or discharge from the service; 8) making changes taking into account the recommendations on ways to improve the effectiveness and quality of work of disciplinary committee and the selection procedure issued based on the findings of the study indicated in subclause 2.1.6.2.1. | 01.12.2023 | 31.12.2024 | Ministry of Internal Affairs of Ukraine | National Police of Ukraine | state budget | within the established budget allocations for the relevant year | The draft law has been submitted to the Parliament of Ukraine. | Відповідно до постанови Кабінету Міністрів України від 18.10.2024 № 1194 "Про внесення змін до Державної антикорупційної програми на 2023–2025 роки" внесено зміни до змісту заходу. З огляду на це Національна поліція України (далі - НПУ) розробила оновлений проект Закону України «Про внесення змін до Дисциплінарного статуту Національної поліції України щодо вдосконалення порядку проведення службових розслідувань та забезпечення незалежності дисциплінарних комісій» . Зазначений законопроект погоджено з усіма заінтересованими органами, у тому числі правоохоронними органами, на працівників яких поширюється дія Дисциплінарного статуту НПУ, а також проведено відповідні експертизи відповідно до положень Регламенту Кабінету Міністрів України, затвердженого постановою Кабінету Міністрів України від 18.07.2007 № 950. 24.06.2025 доопрацьований з урахуванням зауважень Секретаріату Кабінету Міністрів відповідний законопроект внесено на розгляд Уряду. 08.07.2025 проект Закону України «Про внесення змін до Дисциплінарного статуту Національної поліції України щодо вдосконалення порядку проведення службових розслідувань та забезпечення незалежності дисциплінарних комісій» зареєстровано у Верховній Раді України за № 13458. Водночас 17.07.2025 законопроект від 08.07.2025 № 13458 знято з розгляду (відкликано відповідно до ч. 3 ст. 105 Закону України "Про Регламент Верховної Ради України" у зв'язку з припиненням повноважень Кабінету Міністрів України). 29.07.2025 МВС повторно подало на розгляд Уряду вище згаданий законопроект, який схвалено Кабінетом Міністрів України 26.08.2025 та 29.08.2025 зареєстровано у Верховній Раді України за № 13713. Водночас законопроект від 29.08.2025 № 13713 частково відповідає положенням п.п. 2, 3 та 6 п. 2.1.6.2.3 додатка 2 до Державної антикорупційної програми на 2023 - 2025 роки (далі - Програма), у зв'язку з чим, захід не може вважатися таким, що виконаний повністю. Так, відповідно до п.п. 2 п. 2.1.6.2.3 додатка 2 до Програми законопроектом має бути передбачено «включення до складу дисциплінарних комісій з розгляду питань щодо порушення поліцейськими прав людини або громадянина не менше половини членів, які є авторитетними і відомими представниками громадськості, правозахисних організацій». Разом з тим, законопроект від 29.08.2025 № 13713 не містить відповідних положень. До того ж, згідно з положеннями п.п. 3 п. 2.1.6.2.3 додатка 2 до Програми, йдеться про повноваження Міністра внутрішніх справ чи Голови Національної поліції України затверджувати кількість та склад дисциплінарних комісій, водночас законопроектом пропонується наділити зазначених суб'єктів повноваженням затвердження лише складу. Відповідно до абз. 2 ч. 8 ст. 19 Дисциплінарного статуту Національної поліції України (у редакції законопроекту): "У разі розгляду висновку службового розслідування та незгоди уповноваженого керівника із запропонованим у ньому дисциплінарним стягненням" використано формулювання "у разі", що створює ризики тлумачення в такий спосіб, що встановлює нічим не регламентовану дискрецію щодо розгляду чи не розгляду висновку службового рослідування. Такий підхід не повною мірою узгоджується з положеннями п.п. 6 п. 2.1.6.2.3 додатка 2 до Програми. | Partially implemented | 0.0