## Заходи
№ Напрямку | Напрямок | Проблема | № ОСР | Назва ОСР | № Заходу | Назва заходу | Дата початку | Дата завершення | Головний виконавець | Співвиконавці | Джерела фінансування | Обсяги фінансування, тис.грн. | Показник (індикатор) виконання | Стан виконання | Статус виконання | Оцінка досягнення ОСР
2.1 | Fair courts, prosecutorial and law enforcement authorities | 2.1.6 Lack of an effective model of appointment to positions, remuneration, career promotion, and review of disciplinary complaints within the system of the National Police | 2.1.6.3 | A system for evaluating the performance of employees of the National Police as well as an electronic human resources management system have been developed | 2.1.6.3.1 | Drafting and submitting to the Cabinet of Ministers of Ukraine a draft law stipulating that: 1) the procedure of certification of police officers must include the mandatory evaluation of the effectiveness of police officers, and the existing criteria must be supplemented with such evaluation criteria as integrity (using the reasonable doubt approach), managerial competencies (for managers), and job performance; 2) the evaluation of a police officer’s effectiveness as part of certification shall be carried out in the electronic human resources management system (e-HR); 3) the consolidated results of evaluation of the effectiveness of police officers as part of certification shall be published on the official website of the National Police; 4) an interview as a method of evaluation of managerial competencies shall be conducted only for police officers in managerial positions by a committee at least 25 percent of whose members are representatives of the public; 5) the evaluation rating of police officers and the recommendations of the electronic evaluation system must be considered when approving managerial and staffing decisions at the National Police, including with respect to awarding additional kinds of monthly allowances, bonuses. | 01.05.2023 | 31.12.2024 | Ministry of Internal Affairs of Ukraine | National Police of Ukraine | state budget | within the established budget allocations for the relevant year | The draft law has been submitted to the Parliament of Ukraine. | На виконання відповідного заходу Міністерство внутрішніх справ України (далі - МВС) спільно з Національною поліцією України розробили проекту Закону України "Про внесення змін до Закону України "Про Національну поліцію" щодо вдосконалення службової діяльності поліції". Зазначена законодавча ініціатива 21.08.2024 листом МВС № 24159/01/38-2024 подана на розгляд Уряду. 28.10.2024 відповідний законопроект зареєстровано у Верховній Раді України як проект Закону "Про внесення змін до Закону України "Про Національну поліцію" щодо підвищення ефективності службової діяльності поліції" (реєстр. 12159). Водночас 17.07.2025 законопроект реєстр. № 12159 від 28.10.2024 знято з розгляду (відкликано відповідно до ч. 3 ст. 105 Закону України "Про Регламент Верховної Ради України" у зв'язку з припиненням повноважень Кабінету Міністрів України). 31.07.2025 МВС подало на розгляд Уряду проект Закону України "Про внесення змін до Закону України "Про Національну поліцію" щодо підвищення ефективності службової діяльності поліції", який схвалено Кабінетом Міністрів України 26.08.2025 та 29.08.2025 зареєстровано у Верховній Раді України за № 13716. Законопроект від 29.08.2025 № 13716 частково відповідає положенням п.п. 1, 2, 3 та 5 п. 2.1.6.3.1 додатка 2 до Державної антикорупційної програми на 2023 - 2025 роки (далі - Програма), у зв'язку з чим, захід не може вважатися таким, що виконаний повністю. Так, відповідно до п.п. 1 п. 2.1.6.3.1 додатка 2 до Програми у рамках процедури атестування поліцейських законопроект від 29.08.2025 № 13716 мав би додатково до наявних впровадити такий критерій оцінювання, як результативність роботи, водночас відповідні пропозиції у ньому відсутні. Крім того, вимоги п.п. 2, 3, 5 п. 2.1.6.3.1 додатка 2 до Програми про проведення оцінювання ефективності поліцейського в рамках атестування в електронній системі управління персоналом, про оприлюднення узагальнених результатів оцінювання ефективності поліцейських, а також про врахування результатів атестування під час ухвалення управлінських кадрових рішень поширено лише на процедуру атестування поліцейських, які обіймають керівні посади. | Partially implemented | 0.0
2.1 | Fair courts, prosecutorial and law enforcement authorities | 2.1.6 Lack of an effective model of appointment to positions, remuneration, career promotion, and review of disciplinary complaints within the system of the National Police | 2.1.6.3 | A system for evaluating the performance of employees of the National Police as well as an electronic human resources management system have been developed | 2.1.6.3.6 | Arranging an analytical study focused on the prospects of improvement of the staffing policy and changes in the conditions of remuneration of police officers with a view to enhancing the competitive ability of police service in the labor market, including proposals regarding justified options of resolution of the policemen’s low salary | 01.03.2023 | 31.10.2023 | Ministry of Internal Affairs of Ukraine | National Police of Ukraine | state budget and/or international technical assistance funds | within the established budget allocations for the relevant year | The analytical study has been conducted and a report on its findings has been published. | МВС забезпечено проведення аналітичного дослідження, предметом якого є перспективи вдосконалення кадрової політики та зміни умов оплати праці поліцейських з метою підвищення конкурентоспроможності служби в поліції на ринку праці. За результатами моніторингу встановлено, що звіт характеризується загалом високим рівнем доказовості в частині визначення проблеми, оскільки ґрунтується на об'єктивних даних. Звіт також містить пропозиції щодо обґрунтованих варіантів вирішення проблеми низької оплати праці поліцейських. З огляду на фактичну відповідність вжитих дій вимогам Державної антикорупційної програми на 2023 - 2025 роки, захід може вважатися таким, що виконано повністю. | Implemented | 0.0
2.1 | Fair courts, prosecutorial and law enforcement authorities | 2.1.6 Lack of an effective model of appointment to positions, remuneration, career promotion, and review of disciplinary complaints within the system of the National Police | 2.1.6.3 | A system for evaluating the performance of employees of the National Police as well as an electronic human resources management system have been developed | 2.1.6.3.7 | Presenting a report on the findings of the analytical study indicated in subclause 2.1.6.3.6, conducing an expert discussion of the report, reviewing suggestions and critical comments | 01.11.2023 | 31.01.2024 | Ministry of Internal Affairs of Ukraine | National Police of Ukraine | state budget and/or international technical assistance funds | within the established budget allocations for the relevant year | The expert discussion of the report has been conducted and its results have been publicized. | On January 31, 2024, a public discussion of the report on the results of the analytical study referred to in subclause 2.1.6.3.6. took place and a report was prepared and published on the website of the Ministry of Internal Affairs. According to the published report, the analytical study received 2 proposals from the All-Ukrainian Trade Union of the National Police. | Implemented | 0.0