## Заходи
№ Напрямку | Напрямок | Проблема | № ОСР | Назва ОСР | № Заходу | Назва заходу | Дата початку | Дата завершення | Головний виконавець | Співвиконавці | Джерела фінансування | Обсяги фінансування, тис.грн. | Показник (індикатор) виконання | Стан виконання | Статус виконання | Оцінка досягнення ОСР
2.2 | State regulation of the economy | 2.2.3 Excessive and unjustified regulatory burden on businesses, which contributes to a high level of corruption in this sector | 2.2.3.3 | The process of starting the most widespread kinds of business online according to the principle of life situations has been established and streamlined | 2.2.3.3.1 | Compiling the list of the most widespread kinds of business to subsequently allow creating them online via the Unified State Web Portal for Electronic Services | 01.03.2023 | 31.08.2023 | Ministry of Digital Transformation of Ukraine | Ministry of Economy, Environment and Agriculture of Ukraine | state budget | within the established budget allocations for the relevant year | The list of the most widespread kinds of business according to the principle of life situations has been compiled to subsequently allow creating them online. | The list of the most common types of business, based on the principle of life situations regarding the possibility of starting them online, was defined within the framework of the national project Diia.Business. In particular, more than 160 business ideas for starting a business that require minimal start-up capital have been identified, and a list of necessary documents for starting a business and templates of basic documents have been provided. | Implemented | 0.0
2.2 | State regulation of the economy | 2.2.3 Excessive and unjustified regulatory burden on businesses, which contributes to a high level of corruption in this sector | 2.2.3.3 | The process of starting the most widespread kinds of business online according to the principle of life situations has been established and streamlined | 2.2.3.3.2 | Implementing the first stage of development of the comprehensive service of starting a business on the Unified State Web Portal for Electronic Services | 01.09.2023 | 31.03.2024 | Ministry of Digital Transformation of Ukraine |  | state budget | within the established budget allocations for the relevant year | The first stage of development of the comprehensive service of starting a business on the Unified State Web Portal for Electronic Services has been completed. | The Cabinet of Ministers of Ukraine adopted the Resolution No. 1156 dated November 7, 2023, which defines the procedure for providing a comprehensive electronic public service "e-Entrepreneur", which simplifies the conditions for starting and/or conducting business activities and consists of the following electronic public services - state registration of an individual as an entrepreneur; - state registration of changes to the information about an individual entrepreneur contained in the Unified State Register of Legal Entities, Individual Entrepreneurs and Public Associations; - submission of a notice of use or refusal to use a single account; - registration as a single tax payer; - registration as a value added tax payer; - registration of a payment transaction registrar and a software payment transaction registrar, as well as search for a fiscal receipt; - registration of a declaration of compliance of the material and technical base of a business entity with the requirements of fire safety legislation; - submission of information on labor demand (vacancies); - state registration of food market operators' facilities; - issuance of a permit to perform high-risk work and start of operation (use) of high-risk machinery, mechanisms, and equipment; - registration of a declaration of compliance of the material and technical base with the requirements of labor protection legislation; - opening a bank account. The e-Entrepreneur service is provided at the request of an individual who intends to start and/or conduct business activities. The provision of electronic public services that are part of the e-Entrepreneur service through the Unified State Web Portal of Electronic Services is an alternative way of obtaining them and does not exclude the possibility of obtaining these services in accordance with the procedure established by law. The Unified State Web Portal of Electronic Services provides the applicant with the opportunity to choose the electronic public services he/she wishes to receive as part of the e-Entrepreneur service. | Implemented | 0.0
2.2 | State regulation of the economy | 2.2.3 Excessive and unjustified regulatory burden on businesses, which contributes to a high level of corruption in this sector | 2.2.3.3 | The process of starting the most widespread kinds of business online according to the principle of life situations has been established and streamlined | 2.2.3.3.3 | Implementing the second stage of development of the comprehensive service of starting a business on the Unified State Web Portal for Electronic Services | 01.04.2024 | 30.11.2024 | Ministry of Digital Transformation of Ukraine |  | state budget and/or international technical assistance | within the established budget allocations for the relevant year and/or within the limits of international technical funds | The second stage of development of the comprehensive service of starting a business on the Unified State Web Portal for Electronic Services has been completed. | A new comprehensive e-Entrepreneur service has been launched on the Diia portal, which is designed to simplify doing business. e-Entrepreneur can be used by adult citizens of Ukraine who want to register a company, and existing businesses that want to change/expand the direction of their activity. e-Entrepreneur offers a set of services for several types of small businesses – cafes, beauty parlors, points of sale, IT firms, or some other type of activity. The questionnaire specifies the details of services to make it easier for you to decide. The application is automatically sent to public authorities after business registration. You can use the service at any stage of starting or developing a business. New and existing entrepreneurs can access 10 services with one application, namely: 1. State registration of an individual entrepreneur. 2. State registration of changes to information about an individual entrepreneur contained in the Unified State Register. 3. Registration of the declaration of compliance of the material and technical base of the business entity with the requirements of the legislation on fire safety. 4. State registration of the facilities of food market operators. 5. State registration of the creation of an LLC under a model charter. 6. State registration of an LLC transitioning to operation under a model charter. 7. Posting job openings. 8. Registration/transition to the simplified taxation system. 9. Registration as a payer of the value-added tax. 10. Opening a bank account. | Implemented | 0.0
2.2 | State regulation of the economy | 2.2.3 Excessive and unjustified regulatory burden on businesses, which contributes to a high level of corruption in this sector | 2.2.3.3 | The process of starting the most widespread kinds of business online according to the principle of life situations has been established and streamlined | 2.2.3.3.4 | Implementing the third stage of development of the comprehensive service of starting a business on the Unified State Web Portal for Electronic Services | 01.11.2024 | 30.04.2025 | Ministry of Digital Transformation of Ukraine |  | state budget and/or international technical assistance | within the established budget allocations for the relevant year and/or within the limits of international technical funds | The third stage of development of the comprehensive service of starting a business on the Unified State Web Portal for Electronic Services has been completed. | Відповідно до повідомлення головного виконавця: «На Порталі Дія, в рамках комплексної послуги е-Підприємець, яка створена для спрощення ведення бізнесу, можна подати заяву та отримати такі послуги для початку ведення своєї справи: — зареєструвати ФОП або змінити дані про нього; — зареєструвати ТОВ на підставі модельного статуту або перевести діючий ТОВ на модельний статут; — перейти на спрощену систему оподаткування або стати платником податку на додану вартість; — відкрити банківський рахунок; — подати вакансії до Центру зайнятості; — задекларувати відповідність матеріально-технічної бази законодавству з питань пожежної безпеки; — задекларувати відповідність матеріально-технічної бази законодавству з питань охорони праці; — зареєструвати потужності операторів ринку харчових продуктів; — зареєструвати ПРРО; — зареєструвати РРО; — подати повідомлення про прийняття працівника на роботу; — подати повідомлення про використання єдиного рахунку; — подати повідомлення про об’єкти оподаткування (за формою 20-ОПП)». Відповідно до Додатку 2 Програми показником виконання цього заходу є «реалізовано третій етап розробки комплексної послуги з відкриття бізнесу на Єдиному державному вебпорталі електронних послуг». Відповідно до Додатку 2 Програми строк виконання цього заходу визначений як: дата початку виконання - 01 листопада 2024; дата завершення виконання - 30 квітня 2025. З огляду на інформацію, що міститься вище, за результатами моніторингу за IІ квартал поточного року заходу 2.2.3.3.4 Програми присвоєно статус «виконано» (виконано повністю та вчасно). | Implemented | 0.0
2.2 | State regulation of the economy | 2.2.3 Excessive and unjustified regulatory burden on businesses, which contributes to a high level of corruption in this sector | 2.2.3.3 | The process of starting the most widespread kinds of business online according to the principle of life situations has been established and streamlined | 2.2.3.3.5 | Putting into operation the comprehensive service of starting a business on the Unified State Web Portal for Electronic Services | 01.05.2025 | 31.07.2025 | Ministry of Digital Transformation of Ukraine |  | state budget and/or international technical assistance | within the established budget allocations for the relevant year and/or within the limits of international technical funds | The Unified State Web Portal for Electronic Services allows starting the most widespread kinds of business according to the principle of life situations. | Інформація за 3 квартал 2025 року. За посиланням забезпечено можливість подати заяву та отримати всі необхідні послуги для початку ведення своєї справи: https://diia.gov.ua/services/e-pidpriyemec Крім того, розроблено проект постанови Кабінету Міністрів України “Про внесення змін до Порядку надання комплексної електронної публічної послуги “е-Підприємець”, що спрямований на розширення переліку послуг, які стануть доступними для отримання в рамках комплексної електронної публічної послуги “е-Підприємець”, який готується до засилу до заінтересованих органів. З огляду на вищенаписане захід виконаний повністю та вчасно. | Implemented | 0.0