## Заходи
№ Напрямку | Напрямок | Проблема | № ОСР | Назва ОСР | № Заходу | Назва заходу | Дата початку | Дата завершення | Головний виконавець | Співвиконавці | Джерела фінансування | Обсяги фінансування, тис.грн. | Показник (індикатор) виконання | Стан виконання | Статус виконання | Оцінка досягнення ОСР
2.2 | State regulation of the economy | 2.2.3 Excessive and unjustified regulatory burden on businesses, which contributes to a high level of corruption in this sector | 2.2.3.6 | Regulatory acts of local self-government bodies and officials have been reviewed with a focus on their effectiveness; proposals have been submitted to amend acts that do not meet the requirements of current legislation, contain factors that foster corruption or distort competition | 2.2.3.6.1 | Causing the Interagency Working Group on Issues of Accelerated Revision of Instruments of Government Regulation of Business to prepare proposals for the central executive authorities | 01.03.2023 | 31.08.2023 | Ministry of Economy, Environment and Agriculture of Ukraine |  | State budget | within the established budget allocations for the relevant year | Proposals of the Interagency Group have been submitted to the concerned agencies. | The Ministry of Economy of Ukraine continues to provide updated information on the effectiveness of the implementation of the measure. Thus, according to the Ministry of Economy of Ukraine, nineteen meetings of the Interagency Group on Issues of Accelerated Revision of Instruments of Government Regulation of Business were held (18 meetings on the review of instruments, 1 meeting on the review of control functions of authorities). As a result of this work: 1. 1323 instruments of government regulation of business of 20 central executive authorities were reviewed: - Ministry of Health of Ukraine - 310, - Ministry for Communities, Territories and Infrastructure Development of Ukraine - 225, - Ministry of Agrarian Policy and Food of Ukraine - 212, - Ministry of Environmental Protection and Natural Resources of Ukraine - 161, - Ministry of Economy of Ukraine - 107, - Ministry of Internal Affairs of Ukraine - 87, - Ministry of Finance of Ukraine - 45, - Ministry of Culture and Information Policy of Ukraine - 35, - National Commission for State Regulation of Energy and Public Utilities - 34, - Ministry of Education and Science - 23, - National Commission for the State Regulation of Electronic Communications, Radiofrequency Spectrum and the Provision of Postal Services - 22, - Administration of State Service of Special Communications and Information Protection of Ukraine - 18, - State Space Agency of Ukraine - 8, - Ministry of Justice of Ukraine - 7, - Ministry for Strategic Industries of Ukraine - 7, - Ministry of Youth and Sports of Ukraine - 7, - State Film Agency of Ukraine - 5, - Ministry of Energy of Ukraine - 4, - State Property Fund of Ukraine - 3, - State Nuclear Regulatory Inspectorate of Ukraine - 3. The Interagency Group reviewed 100 percent of the total number of instruments of government regulation of business scheduled for review at its meetings and approved the minutes of its meetings. About a third of the reviewed instruments are to be cancelled. The proposals of the Interagency Group were sent to the concerned authorities. 2. 6 areas of state control over the transport of goods and passengers by sea, river, rail, road, air, and postal services were reviewed. During the monitoring of the implementation of the measure, scheduled to be implemented in August 2023, it was found that it was fully implemented, but with a delay. | Implemented | 0.0
2.2 | State regulation of the economy | 2.2.3 Excessive and unjustified regulatory burden on businesses, which contributes to a high level of corruption in this sector | 2.2.3.6 | Regulatory acts of local self-government bodies and officials have been reviewed with a focus on their effectiveness; proposals have been submitted to amend acts that do not meet the requirements of current legislation, contain factors that foster corruption or distort competition | 2.2.3.6.2 | Semiannual monitoring of the drafting and entry into force of normative legal acts aimed at the implementation of the proposals of the Interagency Working Group on Issues of Accelerated Revision of Instruments of Government Regulation of Business | 01.09.2023 | 31.12.2025 | Ministry of Economy, Environment and Agriculture of Ukraine |  | State budget | within the established budget allocations for the relevant year | The monitoring results have been made public. | За результатами моніторингу за 1 квартал 2025 року, відповідно інформації, МРГ опрацювала 1323 регуляторних інструментів для бізнесу. З них: - 456 рекомендовано скасувати; -283 залишити без змін; - 584 рекомендовано оптимізувати; - 352 скасовано. Інформація доступна за посиланням: https://deregulation.me.gov.ua За результатами моніторингу за 2 квартал 2025 року, відповідно до інформації, МРГ опрацювала 1323 регуляторних інструментів для бізнесу. З них: - 456 рекомендовано скасувати; - 584 рекомендовано оптимізувати. За результатами моніторингу за 2 квартал 2025 року, відповідно до інформації: 584 рекомендовано оптимізувати, 456 рекомендовано скасувати. З огляду на вищенаписане, прогрес у виконанні заходу відсутній. За результатами моніторингу за 4 квартал 2025 року, відповідно до інформації Міністерства економіки, довкілля та сільського господарства України: 584 рекомендовано оптимізувати, 456 рекомендовано скасувати (інформація доступна за посиланням: https://deregulation.me.gov.ua/). За інформацією, наданою Міністерством економіки, довкілля та сільського господарства України, за 1 квартал 2026 року, в період з вересня 2023 року до грудня 2025 року моніторинг проведено, прийнято 37 нормативно-правових актів, якими скасовано 357 інструментів державного регулювання бізнесу. При цьому надана інформація не підкріплена джерелом, яке б її підтверджувало. За результатами моніторингу станом на 2 квартал 2026 року головним виконавцем не надано нової інформації, яка б свідчила про зміну стану виконання заходу. З огляду на те, що а) настала дата завершення виконання заходу; б) замість безпосереднього моніторингу розроблення та набрання чинності нормативно-правовими актами, спрямованих на реалізацію пропозицій МРГ, надавалися посилання на діяльність МРГ, захід 2.2.3.6.2. вважається невиконаним. | Not implemented | 0.0