## Заходи
№ Напрямку | Напрямок | Проблема | № ОСР | Назва ОСР | № Заходу | Назва заходу | Дата початку | Дата завершення | Головний виконавець | Співвиконавці | Джерела фінансування | Обсяги фінансування, тис.грн. | Показник (індикатор) виконання | Стан виконання | Статус виконання | Оцінка досягнення ОСР
1.1 | Shaping and implementing the state anticorruption policy | 1.1.1 The state anticorruption policy is not always based on complete, objective, and reliable data; The efforts of different government agencies, local self-government bodies, and the public are not sufficiently coordinated | 1.1.1.2 | A single unified system for gathering, consolidating, and visualizing statistical data prescribed by Part 2 of Article 183 of the Law of Ukraine On Prevention of Corruption (hereinafter “the Law”) on the performance of the National Agency, the National Anticorruption Bureau of Ukraine, the State Bureau of Investigations, ARMA, the National Police of Ukraine, the prosecutorial authorities, courts and other government agencies has been implemented | 1.1.1.2.1 | Defining the procedure by which the National Anticorruption Bureau, the State Bureau of Investigations, the Asset Recovery and Management Agency, the National Police, prosecutorial authorities, courts, and other government agencies shall furnish information prescribed by Article 183 of the Law to the National Agency | 01.03.2023 | 31.05.2023 | National Agency on Corruption Prevention |  | state budget | within the established budget allocations for the relevant year | The procedure for furnishing information prescribed by Article 183 of the Law has been defined | Under Article 18-3(3) of the Law of Ukraine On Prevention of Corruption, the National Agency on Corruption Prevention approved Order No. 115/23 dated May 31, 2023, On Approving the Procedure for Providing Statistical Data and Other Information Related to the Implementation of the State Anti-Corruption Policy by Specially Authorized Anti-Corruption Entities and Actors Implementing the State Anti-Corruption Program for the Implementation of the Anti-Corruption Strategy, registered with the Ministry of Justice of Ukraine on June 8, 2023, under No. 955/40011 (as amended by Order of the National Agency on Corruption Prevention No. 125/23 of June 14, 2023 On Taking into Account the Comments Made by the State Registration Body on the Order of the National Agency on Corruption Prevention No. 115/23 of May 31, 2023, registered with the Ministry of Justice of Ukraine on June 15, 2023 under No. 1002/40058). | Implemented | 0.0
1.1 | Shaping and implementing the state anticorruption policy | 1.1.1 The state anticorruption policy is not always based on complete, objective, and reliable data; The efforts of different government agencies, local self-government bodies, and the public are not sufficiently coordinated | 1.1.1.2 | A single unified system for gathering, consolidating, and visualizing statistical data prescribed by Part 2 of Article 183 of the Law of Ukraine On Prevention of Corruption (hereinafter “the Law”) on the performance of the National Agency, the National Anticorruption Bureau of Ukraine, the State Bureau of Investigations, ARMA, the National Police of Ukraine, the prosecutorial authorities, courts and other government agencies has been implemented | 1.1.1.2.2 (1) | Annual submission (by February 15) by specially authorized anticorruption entities and actors implementing the 2023-2025 State Anticorruption Program (hereinafter “the Program”) of statistical data on the results of their work to the National Agency, with mandatory inclusion of data specified in Part 2 of Article 183 of the Law | 01.02.2024 | 28.02.2025 | National Anti-Corruption Bureau of Ukraine |  | state budget | within the established budget allocations for the relevant year | 1) The scope of statistical data conforms to the requirements of Article 183 of the Law. 2) Statistics are submitted in accordance with the Procedure defined by the National Agency, particularly in keeping with submission deadlines | Національне антикорупційне бюро України, у межах повноважень, направило відповідні статистичні дані за 2023 рік листом від 15.02.2024 № 01-043/4562, а листом від 14.02.2025 № 04-043/4732 - за 2024 рік у повному обсязі із дотриманням граничних термінів її надання. Надіслані статистичні дані систематизовано та оприлюднено у розділі «Статистична інформація про результати роботи спеціально уповноважених суб’єктів у сфері протидії корупції та інших державних органів» Інформаційної системи моніторингу реалізації державної антикорупційної політики. | Implemented | 0.0
1.1 | Shaping and implementing the state anticorruption policy | 1.1.1 The state anticorruption policy is not always based on complete, objective, and reliable data; The efforts of different government agencies, local self-government bodies, and the public are not sufficiently coordinated | 1.1.1.2 | A single unified system for gathering, consolidating, and visualizing statistical data prescribed by Part 2 of Article 183 of the Law of Ukraine On Prevention of Corruption (hereinafter “the Law”) on the performance of the National Agency, the National Anticorruption Bureau of Ukraine, the State Bureau of Investigations, ARMA, the National Police of Ukraine, the prosecutorial authorities, courts and other government agencies has been implemented | 1.1.1.2.2 (2) | Annual submission (by February 15) by specially authorized anticorruption entities and actors implementing the 2023-2025 State Anticorruption Program (hereinafter “the Program”) of statistical data on the results of their work to the National Agency, with mandatory inclusion of data specified in Part 2 of Article 183 of the Law | 01.02.2024 | 28.02.2025 | State Bureau of Investigation |  | state budget | within the established budget allocations for the relevant year | 1) The scope of statistical data conforms to the requirements of Article 183 of the Law. 2) Statistics are submitted in accordance with the Procedure defined by the National Agency, particularly in keeping with submission deadlines | Державне бюро розслідувань, у межах повноважень, направило відповідні статистичні дані за 2023 рік листом від 13.02.2024 № 1887-24/10-6-01-1882/24, листом від 13.02.2025 № 10-6-01-4421 - за 2024 рік, листом від 09.02.2026 № 1592-26/10-6-01-1769/26 - за 2025 рік у повному обсязі із дотриманням граничних термінів її надання. Надіслані статистичні дані систематизовано та оприлюднено у розділі «Статистична інформація про результати роботи спеціально уповноважених суб’єктів у сфері протидії корупції та інших державних органів» Інформаційної системи моніторингу реалізації державної антикорупційної політики. | Implemented | 0.0
1.1 | Shaping and implementing the state anticorruption policy | 1.1.1 The state anticorruption policy is not always based on complete, objective, and reliable data; The efforts of different government agencies, local self-government bodies, and the public are not sufficiently coordinated | 1.1.1.2 | A single unified system for gathering, consolidating, and visualizing statistical data prescribed by Part 2 of Article 183 of the Law of Ukraine On Prevention of Corruption (hereinafter “the Law”) on the performance of the National Agency, the National Anticorruption Bureau of Ukraine, the State Bureau of Investigations, ARMA, the National Police of Ukraine, the prosecutorial authorities, courts and other government agencies has been implemented | 1.1.1.2.2 (3) | Annual submission (by February 15) by specially authorized anticorruption entities and actors implementing the 2023-2025 State Anticorruption Program (hereinafter “the Program”) of statistical data on the results of their work to the National Agency, with mandatory inclusion of data specified in Part 2 of Article 183 of the Law | 01.02.2024 | 28.02.2025 | Asset Recovery and Management Agency |  | state budget | within the established budget allocations for the relevant year | 1) The scope of statistical data conforms to the requirements of Article 183 of the Law. 2) Statistics are submitted in accordance with the Procedure defined by the National Agency, particularly in keeping with submission deadlines | Національне агентство України з питань виявлення, розшуку та управління активами, одержаними від корупційних та інших злочинів, у межах повноважень, направило відповідні статистичні дані за 2023 рік листом від 15.02.2024 № 1940/1-31-24/14, а листом від 12.02.2025 № 1449/1-31-25/14 - за 2024 рік у повному обсязі із дотриманням граничних термінів її надання. Надіслані статистичні дані систематизовано та оприлюднено у розділі «Статистична інформація про результати роботи спеціально уповноважених суб’єктів у сфері протидії корупції та інших державних органів» Інформаційної системи моніторингу реалізації державної антикорупційної політики. | Implemented | 0.0
1.1 | Shaping and implementing the state anticorruption policy | 1.1.1 The state anticorruption policy is not always based on complete, objective, and reliable data; The efforts of different government agencies, local self-government bodies, and the public are not sufficiently coordinated | 1.1.1.2 | A single unified system for gathering, consolidating, and visualizing statistical data prescribed by Part 2 of Article 183 of the Law of Ukraine On Prevention of Corruption (hereinafter “the Law”) on the performance of the National Agency, the National Anticorruption Bureau of Ukraine, the State Bureau of Investigations, ARMA, the National Police of Ukraine, the prosecutorial authorities, courts and other government agencies has been implemented | 1.1.1.2.2 (4) | Annual submission (by February 15) by specially authorized anticorruption entities and actors implementing the 2023-2025 State Anticorruption Program (hereinafter “the Program”) of statistical data on the results of their work to the National Agency, with mandatory inclusion of data specified in Part 2 of Article 183 of the Law | 01.02.2024 | 28.02.2025 | National Police of Ukraine |  | state budget | within the established budget allocations for the relevant year | 1) The scope of statistical data conforms to the requirements of Article 183 of the Law. 2) Statistics are submitted in accordance with the Procedure defined by the National Agency, particularly in keeping with submission deadlines | Національна поліція України, у межах повноважень, направила відповідні статистичні дані за 2023 рік листом від 13.02.2024 № 24286/01-2024, листом від 12.02.2025 № 22919/01-2025 - за 2024 рік, листом від 13.02.2026 № 21586/06-2026 - за 2025 рік у повному обсязі із дотриманням граничних термінів її надання. Надіслані статистичні дані систематизовано та оприлюднено у розділі «Статистична інформація про результати роботи спеціально уповноважених суб’єктів у сфері протидії корупції та інших державних органів» Інформаційної системи моніторингу реалізації державної антикорупційної політики. | Implemented | 0.0
1.1 | Shaping and implementing the state anticorruption policy | 1.1.1 The state anticorruption policy is not always based on complete, objective, and reliable data; The efforts of different government agencies, local self-government bodies, and the public are not sufficiently coordinated | 1.1.1.2 | A single unified system for gathering, consolidating, and visualizing statistical data prescribed by Part 2 of Article 183 of the Law of Ukraine On Prevention of Corruption (hereinafter “the Law”) on the performance of the National Agency, the National Anticorruption Bureau of Ukraine, the State Bureau of Investigations, ARMA, the National Police of Ukraine, the prosecutorial authorities, courts and other government agencies has been implemented | 1.1.1.2.2 (5) | Annual submission (by February 15) by specially authorized anticorruption entities and actors implementing the 2023-2025 State Anticorruption Program (hereinafter “the Program”) of statistical data on the results of their work to the National Agency, with mandatory inclusion of data specified in Part 2 of Article 183 of the Law | 01.02.2024 | 28.02.2025 | Prosecutor General’s Office of Ukraine |  | state budget | within the established budget allocations for the relevant year | 1) The scope of statistical data conforms to the requirements of Article 183 of the Law. 2) Statistics are submitted in accordance with the Procedure defined by the National Agency, particularly in keeping with submission deadlines | Офіс Генерального прокурора, у межах повноважень, направив відповідні статистичні дані за 2023 рік листом від 15.02.2024 № 25/1-13866ВИХ-24, а листом від 14.02.2025 № 25/1-13622ВИХ-25 - за 2024 рік у повному обсязі із дотриманням граничних термінів її надання. Надіслані статистичні дані систематизовано та оприлюднено у розділі «Статистична інформація про результати роботи спеціально уповноважених суб’єктів у сфері протидії корупції та інших державних органів» Інформаційної системи моніторингу реалізації державної антикорупційної політики. | Implemented | 0.0
1.1 | Shaping and implementing the state anticorruption policy | 1.1.1 The state anticorruption policy is not always based on complete, objective, and reliable data; The efforts of different government agencies, local self-government bodies, and the public are not sufficiently coordinated | 1.1.1.2 | A single unified system for gathering, consolidating, and visualizing statistical data prescribed by Part 2 of Article 183 of the Law of Ukraine On Prevention of Corruption (hereinafter “the Law”) on the performance of the National Agency, the National Anticorruption Bureau of Ukraine, the State Bureau of Investigations, ARMA, the National Police of Ukraine, the prosecutorial authorities, courts and other government agencies has been implemented | 1.1.1.2.2 (6) | Annual submission (by February 15) by specially authorized anticorruption entities and actors implementing the 2023-2025 State Anticorruption Program (hereinafter “the Program”) of statistical data on the results of their work to the National Agency, with mandatory inclusion of data specified in Part 2 of Article 183 of the Law | 01.02.2024 | 28.02.2025 | State Judicial Administration of Ukraine | Supreme Court , High Anti-Corruption Court of Ukraine | state budget | within the established budget allocations for the relevant year | 1) The scope of statistical data conforms to the requirements of Article 183 of the Law. 2) Statistics are submitted in accordance with the Procedure defined by the National Agency, particularly in keeping with submission deadlines | Державна судова адміністрація України, у межах повноважень, направила відповідні статистичні дані за 2023 рік листом від 15.02.2024 № 20-4782/24, а листом від 14.02.2025 № 15-3286/25 - за 2024 рік у повному обсязі із дотриманням граничних термінів її надання. Надіслані статистичні дані систематизовано та оприлюднено у розділі «Статистична інформація про результати роботи спеціально уповноважених суб’єктів у сфері протидії корупції та інших державних органів» Інформаційної системи моніторингу реалізації державної антикорупційної політики. | Implemented | 0.0
1.1 | Shaping and implementing the state anticorruption policy | 1.1.1 The state anticorruption policy is not always based on complete, objective, and reliable data; The efforts of different government agencies, local self-government bodies, and the public are not sufficiently coordinated | 1.1.1.2 | A single unified system for gathering, consolidating, and visualizing statistical data prescribed by Part 2 of Article 183 of the Law of Ukraine On Prevention of Corruption (hereinafter “the Law”) on the performance of the National Agency, the National Anticorruption Bureau of Ukraine, the State Bureau of Investigations, ARMA, the National Police of Ukraine, the prosecutorial authorities, courts and other government agencies has been implemented | 1.1.1.2.2 (7) | Annual submission (by February 15) by specially authorized anticorruption entities and actors implementing the 2023-2025 State Anticorruption Program (hereinafter “the Program”) of statistical data on the results of their work to the National Agency, with mandatory inclusion of data specified in Part 2 of Article 183 of the Law | 01.02.2024 | 28.02.2025 | Economic Security Bureau of Ukraine |  | state budget | within the established budget allocations for the relevant year | 1) The scope of statistical data conforms to the requirements of Article 183 of the Law. 2) Statistics are submitted in accordance with the Procedure defined by the National Agency, particularly in keeping with submission deadlines | Бюро економічної безпеки України, у межах повноважень, направило відповідні статистичні дані за 2023 рік листом від 15.02.2024 № 11/20/1569-24, а листом від 12.02.2025 № 11/20/1523-25 - за 2024 рік у повному обсязі із дотриманням граничних термінів її надання. Надіслані статистичні дані систематизовано та оприлюднено у розділі «Статистична інформація про результати роботи спеціально уповноважених суб’єктів у сфері протидії корупції та інших державних органів» Інформаційної системи моніторингу реалізації державної антикорупційної політики. | Implemented | 0.0
1.1 | Shaping and implementing the state anticorruption policy | 1.1.1 The state anticorruption policy is not always based on complete, objective, and reliable data; The efforts of different government agencies, local self-government bodies, and the public are not sufficiently coordinated | 1.1.1.2 | A single unified system for gathering, consolidating, and visualizing statistical data prescribed by Part 2 of Article 183 of the Law of Ukraine On Prevention of Corruption (hereinafter “the Law”) on the performance of the National Agency, the National Anticorruption Bureau of Ukraine, the State Bureau of Investigations, ARMA, the National Police of Ukraine, the prosecutorial authorities, courts and other government agencies has been implemented | 1.1.1.2.2 (8) | Annual submission (by February 15) by specially authorized anticorruption entities and actors implementing the 2023-2025 State Anticorruption Program (hereinafter “the Program”) of statistical data on the results of their work to the National Agency, with mandatory inclusion of data specified in Part 2 of Article 183 of the Law | 01.02.2024 | 28.02.2025 | Security Service of Ukraine |  | state budget | within the established budget allocations for the relevant year | 1) The scope of statistical data conforms to the requirements of Article 183 of the Law. 2) Statistics are submitted in accordance with the Procedure defined by the National Agency, particularly in keeping with submission deadlines | Служба безпеки України, у межах повноважень, направила відповідні статистичні дані за 2023 рік листом від 15.02.2024 № 9/1739ві, листом від 17.02.2025 № 9/61-4ві - за 2024 рік, листом від 12.02.2026 № 9/495ві - за 2025 рік у повному обсязі. Разом з цим статистична інформація за 2024 рік направлена з порушенням граничних строків її подання (після 15 лютого), що не повністю відповідає показнику виконання заходу 1.1.1.2.2 (8). З огляду на це відповідному заходу присвоєно статус "Виконано частково". Надіслані статистичні дані систематизовано та оприлюднено у розділі «Статистична інформація про результати роботи спеціально уповноважених суб’єктів у сфері протидії корупції та інших державних органів» Інформаційної системи моніторингу реалізації державної антикорупційної політики. | Partially implemented | 0.0
1.1 | Shaping and implementing the state anticorruption policy | 1.1.1 The state anticorruption policy is not always based on complete, objective, and reliable data; The efforts of different government agencies, local self-government bodies, and the public are not sufficiently coordinated | 1.1.1.2 | A single unified system for gathering, consolidating, and visualizing statistical data prescribed by Part 2 of Article 183 of the Law of Ukraine On Prevention of Corruption (hereinafter “the Law”) on the performance of the National Agency, the National Anticorruption Bureau of Ukraine, the State Bureau of Investigations, ARMA, the National Police of Ukraine, the prosecutorial authorities, courts and other government agencies has been implemented | 1.1.1.2.3 | Gathering, consolidating, and visualizing (by April 15) statistical data submitted by specially authorized anticorruption entities and other government agencies pursuant to Article 183 of the Law, on the official website of the National Agency (following the creation of the information system for monitoring the implementation of the state anticorruption policy (hereinafter “the information monitoring system”) — within a dedicated segment of this system) | 01.03.2023 | 30.04.2025 | National Agency on Corruption Prevention |  | state budget | within the established budget allocations for the relevant year | Statistical data are published annually (by April 15) on the official website of the National Agency | 1) В І кварталі 2024 року зібрано та узагальнено статистичну інформацію за 2023 рік, що надається спеціально уповноваженими суб’єктами у сфері протидії корупції та іншими державними органами (ДСА, ДБР, БЕБ, СБУ та інші) за формами статистичної звітності відповідно до Порядку надання спеціально уповноваженими суб’єктами у сфері протидії корупції та виконавцями державної антикорупційної програми з виконання Антикорупційної стратегії статистичних даних та іншої інформації, пов’язаної з реалізацією державної антикорупційної політики, затвердженого наказом Національного агентства від 31.05.2023 № 115/23, зареєстрованим у Міністерстві юстиції України 08.06.2023 за № 955/40011(зі змінами). Статистичну інформацію (у т.ч. візуалізовані дані за окремими показниками) оприлюднено 15.04.2024 в рамках створеного окремого розділу Інформаційної системи моніторингу реалізації державної антикорупційної політики. 2) У І кварталі 2025 року зібрано та узагальнено статистичну інформацію за 2024 рік, надану спеціально уповноваженими суб’єктами у сфері протидії корупції та іншими державними органами (ВАКС, ДСА, ДБР, БЕБ, АРМА, СБУ тощо). 3) У І кварталі 2026 року зібрано та узагальнено статистичну інформацію за 2025 рік, надану спеціально уповноваженими суб’єктами у сфері протидії корупції та іншими державними органами (ВАКС, ДСА, ДБР, БЕБ, АРМА, СБУ тощо). Відповідну інформацію (у т.ч. візуалізовані дані за окремими показниками) оприлюднено в окремому розділі Інформаційної системи моніторингу реалізації державної антикорупційної політики. | Implemented | 0.0