## Заходи
№ Напрямку | Напрямок | Проблема | № ОСР | Назва ОСР | № Заходу | Назва заходу | Дата початку | Дата завершення | Головний виконавець | Співвиконавці | Джерела фінансування | Обсяги фінансування, тис.грн. | Показник (індикатор) виконання | Стан виконання | Статус виконання | Оцінка досягнення ОСР
2.3 | Customs and taxation | 2.3.5 Excessive scope of discretionary powers of employees of tax authorities | 2.3.5.1 | Unjustified influence of subjective factors during the exercise of powers by officials of the tax authorities has been prevented | 2.3.5.1.1 | Developing the draft order on amendments to the Procedure of Operation of the Electronic Workspace, approved by the order of the Ministry of Finance dated July 14, 2017, No. 637 pertaining to: a) receipt by a taxpayer of additional fiscal information (information about inclusion in / removal from the list of taxpayers meeting the criteria of a taxpayer with a high risk level, information about suspended registration of tax invoices / reconciliation payments, etc.) about other taxpayers with the prior consent of such individuals, in the form of a document of an established format, in electronic form with the application of the qualified electronic seal of the controlling authority; b) expansion of services available in the electronic taxpayer workspace by launching new electronic services that allow, among other things, correspondence through the electronic workspace between the controlling authorities and taxpayers that submit reports in electronic form and/or passed electronic identification online in the electronic workspace and applied to receive documents through the electronic workspace. | 01.03.2023 | 30.04.2023 | Ministry of Finance of Ukraine | State Tax Service of Ukraine | state budget | within the established budget allocations for the relevant year | The draft order has been drafted and publicized for a public discussion. | Станом на 30.04.2023 Міністерством фінансів України повідомлено, що розроблено проєкт Наказу «Про внесення змін у додаток 5 до Порядку функціонування Електронного кабінету», який охоплює положення підпунтку "а" заходу 2.3.5.1.1. В свою чергу Наказом Міністерства фінансів України від 18.03.2021 № 159 "Про затвердження Змін до Порядку функціонування Електронного кабінету" передбачено положення підпункту "б" заходу 2.3.5.1.1. Водночас одним із показників виконання зазначеного заходу є оприлюднення зазначеного наказу для проведення громадського обговорення. При цьому інформації щодо оприлюднення відповідного наказу для проведення громадського обговорення надано не було. З огляду на це за наслідками моніторингу цьому заходу присвоєно статус "Виконано частково". Водночас станом на І квартал 2024 року Міністерством фінансів України повідомлено, що проєкт наказу обговорювався на робочих групах, а також те, що відповідні зміни до наказу щодо Порядку функціонування Електронного кабінету було внесено за пропозицією представників громадськості, бізнес-асоціацій та експертів з питань оподаткування. Крім того, відповідно до листа Державної регуляторної служби України від 03.02.2023 № 9087 проєкт наказу не містить норм регуляторного характеру, а його прийняття не потребує реалізації процедур, передбачених Законом України «Про засади державної регуляторної політики у сфері господарської діяльності», що свідить про виконання заходу в повній мірі. В межах звітування за ІІ квартал 2024 року Міністерством фінансів додатково повідомлено, що відповідно до пояснювальної записки до проєкту наказу його розроблено відповідно до Податкового кодексу України, Закону України від 30.11.2021 № 1914-ІХ «Про внесення змін до Податкового кодексу України та інших законодавчих актів України щодо забезпечення збалансованості бюджетних надходжень». Відповідно до пункту 5 розділу II "Прикінцеві положення" цього Закону до порядку підготовки та прийняття нормативно-правових актів, що приймаються на виконання вимог цього Закону, не застосовуються вимоги Закону України "Про засади державної регуляторної політики у сфері господарської діяльності". Враховуючи це, оприлюднення з метою громадського обговорення проєкту наказу не здійснювалось. Аналогічна за змістом інформація надана під час звітування за ІІІ-IV квартали 2024 року, І-ІІІ квартали 2025 року. Однак під час оцінювання виконання заходу 2.3.5.1.1 слід враховувати таке: - одним із показників виконання зазначеного заходу є саме оприлюднення проєкту зазначеного наказу для проведення громадського обговорення. Проте Виконавцем не надано інформації ані щодо оприлюднення відповідного наказу для проведення громадського обговорення, ані проведення самого громадського обговорення; - лист Державної регуляторної служби носить інформаційний характер та не є нормативно-правовим актом, відтак не створює юридичних наслідків. Водночас положення щодо оприлюднення проєкту Наказу «Про внесення змін у додаток 5 до Порядку функціонування Електронного кабінету» для проведення громадського обговорення передбачено положеннями Державної антикорупційної програми на 2023-2025 роки, затвердженою постановою Кабінету Міністрів України від 04.03.2023 № 220, яка підлягає виконанню відповідальними органами. Враховуючи те, що проєкт наказу розроблено, однак його не оприлюднено для проведення громадського обговорення, то показник виконання заходу 2.3.5.1.1. не досягнутий у повній мірі. З огляду на це захід є виконаним вчасно, проте частково. | Partially implemented | 0.0
2.3 | Customs and taxation | 2.3.5 Excessive scope of discretionary powers of employees of tax authorities | 2.3.5.1 | Unjustified influence of subjective factors during the exercise of powers by officials of the tax authorities has been prevented | 2.3.5.1.2 | Clearing the draft order indicated in subclause 2.3.5.1.1 with the concerned authorities and reworking the draft (if necessary) | 01.05.2023 | 30.06.2023 | Ministry of Finance of Ukraine | State Tax Service of Ukraine | state budget | within the established budget allocations for the relevant year | The public discussion has been conducted and its results have been made public. | Станом на 30.06.2023 Міністерством фінансів України повідомлено, що проект Наказу «Про внесення змін у додаток 5 до Порядку функціонування Електронного кабінету» погоджено із Міністерством цифрової трансформації України, Державною службою спеціального зв'язку та захисту інформації України та Державною податковою службою України. Водночас показником виконання цього заходу є проведення громадського обговорення та оприлюднення його результатів, проте інформації щодо цього надано не було. З огляду на це за наслідками моніторингу цьому заходу присвоєно статус "Виконано частково". Водночас станом на І квартал 2024 року Міністерством фінансів України повідомлено, що проект наказу обговорювався на робочих групах, а також те, що відповідні зміни до наказу щодо Порядку функціонування Електронного кабінету було внесено за пропозицією представників громадськості, бізнес-асоціацій та експертів з питань оподаткування. Крім того, відповідно до листа Державної регуляторної служби України від 03.02.2023 № 9087 проект наказу не містить норм регуляторного характеру, а його прийняття не потребує реалізації процедур, передбачених Законом України «Про засади державної регуляторної політики у сфері господарської діяльності», що свідить про виконання заходу в повній мірі. В межах звітування за ІІ квартал 2024 року Міністерством фінансів повідомлено, що відповідно до пояснювальної записки до проекту наказу його розроблено відповідно до Податкового кодексу України, Закону України від 30.11.2021 № 1914-ІХ «Про внесення змін до Податкового кодексу України та інших законодавчих актів України щодо забезпечення збалансованості бюджетних надходжень». Відповідно до пункту 5 розділу II "Прикінцеві положення" цього Закону до порядку підготовки та прийняття нормативно-правових актів, що приймаються на виконання вимог цього Закону, не застосовуються вимоги Закону України "Про засади державної регуляторної політики у сфері господарської діяльності". Враховуючи це, оприлюднення з метою громадського обговорення проекту наказу не здійснювалось. Аналогічна за змістом інформація надана в межах звітування за ІІІ-IV квартали 2024 року, І квартал 2025 року. Однак під час оцінювання виконання заходу слід враховувати таке: - одним із показників виконання зазначеного заходу є саме проведення громадського обговорення та оприлюднення його результатів. Проте Виконавцем не надано інформації ані щодо оприлюднення відповідного наказу для проведення громадського обговорення, ані проведення самого громадського обговорення; - лист Державної регуляторної служби носить інформаційний характер та не є нормативно-правовим актом, відтак не створює юридичних наслідків. Водночас положення щодо проведення громадського обговорення проекту Наказу «Про внесення змін у додаток 5 до Порядку функціонування Електронного кабінету» та оприлюднення його результатів передбачено положеннями Державної антикорупційної програми на 2023-2025 роки, затвердженої постановою Кабінету Міністрів України від 04.03.2023 № 220, яка підлягає виконанню відповідальними органами. Враховуючи те, що проект наказу погоджено із заінтересованими органами, однак громадське обговорення не проведено та не оприлюднено його результати, це свідчить, що показник виконання заходу 2.3.5.1.2. не досягнуто. З огляду на це захід є виконаним вчасно, проте частково. | Implemented | 0.0
2.3 | Customs and taxation | 2.3.5 Excessive scope of discretionary powers of employees of tax authorities | 2.3.5.1 | Unjustified influence of subjective factors during the exercise of powers by officials of the tax authorities has been prevented | 2.3.5.1.3 | Supporting the state registration of the order indicated in subclause 2.3.5.1.1 with the Ministry of Justice | 01.07.2023 | 31.07.2023 | Ministry of Finance of Ukraine |  | state budget | within the established budget allocations for the relevant year | The order has been issued, published, its state registration has been completed, and it has been included in the Unified State Register of Normative Legal Acts. | By letter dated February 27, 2023 No. 26020-08-5/5483, the order of the Ministry of Finance of Ukraine dated February 27, 2023 No. 110 On Amendments to Appendix 5 to the Procedure for the Functioning of the Electronic Workspace (hereinafter - Order No. 110) was submitted for state registration to the Ministry of Justice of Ukraine. Order No. 110 was registered on March 8, 2023 under No. 415/39471 and included in the Unified State Register of Normative Legal Acts. Order No. 110 entered into force on March 17, 2023. In accordance with Order No. 110, the list of tax information, which can be provided to the counterparty with the prior consent of the taxpayer in the amount determined by him/her, was expanded. Thus it will be possible through the Electronic Workspace to find out information about the presence of your counterparty in the list of taxpayers who meet the risk criteria of the taxpayer (date of inclusion in / exclusion from such list, risk criteria). You can also get the following information about your counterparty through the Electronic Workspace: • tax address; • information about the place of accounting; • information about officials; • presence of separate divisions; • types of economic activity; • presence of taxation objects; • indebtedness (tax debt); • accrued monetary obligations; • sums of paid taxes, fees, payments; • presence of licenses; • suspension of the tax invoices and/or adjustment calculations registration; • untimely tax invoices and/or adjustment calculations registration; • a list of goods according to the Ukrainian Classification of Goods for Foreign Economic Activity; • transfer pricing reporting; • financial result before taxation; • residual value of fixed assets and intangible assets; • export/import operations performed. Tax information, the scope of which is determined independently by the counterparty when giving consent, may be received by the taxpayer in the Electronic Workspace in electronic form and, if necessary, in the form of an electronic document with the seal of the controlling authority. At the same time, in the private part of the Electronic Workspace, the taxpayer is given the opportunity: - to access and control the state of settlements with the budget, - of electronic correspondence with the State Tax Service of Ukraine authorities, - to send electronic requests for information, applications for registration as the taxpayer of certain taxes, applications for obtaining a certificate of no debts, complaints against a decision of the Commission of the State Tax Service of Ukraine on refusal to register tax invoices/adjustment calculations in the Unified Register of Tax Invoices, - to create and send electronic tax and statistical reports, a report on the amounts of accrued Single Social Contribution, - to use the services of electronic value added tax administration systems, sales of fuel and ethyl alcohol administration systems, - to access the data of the Unified Register of Tax Invoices, the Unified Register of Excise Invoices, of the tax and excise invoices and/or adjustment calculations registration in the Unified Register of Tax Invoices and the Unified Register of Excise Invoices respectively. | Implemented | 0.0
2.3 | Customs and taxation | 2.3.5 Excessive scope of discretionary powers of employees of tax authorities | 2.3.5.1 | Unjustified influence of subjective factors during the exercise of powers by officials of the tax authorities has been prevented | 2.3.5.1.4 | Developing software for expansion of the functionality of the electronic workspace by launching the services indicated in subclause 2.3.5.1.1 | 17.03.2023 | 30.04.2023 | State Tax Service of Ukraine |  | state budget | within the established budget allocations for the relevant year | The software has been developed. | The order of the Ministry of Finance of Ukraine dated February 27, 2023 No. 110 On Amendments to Appendix 5 to the Procedure for the Functioning of the Electronic Workspace approved the new version of the form "Tax Information with the Prior Consent of the Taxpayer in the Amount Determined by Him/Her". In order to execute the said order on April 13, 2023, software for expanding the functionality of the Electronic Workspace by implementing the services specified in subclause 2.3.5.1.1 was developed. | Implemented | 0.0
2.3 | Customs and taxation | 2.3.5 Excessive scope of discretionary powers of employees of tax authorities | 2.3.5.1 | Unjustified influence of subjective factors during the exercise of powers by officials of the tax authorities has been prevented | 2.3.5.1.5 | Putting the functionality indicated in subclause 2.3.5.1.4 into commercial operation | 17.03.2023 | 30.06.2023 | State Tax Service of Ukraine |  | state budget | within the established budget allocations for the relevant year | The functionality has been put into commercial operation. | The order of the Ministry of Finance of Ukraine dated February 27, 2023 No. 110 On Amendments to Appendix 5 to the Procedure for the Functioning of the Electronic Workspace approved the new version of the form "Tax Information with the Prior Consent of the Taxpayer in the Amount Determined by Him/Her". In order to execute the said order, on June 19, 2023, the Electronic Workspace's software was put into commercial operation. This software provides the ability to expand the list of information, which can be provided to the taxpayer (counterparty) with the prior consent, including information related to: - indebtedness (tax debt); - accrued monetary obligations; - sums of paid taxes, fees, payments; - suspension of the tax invoices and/or adjustment calculations registration; - presence of taxation objects; - presence of licenses; - untimely tax invoices and/or adjustment calculations registration; - a list of goods according to the Ukrainian Classification of Goods for Foreign Economic Activity; - information on inclusion in / exclusion from the list of taxpayers who meet the risk criteria of the taxpayer; - transfer pricing reporting; - financial result before taxation; - residual value of fixed assets and intangible assets; - export/import operations performed. At the same time, the functionality of the Electronic Workspace's Application Programming Interface named "submission of reports, applications, requests and registration of invoices" was supplemented with information on the status of document processing. In addition to that, the taxpayer is given the possibility of electronic correspondence with the State Tax Service authorities. | Implemented | 0.0