## Заходи
№ Напрямку | Напрямок | Проблема | № ОСР | Назва ОСР | № Заходу | Назва заходу | Дата початку | Дата завершення | Головний виконавець | Співвиконавці | Джерела фінансування | Обсяги фінансування, тис.грн. | Показник (індикатор) виконання | Стан виконання | Статус виконання | Оцінка досягнення ОСР
2.4 | Public and private sectors of the economy | 2.4.1 The existing governance model at public sector entities is ineffective, resulting in losses and corruption | 2.4.1.1 | The principles of state ownership policy approved by the Cabinet of Ministers of Ukraine are periodically updated and consistently implemented in practice by entities that perform the functions of the owner of public sector entities | 2.4.1.1.1 | Drafting and submitting to the Cabinet of Ministers of Ukraine a draft law that proposes to provide for: 1) the adoption of the State Ownership Policy by the Cabinet of Ministers of Ukraine; 2) the development and adoption of individual ownership policies at state-owned enterprises; 3) the requirements for the contents of the relevant ownership policies (in particular, they must outline the objectives of state ownership, the key tasks of state-owned companies, and principal kinds of business, and performance indicators). | 01.03.2023 | 31.10.2023 | Ministry of Economy, Environment and Agriculture of Ukraine |  | state budget | within the established budget allocations for the relevant year | The draft law has been submitted to the Parliament of Ukraine. | 22.02.2024 Верховною Радою України ухвалено Закон України "Про внесення змін до деяких законодавчих актів України щодо вдосконалення корпоративного управління" № 3587-IX (законопроект, реєстр. № 5593-д) вцілому (Закон набув чинності 08.03.2024). Положення ухваленого закону: а) передбачає ухвалення Кабінетом Міністрів України Політики державної власності (підп. 1 заходу 2.4.1.1.1); б) у порівнянні з редакцією законопроекту, який був ухвалений у першому читанні, ухвалений закон не містить положень щодо розробки та затвердження індивідуальних політик власності на підприємствах державної форми власності (підп. 2 заходу 2.4.1.1.1) ; в) у тексті ухваленого закону відсутні положення щодо вимог до змісту відповідних політик власності (зокрема, повинні містити цілі державної власності, основні завдання державних компаній, основні види господарської діяльності, показники продуктивності) (підп. 3 заходу 2.4.1.1.1). Разом з тим ухваленим Законом передбачено зміни до ст. 6 Закону України «Про управління об’єктами державної власності» та положення про затвердження уповноваженим органом управління на підставі Політики державної власності та після консультацій з наглядовою радою щороку листа очікувань власника, що містить коротко- та середньострокові фінансові, операційні і нефінансові цілі діяльності державного унітарного підприємства, господарського товариства, у статутному капіталі якого більше 50 відсотків акцій (часток) належать державі, що визначаються з урахуванням стратегічних планів розвитку таких підприємств, господарських товариств, та які підлягають оприлюдненню. Такий лист очікування власника потребує оприлюднення. (п. 5 ч. 1 ст. 6, ст. 11-6 ЗУ України «Про управління об’єктами державної власності»). 29.11.2024 Уряд затвердив Політику, яка містить положення, зокрема, про затвердження листа очікувань, в якому визначаються цілі діяльності підприємства, товариства з контрольною часткою держави та цільові показники ефективності для оцінки досягнення цілей діяльності з урахуванням стратегічного плану розвитку відповідного суб’єкта господарювання. Відповідно Методичних рекомендацій щодо підготовки листа очікувань власника, затверджених наказом Мінекономіки від 01.10.2024 № 24098, цілі діяльності підприємства, товариства з контрольною часткою держави, визначаються з урахуванням його комерційної та некомерційної господарської діяльності та мають відповідати положенням його статуту та фактичним видам діяльності. З метою контролю за досягненням цілей діяльності підприємства, товариства з контрольною часткою держави, для кожної фінансової, операційної та нефінансової цілі рекомендовано зазначати відповідні цільові показники ефективності. Крім цього, передбачається затвердження стратегічного плану розвитку, річного фінансового плану, річного інвестиційного плану, інвестиційного плану на середньострокову перспективу (три - п’ять років) державних унітарних підприємств, господарських товариств, у статутному капіталі яких 100 відсотків акцій (часток) належать державі. Також відповідно до стратегічного плану розвитку, Політики державної власності, цілей діяльності, визначених у листі очікувань власника, керівник державного унітарного підприємства, голова виконавчого органу господарського товариства, у статутному капіталі якого більше 50 відсотків акцій (часток) належать державі, зобов’язаний складати і виконувати річний фінансовий план, річний інвестиційний план, інвестиційний план на середньострокову перспективу (три - п’ять років) відповідно до закону. Однак захід 2.4.1.1.1 додатка 2 до Програми вимагає врегулювання саме на законодавчому рівні окремого кола питань. Таким чином, ухвалений закон забезпечує лише часткове врегулювання питань. Щодо інших із них виконавцем заходу мав би бути розроблений законопроект. | Partially implemented | 0.0
2.4 | Public and private sectors of the economy | 2.4.1 The existing governance model at public sector entities is ineffective, resulting in losses and corruption | 2.4.1.1 | The principles of state ownership policy approved by the Cabinet of Ministers of Ukraine are periodically updated and consistently implemented in practice by entities that perform the functions of the owner of public sector entities | 2.4.1.1.2 | Drafting and submitting to the Cabinet of Ministers of Ukraine the draft State Ownership Policy | 09.03.2024 | 09.11.2024 | Ministry of Economy, Environment and Agriculture of Ukraine |  | state budget | within the established budget allocations for the relevant year | The State Ownership Policy has been approved by the Cabinet of Ministers of Ukraine. | Постановою Кабінету Міністрів України від 29.11.2024 № 1369 "Деякі питання Політики державної власності" затверджено Політику державної власності. | Implemented | 0.0
2.4 | Public and private sectors of the economy | 2.4.1 The existing governance model at public sector entities is ineffective, resulting in losses and corruption | 2.4.1.1 | The principles of state ownership policy approved by the Cabinet of Ministers of Ukraine are periodically updated and consistently implemented in practice by entities that perform the functions of the owner of public sector entities | 2.4.1.1.3 | Preparing drafts of individual ownership policies for at least 15 of the largest (in terms of the cumulative value of assets) enterprises under state ownership, which are of strategic importance for the national economy and security | 05.12.2024 | 05.03.2025 | Authorized management bodies |  | state budget | within the established budget allocations for the relevant year | Drafts of individual ownership policies have been developed. | У ході проведення моніторингу не було надано інформації, яка б надала змогу констатувати результат виконання цього заходу. | Not implemented | 0.0
2.4 | Public and private sectors of the economy | 2.4.1 The existing governance model at public sector entities is ineffective, resulting in losses and corruption | 2.4.1.1 | The principles of state ownership policy approved by the Cabinet of Ministers of Ukraine are periodically updated and consistently implemented in practice by entities that perform the functions of the owner of public sector entities | 2.4.1.1.4 | Holding consultations with stakeholders regarding the drafts of individual ownership policies indicated in subclause 2.4.1.1.3, obtaining expert opinions | 05.04.2025 | 05.05.2025 | Authorized management bodies |  | state budget | within the established budget allocations for the relevant year | Consultations with stakeholders regarding the drafts of individual ownership policies for at least 15 of the largest enterprises under state ownership have been held, and expert opinions have been obtained. | У ході проведення моніторингу не було надано інформації, яка б надала змогу констатувати результат виконання цього заходу. | Not implemented | 0.0
2.4 | Public and private sectors of the economy | 2.4.1 The existing governance model at public sector entities is ineffective, resulting in losses and corruption | 2.4.1.1 | The principles of state ownership policy approved by the Cabinet of Ministers of Ukraine are periodically updated and consistently implemented in practice by entities that perform the functions of the owner of public sector entities | 2.4.1.1.5 | Revising the drafts of individual ownership policies indicated in subclause 2.4.1.1.3 (if needed), approving and making them public | 05.06.2025 | 05.07.2025 | Authorized management bodies |  | state budget | within the established budget allocations for the relevant year | The drafts of individual ownership policies for at least 15 of the largest enterprises under state ownership have been revised, approved, and made public. | У ході проведення моніторингу не було надано інформації, яка б надала змогу констатувати початок виконання цього заходу. | Not implemented | 0.0