## Заходи
№ Напрямку | Напрямок | Проблема | № ОСР | Назва ОСР | № Заходу | Назва заходу | Дата початку | Дата завершення | Головний виконавець | Співвиконавці | Джерела фінансування | Обсяги фінансування, тис.грн. | Показник (індикатор) виконання | Стан виконання | Статус виконання | Оцінка досягнення ОСР
2.4 | Public and private sectors of the economy | 2.4.4 A high level of tolerance of corruption in the private sector of the economy | 2.4.4.6 | Effective mechanisms for verification of information on the ultimate beneficial owners of legal entities under private law in the Unified State Register of Legal Entities, Individual Entrepreneurs, and Public Associations have been introduced | 2.4.4.6.1 | Developing the draft Regulation on the Form and Substance of the Structure of Ownership of a Legal Entity | 01.03.2023 | 31.05.2023 | Ministry of Finance of Ukraine |  | state budget | within the established budget allocations for the relevant year | The draft Regulation has been developed. | According to the information of the Ministry of Finance of Ukraine: "the draft order On Amendments to the Order of the Ministry of Finance of Ukraine dated March 19, 2021 No. 163 (hereinafter - the draft order) has been developed. The provisions of the draft order establish the form, substance of the structure of ownership of legal entities and requirements for its completion. The form of the structure of ownership proposed by the draft order will enable legal entities to submit it to the Unified State Register of Legal Entities, Individual Entrepreneurs, and Public Associations (hereinafter - USR) in electronic form. It will also enable the Ministry of Justice of Ukraine to perform an automated check of the structure of ownership and information about the ultimate beneficial owners using the USR software." | Implemented | 0.0
2.4 | Public and private sectors of the economy | 2.4.4 A high level of tolerance of corruption in the private sector of the economy | 2.4.4.6 | Effective mechanisms for verification of information on the ultimate beneficial owners of legal entities under private law in the Unified State Register of Legal Entities, Individual Entrepreneurs, and Public Associations have been introduced | 2.4.4.6.2 | Clearing the draft Regulation indicated in subclause 2.4.4.6.1 with the concerned agencies | 01.05.2023 | 31.08.2023 | Ministry of Finance of Ukraine | Ministry of Digital Transformation of Ukraine, Ministry of Justice of Ukraine, State Financial Monitoring Service of Ukraine | state budget | within the established budget allocations for the relevant year | The draft Regulation has been cleared with stakeholders. | According to the Ministry of Finance of Ukraine: "On July 31, 2023, the Ministry of Finance of Ukraine sent the draft order of the Ministry of Finance of Ukraine On Amendments to the Order of the Ministry of Finance of Ukraine dated March 19, 2021 No. 163 for approval to the concerned authorities (Ministry of Justice of Ukraine, Ministry of Economy of Ukraine, Ministry of Digital Transformation of Ukraine, State Financial Monitoring Service of Ukraine, National Bank of Ukraine, and the National Commission on Securities and Stock Market). On August 01, 2023, the Ministry of Finance published the draft order on its official website (https://www.mof.gov.ua) to receive comments and suggestions from individuals and legal entities, their associations and sent it to the State Regulatory Service of Ukraine for approval. On September 14, 2023, after processing the comments and proposals to the draft order received from the concerned authorities, the Ministry of Finance held a harmonization meeting with representatives of the Ministry of Justice, the National Commission on Securities and Stock Market and the State Financial Monitoring Service. On October 18, 2023, the refined draft order, taking into account the comments and suggestions provided by all of the concerned authorities, was resubmitted for approval to all of the concerned authorities. The refined draft order was approved by the Ministry of Justice, the Ministry of Digital Transformation, the National Bank of Ukraine, the State Financial Monitoring Service and the State Regulatory Service of Ukraine. On November 23, 2023, a meeting was held under the chairmanship of the First Deputy Minister of Finance Denys Uliutin and with the participation of Yuriy Shapovalov, a member of the National Commission on Securities and Stock Market, and other employees of the Ministry of Finance, the National Commission on Securities and Stock Market and the State Financial Monitoring Service to agree on the position of the National Commission on Securities and Stock Market in terms of determining the range of persons who should be reflected in the ownership structure of a legal entity established, in particular, in the form of a joint-stock company. Based on the results of consideration of the proposals of the National Commission on Securities and Stock Market and taking into account the results of the harmonization meeting held on November 23, 2023, the Ministry of Finance finalized the draft order and resubmitted it to the concerned authorities for approval (letter No. 26110-04-5/3295 dated February 02, 2024). The draft order has been approved by the Ministry of Justice of Ukraine, the Ministry of Digital Transformation of Ukraine, the National Bank of Ukraine, the National Securities and Stock Market Commission, the State Financial Monitoring Service of Ukraine and the State Regulatory Service of Ukraine." | Implemented | 0.0
2.4 | Public and private sectors of the economy | 2.4.4 A high level of tolerance of corruption in the private sector of the economy | 2.4.4.6 | Effective mechanisms for verification of information on the ultimate beneficial owners of legal entities under private law in the Unified State Register of Legal Entities, Individual Entrepreneurs, and Public Associations have been introduced | 2.4.4.6.3 | Approving the Regulation indicated in subclause 2.4.4.6.1, ensuring its state registration | 01.08.2023 | 30.09.2023 | Ministry of Finance of Ukraine | Ministry of Justice of Ukraine | state budget | within the established budget allocations for the relevant year | The Regulation has been approved. | The Ministry of Finance of Ukraine adopted Order No. 161, dated April 2, 2024, “On Amendments to the Order of the Ministry of Finance of Ukraine, dated March 19, 2021, No. 163,” which was registered with the Ministry of Justice of Ukraine on April 17, 2024, under No. 560/41905 | Implemented | 0.0
2.4 | Public and private sectors of the economy | 2.4.4 A high level of tolerance of corruption in the private sector of the economy | 2.4.4.6 | Effective mechanisms for verification of information on the ultimate beneficial owners of legal entities under private law in the Unified State Register of Legal Entities, Individual Entrepreneurs, and Public Associations have been introduced | 2.4.4.6.4 | Developing the draft of the Regulation on the Form and Substance of the Structure of Ownership of Legal Entities Subject to State Regulation and Oversight by the National Securities and Stock Market Commission (NSSMC) | 01.03.2023 | 30.04.2023 | National Commission on Securities and Stock Market |  | state budget | within the established budget allocations for the relevant year | The draft Regulation has been developed. | The National Securities and Stock Market Commission adopted decision dated February 27, 2023 No. 210 On Approval of the Draft Decision of the National Securities and Stock Market Commission On Approval of the Regulation on the Form and Substance of the Structure of Ownership. | Implemented | 0.0
2.4 | Public and private sectors of the economy | 2.4.4 A high level of tolerance of corruption in the private sector of the economy | 2.4.4.6 | Effective mechanisms for verification of information on the ultimate beneficial owners of legal entities under private law in the Unified State Register of Legal Entities, Individual Entrepreneurs, and Public Associations have been introduced | 2.4.4.6.5 | Clearing the draft Regulation indicated in subclause 2.4.4.6.4 with the concerned agencies | 01.04.2023 | 31.05.2023 | National Commission on Securities and Stock Market | Ministry of Finance of Ukraine | state budget | within the established budget allocations for the relevant year | The draft Regulation has been cleared with stakeholders. | 1) The National Commission on Securities and Stock Market, by letter dated February 28, 2023 No. 09/02/1965, sent a draft decision of the National Commission on Securities and Stock Market On Approval of the Regulation on the Form and Substance of the Structure of Ownership (hereinafter - the draft decision of the NCSSM) to the Ministry of Finance of Ukraine for approval. 2) On April 13, 2023, at the suggestion of the Ministry of Finance of Ukraine, a meeting was held with representatives of the National Commission on Securities and Stock Market, the Ministry of Finance of Ukraine, the Ministry of Digital Transformation of Ukraine and the National Bank of Ukraine to discuss issues related to the refinement of the draft decision of the NCSSM (letter of the Ministry of Finance of Ukraine dated April 03, 2023 No. 20/01-08/5755). Based on the results of the meeting, the Ministry of Finance of Ukraine decided to submit its proposals to the draft decision of the NCSSM. 3) The Ministry of Finance of Ukraine provided its comments on the draft decision of the NCSSM by letter dated May 18, 2023 No. 26110-04-10/13577. On June 5, 2023, a meeting was held in a telephone format with the participation of representatives of the National Commission on Securities and Stock Market and the Ministry of Finance of Ukraine to discuss the comments made by the Ministry of Finance of Ukraine on the draft decision of the NCSSM. 4) On June 08, 2023, the draft decision of the NCSSM, refined in accordance with the comments of the Ministry of Finance of Ukraine, was sent to the Ministry of Finance of Ukraine for approval. 5) By decision of the NCSSM dated June 27, 2023 No. 715, the revised draft decision of the NCSSM was approved, taking into account the comments and suggestions of the Ministry of Finance of Ukraine and proposals received from capital market participants. 6) The National Commission on Securities and Stock Market, by letter dated June 28, 2023 No. 09/6877, resubmitted the refined draft to the Ministry of Finance of Ukraine for approval. 7) The Ministry of Finance of Ukraine, by letter dated August 4, 2023 No. 26110-04-10/21392, again provided its comments on the draft decision of the NCSSM. 8) By the decision of the NCSSM dated August 21, 2023, No. 911, the refined in the second time draft decision of the NCSSM was approved, taking into account the comments and suggestions of the Ministry of Finance. 9) The NCSSMC sent the revised draft to the Ministry of Finance for approval by letter dated August 22, 2023 No. 09/02/8933. 10) On November 23, 2023, the Ministry of Finance (invitation letter No. 26110-04-10/31392 of November 15, 2023) held a harmonization meeting with the National Securities and Stock Market Commission in the form of a video conference. Based on the results of the meeting, the NCSSMC prepared the refined in the fourth time draft, which was sent to the Ministry of Finance for approval. 11) By the decision of the NCSSMC dated January 25, 2024 No. 104, the refined in the third time draft decision of the NCSSMC was approved, taking into account the comments and suggestions of the Ministry of Finance. 12) The NCSSM sent the refined draft for approval to the State Financial Monitoring Service, the Ministry of Digital Transformation and the Ministry of Finance, respectively, by letters No. 09/02/2460, No. 09/02/2477 and No. 09/02/2476 dated January 26, 2024. 13) The Draft Decision of the NCSSM On Approval of the Regulation on the Form and Substance of the Structure of Ownership was approved by the Ministry of Finance (letter dated February 1, 2024 No. 26110-04-10/3220), the State Financial Monitoring Service (letter dated February 15, 2024 No. 602/320-06-2) and the Ministry of Digital Transformation (letter dated February 20, 2024 No. 1/04-2-2611). | Implemented | 0.0
2.4 | Public and private sectors of the economy | 2.4.4 A high level of tolerance of corruption in the private sector of the economy | 2.4.4.6 | Effective mechanisms for verification of information on the ultimate beneficial owners of legal entities under private law in the Unified State Register of Legal Entities, Individual Entrepreneurs, and Public Associations have been introduced | 2.4.4.6.6 | Approving the Regulation indicated in subclause 2.4.4.6.4 | 01.05.2023 | 30.06.2023 | National Commission on Securities and Stock Market |  | state budget | within the established budget allocations for the relevant year | The Regulation has been approved. | Decision of the National Commission on Securities and Stock Market dated February 23, 2024 No. 224 On Approval of the Regulation on the Form and Substance of the Structure of Ownership registered with the Ministry of Justice of Ukraine on March 12, 2024 under No. 365/41710 (as amended by the decision of the National Commission on Securities and Stock Market dated March 15, 2024 No. 296 On Amendments to the Decision of the National Commission on Securities and Stock Market dated 23 February 2024 No. 224, registered with the Ministry of Justice of Ukraine on March 20, 2024 under No. 412/41757). | Implemented | 0.0
2.4 | Public and private sectors of the economy | 2.4.4 A high level of tolerance of corruption in the private sector of the economy | 2.4.4.6 | Effective mechanisms for verification of information on the ultimate beneficial owners of legal entities under private law in the Unified State Register of Legal Entities, Individual Entrepreneurs, and Public Associations have been introduced | 2.4.4.6.7 | Developing and submitting to the Cabinet of Ministers of Ukraine and the National Bank the draft Methodology for Determining the Ultimate Beneficial Owner by a Legal Entity | 01.03.2023 | 31.08.2023 | Ministry of Finance of Ukraine |  | state budget | within the established budget allocations for the relevant year | The Methodology has been approved by the Cabinet of Ministers of Ukraine. | The Ministry of Finance of Ukraine developed and submitted to the Cabinet of Ministers of Ukraine for review the Draft Resolution On Approval of the Methodology for Determining the Ultimate Beneficial Owner by a Legal Entity (letter of the Ministry of Finance dated September 14, 2023 No. 26120-02-3/25047). The Methodology for Determining the Ultimate Beneficial Owner by a Legal Entity was approved by the Resolution of the Cabinet of Ministers of Ukraine and the National Bank of Ukraine dated September 19, 2023 No. 1011. | Implemented | 0.0
2.4 | Public and private sectors of the economy | 2.4.4 A high level of tolerance of corruption in the private sector of the economy | 2.4.4.6 | Effective mechanisms for verification of information on the ultimate beneficial owners of legal entities under private law in the Unified State Register of Legal Entities, Individual Entrepreneurs, and Public Associations have been introduced | 2.4.4.6.8 | Developing and submitting to the Cabinet of Ministers of Ukraine the draft Procedure for automatic verification of the details of ultimate beneficial owners of legal entities using the tools of the Unified State Web Portal for Electronic Services with the use of details from the Unified State Demographic Register and the State Register of Individual Taxpayers | 01.03.2023 | 31.05.2023 | Ministry of Digital Transformation of Ukraine | Ministry of Finance of Ukraine, Ministry of Justice of Ukraine, State Tax Service of Ukraine, Ministry of Internal Affairs of Ukraine | state budget | within the established budget allocations for the relevant year | The procedure has been approved by the Cabinet of Ministers of Ukraine. | According to information provided by the Ministry of Digital Transformation of Ukraine: “The Cabinet of Ministers of Ukraine adopted Resolution No. 976 dated September 12, 2023, ‘On Certain Issues of Automatic Verification of Information through the Unified State Web Portal of Electronic Services Using Data from the Unified State Demographic Register and the State Register of Individual Taxpayers,’ which approved the Procedure for Automatic Verification of Information through the Unified State Web Portal of Electronic Services using data from the Unified State Demographic Register and the State Register of Individual Taxpayers.” At the same time, it is important to note that Article 6, part five of the Law of Ukraine “On State Registration of Legal Entities, Individual Entrepreneurs, and Public Organizations” provides for the automatic verification of information about the person who is the ultimate beneficial owner of a legal entity through the Unified State Web Portal of Electronic Services during registration actions regarding any legal entity and in case such a legal entity submits information about the person who is the ultimate beneficial owner of the legal entity in electronic form. In turn, the Resolution of the Cabinet of Ministers of Ukraine No. 976, dated September 12, 2023, stipulates that information about the ultimate beneficial owner of a legal entity is automatically verified through the Unified State Web Portal of Electronic Services during the state registration of the establishment of a limited liability company operating based on a model statute. Additionally, Resolution No. 976 of the Cabinet of Ministers of Ukraine dated September 12, 2023, establishes that such automatic verification during the state registration of the establishment of a legal entity (other than a limited liability company operating on the basis of a model statute) and the amendment of information about a legal entity contained in the Unified State Register of Legal Entities, Individual Entrepreneurs, and Public Organizations, will be conducted after ensuring the technical capability of implementing such state registration through the Unified State Web Portal of Electronic Services. Given this, in previous reporting periods, the National Agency considered the measure to have been partially implemented. However, on July 12, 2024, representatives of the National Agency on Corruption Prevention and the Ministry of Digital Transformation met to discuss the measure’s implementation. As a result of the discussion, Resolution No. 976 of the Cabinet of Ministers of Ukraine, dated September 12, 2023, ensures the legal regulation of automatic verification of information about the person who is the ultimate beneficial owner of a legal entity through the Unified State Web Portal of Electronic Services using data from the Unified State Demographic Register and the State Register of Individual Taxpayers. The Resolution will not require changes upon the expansion of the technical capability to register the formation of other legal entities, except for LLCs with a model statute. Therefore, the measure was implemented in full. At the same time, the State Anti-Corruption Program for 2023–2025 includes the following measure: 2.4.4.6.22. This measure involves ensuring the technical capability to conduct automatic verification of information about the ultimate beneficial owner using the Unified State Web Portal of Electronic Services, leveraging data from the Unified State Demographic Register and the State Register of Individuals – Taxpayers. This measure will be considered fully implemented only upon the introduction of the second stage of automating the legal entity registration process, which will enable the automatic registration of all types of legal entities. | Implemented | 0.0
2.4 | Public and private sectors of the economy | 2.4.4 A high level of tolerance of corruption in the private sector of the economy | 2.4.4.6 | Effective mechanisms for verification of information on the ultimate beneficial owners of legal entities under private law in the Unified State Register of Legal Entities, Individual Entrepreneurs, and Public Associations have been introduced | 2.4.4.6.9 | Developing the draft of the Procedure by which a legal entity must submit explanations and documents to prove information about ultimate beneficial owners and the structure of ownership, as well as the procedure for reviewing them | 01.03.2023 | 30.04.2023 | Ministry of Justice of Ukraine |  | state budget | within the established budget allocations for the relevant year | The draft Procedure has been developed | Міністерство юстиції України розробило проект наказу «Про затвердження Порядку надання юридичною особою пояснень та/або документів для підтвердження відомостей про кінцевого бенефіціарного власника та/або структуру власності юридичної особи, а також порядку їх розгляду». | Implemented | 0.0
2.4 | Public and private sectors of the economy | 2.4.4 A high level of tolerance of corruption in the private sector of the economy | 2.4.4.6 | Effective mechanisms for verification of information on the ultimate beneficial owners of legal entities under private law in the Unified State Register of Legal Entities, Individual Entrepreneurs, and Public Associations have been introduced | 2.4.4.6.11 | Clearing the draft procedure indicated in subclause 2.4.4.6.9 with the concerned agencies | 01.05.2023 | 30.06.2023 | Ministry of Justice of Ukraine | Ministry of Finance of Ukraine | state budget | within the established budget allocations for the relevant year | The draft procedure has been cleared with stakeholders. | The Ministry of Finance of Ukraine by letter dated June 12, 2023 No. 26110-04-5/15953 and the State Financial Monitoring Service of Ukraine by letter dated June 13, 2023 No. 2042/320-06-5 approved the draft order. | Implemented | 0.0
2.4 | Public and private sectors of the economy | 2.4.4 A high level of tolerance of corruption in the private sector of the economy | 2.4.4.6 | Effective mechanisms for verification of information on the ultimate beneficial owners of legal entities under private law in the Unified State Register of Legal Entities, Individual Entrepreneurs, and Public Associations have been introduced | 2.4.4.6.12 | Approving the revised draft procedure indicated in subclause 2.4.4.6.9 | 01.06.2023 | 31.07.2023 | Ministry of Justice of Ukraine |  | state budget | within the established budget allocations for the relevant year | The procedure has been approved. | The order of the Ministry of Justice of Ukraine dated June 14, 2023 No. 2211/5 On Approval of the Procedure for Providing Explanations and/or Documents by a Legal Entity to Prove Information about the Ultimate Beneficial Owner and/or Structure of Ownership of a Legal Entity, as well as the Procedure for Reviewing Them was adopted. The order was registered with the Ministry of Justice of Ukraine on June 14, 2023 under No. 990/40046. | Implemented | 0.0
2.4 | Public and private sectors of the economy | 2.4.4 A high level of tolerance of corruption in the private sector of the economy | 2.4.4.6 | Effective mechanisms for verification of information on the ultimate beneficial owners of legal entities under private law in the Unified State Register of Legal Entities, Individual Entrepreneurs, and Public Associations have been introduced | 2.4.4.6.13 | Developing the draft of the Procedure by which the holder of the Unified State Register of Legal Entities, Individual Entrepreneurs, and Public Associations shall be notified by reporting entities about any discovered discrepancies in information about ultimate beneficial owners and the structure of ownership of legal entities | 01.03.2023 | 31.05.2023 | Ministry of Justice of Ukraine |  | state budget | within the established budget allocations for the relevant year | The draft Procedure has been developed | Міністерством юстиції України розроблено проект наказу «Про затвердження Порядку повідомлення держателя Єдиного державного реєстру юридичних осіб, фізичних осіб – підприємців та громадських формувань про виявлення розбіжностей між отриманими суб’єктом первинного фінансового моніторингу в результаті здійснення належної перевірки та розміщеними в Єдиному державному реєстрі юридичних осіб, фізичних осіб - підприємців та громадських формувань відомостями про кінцевих бенефіціарних власників та/або структуру власності юридичної особи. | Implemented | 0.0
2.4 | Public and private sectors of the economy | 2.4.4 A high level of tolerance of corruption in the private sector of the economy | 2.4.4.6 | Effective mechanisms for verification of information on the ultimate beneficial owners of legal entities under private law in the Unified State Register of Legal Entities, Individual Entrepreneurs, and Public Associations have been introduced | 2.4.4.6.15 | Approving the revised draft procedure indicated in subclause 2.4.4.6.13 | 01.06.2023 | 31.07.2023 | Ministry of Justice of Ukraine |  | state budget | within the established budget allocations for the relevant year | The procedure has been approved. | The order of the Ministry of Justice of Ukraine dated July 12, 2023 No. 2542/5 On Approval of the Procedure for Notification of the Holder of the Unified State Register of Legal Entities, Individual Entrepreneurs, and Public Associations on the Discovery of Discrepancies in the Information Received by the Entity of Primary Financial Monitoring as a Result of the Due Diligence and Information about Ultimate Beneficial Owners and the Structure of Ownership of Legal Entities Published in the Unified State Register of Legal Entities, Individual Entrepreneurs, and Public Associations was adopted and registered with the Ministry of Justice of Ukraine on July 12, 2023 under No. 1185/40241. | Implemented | 0.0
2.4 | Public and private sectors of the economy | 2.4.4 A high level of tolerance of corruption in the private sector of the economy | 2.4.4.6 | Effective mechanisms for verification of information on the ultimate beneficial owners of legal entities under private law in the Unified State Register of Legal Entities, Individual Entrepreneurs, and Public Associations have been introduced | 2.4.4.6.16 | Developing the draft of the Procedure by which reporting entities shall relay information to the specially authorized agency about any discrepancies in information about ultimate beneficial owners and the structure of ownership of legal entities | 01.03.2023 | 30.04.2023 | Ministry of Justice of Ukraine | Ministry of Finance of Ukraine | state budget | within the established budget allocations for the relevant year | The draft Procedure has been developed. | The Ministry of Justice of Ukraine developed the draft of joint order of the Ministry of Justice of Ukraine and the Ministry of Finance of Ukraine On Approval of the Procedure for the Relaying by the Holder of the Unified State Register of Legal Entities, Individual Entrepreneurs, and Public Associations of Information on Discrepancies in Information about Ultimate Beneficial Owners and the Structure of Ownership of Legal Entities Received by the Entity of Primary Financial Monitoring as a Result of the Due Diligence of the Legal Entity and Corresponding Information Published in the Specified Register and about the Entity of Primary Financial Monitoring which Discovered such Discrepancies to the Specially Authorized Agency. | Implemented | 0.0
2.4 | Public and private sectors of the economy | 2.4.4 A high level of tolerance of corruption in the private sector of the economy | 2.4.4.6 | Effective mechanisms for verification of information on the ultimate beneficial owners of legal entities under private law in the Unified State Register of Legal Entities, Individual Entrepreneurs, and Public Associations have been introduced | 2.4.4.6.17 | Approving the draft Procedure indicated in subclause 2.4.4.6.16 | 01.05.2023 | 30.06.2023 | Ministry of Justice of Ukraine | Ministry of Finance of Ukraine | state budget | within the established budget allocations for the relevant year | The procedure has been approved. | The order of the Ministry of Justice of Ukraine and the Ministry of Finance of Ukraine dated July 10, 2023 No. 2513/5/378 On Approval of the Procedure for the Relaying by the Holder of the Unified State Register of Legal Entities, Individual Entrepreneurs, and Public Associations of Information on Discrepancies in Information about Ultimate Beneficial Owners and the Structure of Ownership of Legal Entities Received by the Entity of Primary Financial Monitoring as a Result of the Due Diligence of the Legal Entity and Corresponding Information Published in the Specified Register and about the Entity of Primary Financial Monitoring which Discovered such Discrepancies to the Specially Authorized Agency was adopted and registered with the Ministry of Justice of Ukraine on July 11, 2023 under No. 1168/40224. | Implemented | 0.0
2.4 | Public and private sectors of the economy | 2.4.4 A high level of tolerance of corruption in the private sector of the economy | 2.4.4.6 | Effective mechanisms for verification of information on the ultimate beneficial owners of legal entities under private law in the Unified State Register of Legal Entities, Individual Entrepreneurs, and Public Associations have been introduced | 2.4.4.6.18 | Developing the draft of the Procedure for holding legal entities liable and the procedure for determining the amount of fines for entering or submitting false information about the ultimate beneficial owner of the legal entity (or the absence thereof), failure to submit or late submission of said information | 01.03.2023 | 30.04.2023 | Ministry of Justice of Ukraine |  | state budget | within the established budget allocations for the relevant year | The draft Procedure has been developed. | According to the Ministry of Justice of Ukraine, the draft order On Approval of the Procedure for Holding Legal Entities Liable and the Procedure for Determining the Amount of Fines for Violations in the State Registration of Legal Entities Area has been developed. | Implemented | 0.0
2.4 | Public and private sectors of the economy | 2.4.4 A high level of tolerance of corruption in the private sector of the economy | 2.4.4.6 | Effective mechanisms for verification of information on the ultimate beneficial owners of legal entities under private law in the Unified State Register of Legal Entities, Individual Entrepreneurs, and Public Associations have been introduced | 2.4.4.6.20 | Approving the revised draft procedure indicated in subclause 2.4.4.6.18 | 01.05.2023 | 30.06.2023 | Ministry of Justice of Ukraine |  | state budget | within the established budget allocations for the relevant year | The procedure has been approved. | The order of the Ministry of Justice of Ukraine dated September 13, 2023 No. 3258/5 On Approval of the Procedure for Bringing to Justice and the Procedure for Determining the Amount of Fines for Violations in the State Registration of Legal Entities Area was adopted and registered with the Ministry of Justice of Ukraine on September 14, 2023 under No. 1614/40670. | Implemented | 0.0
2.4 | Public and private sectors of the economy | 2.4.4 A high level of tolerance of corruption in the private sector of the economy | 2.4.4.6 | Effective mechanisms for verification of information on the ultimate beneficial owners of legal entities under private law in the Unified State Register of Legal Entities, Individual Entrepreneurs, and Public Associations have been introduced | 2.4.4.6.21 | Providing the technical capability to make a notation in the Unified State Register of Legal Entities, Individual Entrepreneurs, and Public Associations about a potentially misleading nature of the information about the ultimate beneficial owner or the structure of ownership of the legal entity and about the National Bank having found the structure of ownership of the legal entity to be nontransparent (transparent) | 01.04.2023 | 30.06.2023 | Ministry of Justice of Ukraine |  | state budget | within the established budget allocations for the relevant year | The technical capability to make a notation in the Unified State Register of Legal Entities, Individual Entrepreneurs, and Public Associations about a potentially misleading nature of the information about the ultimate beneficial owner or the structure of ownership of the legal entity and about the National Bank having found the structure of ownership of the legal entity to be nontransparent (transparent) has been ensured. | On June 16, 2023, the State Enterprise "National Information Systems" updated the software of the Unified State Register of Legal Entities, Individual Entrepreneurs, and Public Associations, namely: - the new registration action "State Registration of Confirmation of the Authenticity of Information on the Ultimate Beneficial Owner and/or Structure of Ownership" was implemented (the purpose of this registration action is to make a note about the possible inauthenticity of the structure of ownership, that the structure of ownership is recognized by the National Bank of Ukraine as opaque, as well as a note about the possible inauthenticity of information on the ultimate beneficial owner); - a separate block of information on the structure of ownership was created; - the single versatile form for entering information about the ultimate beneficial owner with the possibility of entering several citizenships was created; - updated information is displayed in the forms for providing information from the Unified State Register. | Implemented | 0.0
2.4 | Public and private sectors of the economy | 2.4.4 A high level of tolerance of corruption in the private sector of the economy | 2.4.4.6 | Effective mechanisms for verification of information on the ultimate beneficial owners of legal entities under private law in the Unified State Register of Legal Entities, Individual Entrepreneurs, and Public Associations have been introduced | 2.4.4.6.22 | Ensuring the technical capability to perform automatic verification of the details of ultimate beneficial owners of legal entities using the tools of the Unified State Web Portal for Electronic Services with the use of details from the Unified State Demographic Register and the State Register of Individual Taxpayers | 01.04.2023 | 31.12.2025 | Ministry of Digital Transformation of Ukraine | State Tax Service of Ukraine, State Migration Service of Ukraine | state budget | within the established budget allocations for the relevant year | The technical capability to perform automatic verification of the details of ultimate beneficial owners of legal entities using the tools of the Unified State Web Portal for Electronic Services with the use of details from the Unified State Demographic Register and the State Register of Individual Taxpayers has been ensured. | За інформацією Міністерства цифрової трансформації: «Наразі засобами Порталу Дія реалізовано можливість державної реєстрації створення товариства з обмеженою відповідальністю, що діє на підставі модельного статуту товариства з обмеженою відповідальністю. Інших послуг з реєстрації бізнесу в яких може проводитися перевірка КБВ в електронній формі не існує та не передбачено законодавством України. Відомості перевіряються (верифікуються) шляхом електронної інформаційної взаємодії з державних електронних інформаційних ресурсів: - з Єдиного державного демографічного реєстру через єдину інформаційну систему МВС – відомості про прізвище, ім’я, по батькові (за наявності); дата народження; тип документа; серія (за наявності) та номер документа (документів), що посвідчує особу та підтверджує громадянство (підданство), зокрема, але не виключно, паспорта громадянина України для виїзду за кордон; унікальний номер запису в Єдиному державному демографічному реєстрі; місце проживання; - з Державного реєстру фізичних осіб – платників податків – відомості про реєстраційний номер облікової картки платника податків. Відтак, забезпечено технічну можливість для проведення автоматичної перевірки відомостей щодо кінцевого бенефіціарного власника засобами Порталу Дія для товариства з обмеженою відповідальністю, що діє на підставі модельного статуту. Інших послуг з реєстрації бізнесу засобами Порталу Дія, в яких може проводитися перевірка КБВ в електронній формі наразі не існує. У разі запровадження нових послуг у сфері бізнесу для надання засобами Порталу Дія, після забезпечення технічної можливості реалізації такої послуги буде внесено відповідні зміни до постанови Кабінету Міністрів України від 12 вересня 2023 р. № 976». Постанова КМУ від 12 вересня 2023 р. № 976 "Деякі питання автоматичної перевірки (верифікації) відомостей засобами Єдиного державного вебпорталу електронних послуг з використанням відомостей з Єдиного державного демографічного реєстру, Державного реєстру фізичних осіб - платників податків" передбачає 2 етапи впровадження такої перевірки: 1) запровадження автоматичної перевірки щодо ТОВ, які діють на основі модельного статуту та наразі реєструються у Дії; 2) передбачення технічної можливості реєстрації утворення інших видів юридичних осіб за допомогою Дії та здійснення автоматичної перевірки їхніх КБВ. Наразі впроваджено лише перший етап і автоматична перевірка здійснюється лише щодо ТОВ, які діють на підставі модельного статуту. З огляду на це, захід виконано частково. За інформацією Міністерства цифрової трансформації, що надана у IV кварталі 2024 року: «За результатами проведених нарад із Національним агентством з питань запобігання корупції пропонується змінити дату виконання заходу на грудень 2025 року». Постановою Кабінету Міністрів України від 25 червня 2025 р. № 758 «Про внесення змін у додаток 2 до Державної антикорупційної програми на 2023-2025 роки» було внесено зміни до Державної антикорупційної програми на 2023-2025 роки, затвердженої постановою Кабінету Міністрів України від 04.03.2023 № 220, які полягали у перенесенні строків виконання, зміні редакції найменування та індикатору виконання заходу 2.4.4.6.22. Змінами уточнено, що зазначений захід стосується перевірки відомостей про кінцевого бенефіціарного власника засобами Єдиного державного вебпорталу електронних послуг під час державної реєстрації утворення товариства з обмеженою відповідальністю, що діє на підставі модельного статуту. Відповідно станом на 30.06.2025 захід виконано повністю та вчасно. | Implemented | 0.0