## Заходи
№ Напрямку | Напрямок | Проблема | № ОСР | Назва ОСР | № Заходу | Назва заходу | Дата початку | Дата завершення | Головний виконавець | Співвиконавці | Джерела фінансування | Обсяги фінансування, тис.грн. | Показник (індикатор) виконання | Стан виконання | Статус виконання | Оцінка досягнення ОСР
2.4 | Public and private sectors of the economy | 2.4.4 A high level of tolerance of corruption in the private sector of the economy | 2.4.4.9 | Legislation establishes the obligation of internal auditors to report the facts of corruption and corruption-related offenses they have discovered | 2.4.4.9.1 | Drafting and submitting to the Cabinet of Ministers of Ukraine a draft law proposing to amend Article 61 of the Law and provide for the obligation of the employee of the legal entity conducting an internal audit to notify the specially authorized anticorruption entity as well as the officer responsible for preventing corruption in the operations of the legal entity, the manager of the legal entity, or the founders (shareholders) of the legal entity about any instances of corruption and corruption-related offenses, as well as instances where attempts were made to incite corruption in the operations of the legal entity | 01.03.2023 | 31.10.2023 | National Agency on Corruption Prevention |  | state budget | within the established budget allocations for the relevant year | The draft law has been submitted to the Parliament of Ukraine. | 30.06.2023 проект Закону України «Про внесення змін до деяких законодавчих актів України щодо вдосконалення механізмів запобігання корупції, зокрема у приватній сфері» (листом № 10-03/14224-23) внесено на розгляд до Кабінету Міністрів України. 14.07.2023 Кабінет Міністрів України схвалив зазначений законопроект. 17.07.2023 Верховна Рада України отримала відповідний законопроект (реєстр.№ 9505). Разом з тим, 06.02.2024 зазначений законопроект знято з розгляду. Отже, у зв'язку з недосягненням показника (індикатора) виконання, відповідний захід не може вважатись виконаним повністю. | Partially implemented | 0.0