## Заходи
№ Напрямку | Напрямок | Проблема | № ОСР | Назва ОСР | № Заходу | Назва заходу | Дата початку | Дата завершення | Головний виконавець | Співвиконавці | Джерела фінансування | Обсяги фінансування, тис.грн. | Показник (індикатор) виконання | Стан виконання | Статус виконання | Оцінка досягнення ОСР
2.5 | Construction, land relations, and infrastructure | 2.5.4 The procedure by which land plots are formed is overcomplicated and involves an excessive amount of discretion | 2.5.4.3 | Software used to form land plots has been put into operation, and it has been mandated that land management documentation and technical documentation for land appraisal shall be developed exclusively in electronic form (without the development of hardcopy documentation) | 2.5.4.3.1 | Conducting an independent technical audit of software, hardware, and process equipment of the State Land Cadaster, the effectiveness of storage and protection of information of the State Land Cadaster, particularly an evaluation of the degree to which the functionality of State Land Cadaster software conforms to the requirements of legislation | 01.03.2023 | 30.04.2023 | State Service of Ukraine for Geodesy, Cartography and Cadastre |  | state budget | is determined by a separate assessment | A report on the independent technical audit has been submitted to the Ministry of Agrarian Policy and the National Agency. | The technical audit (assessment) of the automated system of the State Land Cadastre (AS SLC) was performed in the period from June 2022 to February 2023 commissioned by the State Service of Ukraine for Geodesy, Cartography and Cadastre with the support of the Supporting Transparent Land Governance in Ukraine project, which is financed by the European Union and implemented by the World Bank. Based on the findings of the assessment, the technical audit report was prepared and sent to the National Agency on Corruption Prevention by letter of the State Service of Ukraine for Geodesy, Cartography and Cadastre dated April 28, 2023 No. 7-28-0.252-3817/2-23. The report was presented to the management of the Ministry of Agrarian Policy and Food of Ukraine on March 21, 2023 in its premises. | Implemented | 0.0