## Заходи
№ Напрямку | Напрямок | Проблема | № ОСР | Назва ОСР | № Заходу | Назва заходу | Дата початку | Дата завершення | Головний виконавець | Співвиконавці | Джерела фінансування | Обсяги фінансування, тис.грн. | Показник (індикатор) виконання | Стан виконання | Статус виконання | Оцінка досягнення ОСР
2.5 | Construction, land relations, and infrastructure | 2.5.10 Imperfection of existing control instruments and lack of transparency of road construction, repair, and maintenance processes | 2.5.10.3 | An open map of road construction, repair, and maintenance has been created, which displays the tenders held and contracts signed for such work in order to avoid overlapping operations at the same sites; this map has been integrated with the Unified State Electronic System in Construction | 2.5.10.3.1 | Developing and signing documentation for the implementation of the tool for digital management of the rebuilding (modernization) of Ukraine, which will ensure public access to an interactive map of projects, including those involving the rebuilding (modernization) of Ukraine, with information about competitive bidding processes completed, contracts signed, contractors and current progress of construction all over Ukraine, making it possible to monitor the progress of renovations and construction and avoid overlapping operations at the same sites | 01.03.2023 | 31.07.2023 | Ministry for Communities and Territories Development of Ukraine | State Agency for Restoration and Infrastructure Development of Ukraine | state budget and/or international technical assistance funds | within the established budget allocations for the relevant year and/or international technical assistance funds | The documentation has been signed. | In order to implement the measure provided for in subclause 2.5.10.3.1 of the State Anti-Corruption Programme for 2023-2025, the Ministry for Communities, Territories and Infrastructure Development of Ukraine informs that: "1) The Government adopted Resolution No. 1286 dated November 15 2022 On the Implementation of a Pilot Project for the Creation, Implementation and Maintenance of the Unified Digital Integrated Information and Analytical System for the Management of the Reconstruction of Real Estate, Construction and Infrastructure (hereinfater - the Resolution). Furthermore, it was amended by the Resolution of the Cabinet of Ministers of Ukraine dated May 2, 2023 No. 434. Link: https://zakon.rada.gov.ua/laws/show/1286-2022-%D0%BF#Text. 2) order of the Ministry for Communities, Territories and Infrastructure Development of Ukraine dated January 23, 2024 No. 65 On Approval of the Regulation on the Unified Digital Integrated Information and Analytical System for Management of the Reconstruction of Real Estate, Construction and Infrastructure, was issued and registered with the Ministry of Justice of Ukraine on February 08, 2024 under No. 198/41543. Link: https://zakon.rada.gov.ua/laws/show/z0198-24#Text2". It should be noted that the order of the Ministry for Communities, Territories and Infrastructure Development of Ukraine dated January 23, 2024 No. 65 On Approval of the Regulation on the Unified Digital Integrated Information and Analytical System for Management of the Reconstruction of Real Estate, Construction and Infrastructure regulates the organizational principles of operation of the Unified Digital Integrated Information and Analytical System for Management of the Reconstruction of Real Estate, Construction and Infrastructure. In particular, the main tasks of the Unified Digital System include: providing information on procurement procedures related to the restoration and/or reconstruction of facilities; keeping records of projects aimed at restoring and/or reconstructing facilities for which procurement procedures have been conducted and an agreement has been concluded between the customer and the contractor for services on the development of project documentation, new construction, reconstruction, restoration, etc.; ensuring monitoring of the expiration date of the contract for the restoration and/or reconstruction of facilities; creation of analytical dashboards on the work progress, duration of work (in accordance with the planned and actual terms) regarding the restoration and/or reconstruction of facilities, etc. Thus, we can state that the regulatory framework for the implementation of the tool for digital management of the rebuilding (modernization) of Ukraine, which will ensure public access to an interactive map of projects, including those involving the rebuilding (modernization) of Ukraine, with information about competitive bidding processes completed, contracts signed, contractors and current progress of construction all over Ukraine, making it possible to monitor the progress of renovations and construction and avoid overlapping operations at the same sites, has been developed. In addition, the Unified Digital System is currently operating in a test mode, with the following functionalities available: 1. Public portal - https://dream.gov.ua/ 2. User functionality - https://my.dream.gov.ua/ 3. Analytics module - https://bi.dream.gov.ua/ 4. Chatbot for community support - https://t.me/DREAM_GOV_UA_bot Thus, given that the documentation for the implementation of the tool for digital management of the rebuilding (modernization) of Ukraine has been developed and signed, we can state that the measure provided for in subclause 2.5.10.3.1 has been fully implemented, but not in time. | Implemented | 0.0
2.5 | Construction, land relations, and infrastructure | 2.5.10 Imperfection of existing control instruments and lack of transparency of road construction, repair, and maintenance processes | 2.5.10.3 | An open map of road construction, repair, and maintenance has been created, which displays the tenders held and contracts signed for such work in order to avoid overlapping operations at the same sites; this map has been integrated with the Unified State Electronic System in Construction | 2.5.10.3.2 | Conducting pilot operation of the digital management tool indicated in subclause 2.5.10.3.1, adjusting it (if needed), and putting it into commercial operation. | 01.08.2023 | 31.12.2025 | Ministry for Communities and Territories Development of Ukraine | State Agency for Restoration and Infrastructure Development of Ukraine | state budget and/or international technical assistance funds | within the established budget allocations for the relevant year and/or international technical assistance funds | The tool for digital management of the rebuilding (modernization) of Ukraine has been put into commercial operations. | 1. На виконання заходу передбаченого п. 2.5.10.3.2 Державної антикорупційної програми на 2023-2025 роки, Міністерством розвитку громад та територій України повідомлено, що: 1) наказом Мінрозвитку від 20 серпня 2025 року № 1289 програмне забезпечення Єдиної цифрової інтегрованої інформаційно-аналітичної системи управління процесом реконструкції нерухомості, будівництва та інфраструктури» (далі – екосистема DREAM) введено в дослідну експлуатацію; 2) наразі екосистема DREAM функціонує у належному стані; 3) разом з тим зазначаємо, що в Україні триває реформа управління публічними фінансами; 4) відповідно до підпункту 3 пункту 2 постанови Кабінету Міністрів України від 26 серпня 2025 р. № 1049 “Про внесення змін до постанови Кабінету Міністрів України від 28 лютого 2025 р. N 527” до набрання чинності нормативно-правовим актом Кабінету Міністрів України, який визначатиме порядок функціонування та складові Єдиної інформаційної системи управління публічними інвестиційними проєктами (ЄІС), підготовка, оцінка публічних інвестиційних проєктів, формування Єдиного проектного портфелю держави, галузевих (секторальних) портфелів, а також внесення і оновлення інформації здійснюються з використанням екосистеми DREAM; 5) модернізація екосистеми DREAM як засобу інформатизації та впровадження нових функціональних можливостей здійснюється відповідно до вимог, передбачених постановою КМУ від 21 лютого 2025 р. № 205 Деякі питання створення, адміністрування та забезпечення функціонування засобу інформатизації», та є поетапним процесом, що потребує значних витрат ресурсів та часу; 6) таким чином, введення екосистеми DREAM в промислову експлуатацію доцільно розглядати після завершення процесу її модернізації відповідно до реформи управління публічними фінансами; 7) станом на сьогодні в екосистемі DREAM реалізовано функціонал щодо формування Середньострокового плану пріоритетних публічних інвестицій держави (регіону, територіальної громади), підготовки та оцінки публічних інвестиційних проектів і програм на державному, регіональному та місцевому рівнях, формування Єдиного проектного портфеля публічних інвестицій регіону та територіальної громади, тощо. 2. Відповідно до Додатку 2 Програми показником виконання цього заходу є «інструмент цифрового управління відбудовою (модернізацією) України введено в промислову експлуатацію». 3. Відповідно до Додатку 2 Програми строк виконання цього заходу визначений як 01.08.2023 (дата початку виконання) – 31.12.2025 (дата завершення виконання). 4. З огляду на інформацію, що міститься у пп. 1 – 3, за результатами моніторингу за IІ квартал 2026 року заходу 2.5.10.3.2 Програми присвоєно статус «не виконано». | Not implemented | 0.0
2.5 | Construction, land relations, and infrastructure | 2.5.10 Imperfection of existing control instruments and lack of transparency of road construction, repair, and maintenance processes | 2.5.10.3 | An open map of road construction, repair, and maintenance has been created, which displays the tenders held and contracts signed for such work in order to avoid overlapping operations at the same sites; this map has been integrated with the Unified State Electronic System in Construction | 2.5.10.3.3 | Ensuring constant operation (with public access) and updating of the interactive map of projects, particularly projects to rebuild (modernize) Ukraine, with information about competitive bidding processes completed, contracts signed, contractors and current progress of construction all over Ukraine, making it possible to monitor the progress of repairs and construction | 01.09.2024 | 31.12.2025 | Ministry for Communities and Territories Development of Ukraine |  | state budget | within the established budget allocations for the relevant year | Public access to the interactive map of projects, particularly projects to rebuild Ukraine, has been granted. | На виконання заходу передбаченого п. 2.5.10.3.3. Державної антикорупційної програми на 2023-2025 роки, Міністерством розвитку громад та територій України повідомлено, що: 1) здійснюється постійне функціонування (надання можливості публічного доступу) та оновлення інтерактивної карти робіт; 2) Єдиною цифровою інтегрованою інформаційно-аналітичною системою управління процесом відбудови об'єктів нерухомого майна, будівництва та інфраструктури забезпечується основна функції щодо реалізації реформи управління публічними інвестиціями; 3) фактично система виконує функції інструменту, через який забезпечуються збір, структуризація, публікація та відображення інформації щодо проектів, критеріїв їх пріоритизації, джерел фінансування, закупівель, виконання та моніторингу; 4) наразі серед цифрових інструментів реформи УПІ лише система DREAM забезпечує: - відображення проектів та програм у структурованому вигляді; - простежуваність руху проекту від етапу ініціювання до реалізації; - відображення його належності до відповідних портфелів; - зв’язок із даними про фінансування; - зв’язок із закупівлями через інтеграцію з електронною системою закупівель Prozorro; - відстеження етапів реалізації; - публічність інформації, достатньої для здійснення громадського контролю та моніторингу. 2. Відповідно до Додатку 2 Програми показником виконання цього заходу є «публічний доступ до інтерактивної карти робіт, зокрема робіт з відновлення України, забезпечено». 3. Відповідно до Додатку 2 Програми строк виконання цього заходу визначений як 01.09.2024 (дата початку виконання) – 31.12.2025 (дата завершення виконання). 4. З огляду на інформацію, що міститься у пп. 1 – 3, за результатами моніторингу за I квартал 2026 року заходу 2.5.10.3.3 Програми присвоєно статус «виконано вчасно і повністю». | Implemented | 0.0
2.5 | Construction, land relations, and infrastructure | 2.5.10 Imperfection of existing control instruments and lack of transparency of road construction, repair, and maintenance processes | 2.5.10.3 | An open map of road construction, repair, and maintenance has been created, which displays the tenders held and contracts signed for such work in order to avoid overlapping operations at the same sites; this map has been integrated with the Unified State Electronic System in Construction | 2.5.10.3.4 | Developing technical documentation for integration of the interactive map of projects, including projects to rebuild (modernize) Ukraine, with the Unified State Electronic System in Construction | 01.07.2024 | 30.09.2024 | Ministry for Communities and Territories Development of Ukraine | Ministry of Digital Transformation of Ukraine, State Agency for Restoration and Infrastructure Development of Ukraine | state budget and/or international technical assistance funds | within the established budget allocations for the relevant year and/or international technical assistance funds | The technical documentation has been developed. | 1.На виконання заходу передбаченого п. 2.5.10.3.4. Державної антикорупційної програми на 2023-2025 роки, Міністерством розвитку громад та територій України повідомлено, що: "Відповідно до Протоколу електронної інформаційної взаємодії між Єдиною цифровою інтегрованою інформаційно- аналітичною системою управління процесом відбудови об’єктів нерухомого майна, будівництва та інфраструктури та Єдиною державною електронною системою у сфері будівництва від 23.05.2025, сторонами якого є Мінрозвитку, ДП «Дія» та Державне агентство відновлення та розвитку інфраструктури України, реалізовано інформаційну взаємодію по документах обʼєкта будівництва". 2. Показником виконання даного заходу є "технічну документацію розроблено". 3. З огляду на це, констатуємо, що захід є виконаним. | Implemented | 0.0
2.5 | Construction, land relations, and infrastructure | 2.5.10 Imperfection of existing control instruments and lack of transparency of road construction, repair, and maintenance processes | 2.5.10.3 | An open map of road construction, repair, and maintenance has been created, which displays the tenders held and contracts signed for such work in order to avoid overlapping operations at the same sites; this map has been integrated with the Unified State Electronic System in Construction | 2.5.10.3.5 | Conducting pilot operation and performing the commercial launch of the interactive map of projects, including projects to rebuild (modernize) Ukraine, integrated with the Unified State Electronic System in Construction | 01.10.2024 | 31.03.2025 | State Agency for Restoration and Infrastructure Development of Ukraine | Ministry of Digital Transformation of Ukraine, Ministry for Communities and Territories Development of Ukraine | state budget and/or international technical assistance funds | within the established budget allocations for the relevant year and/or international technical assistance funds | The interactive map of projects, including projects to rebuild (modernize) Ukraine, has been integrated with the Unified State Electronic System in Construction. | 1. На виконання заходу передбаченого п. 2.5.10.3.5. Державної антикорупційної програми на 2023-2025 роки, Державним агентством відновлення та розвитку інфраструктури України повідомлено, що: "Інтерактивна карта функціонує за посиланням - https://map.dream.gov.ua/ у рамках реалізації Єдиної цифрової інтегрованої інформаційно-аналітичної системи управління процесом відбудови об’єктів нерухомого майна, будівництва та інфраструктури (DREAM). Між ЄДЕССБ та DREAM реалізовано інтеграцію у частині відомостей про проектну документацію, відомостей про атестованих осіб і техніко-економічним показників об’єкта будівництва (відновлення) відповідно до Протоколу електронної інформаційної взаємодії між Єдиною цифровою інтегрованою інформаційно- аналітичною системою управління процесом відбудови об’єктів нерухомого майна, будівництва та інфраструктури та Єдиною державною електронною системою у сфері будівництва від 23.05.2025." 2. Таким чином, констатуємо, що на разі забезпечується функціонування інтерактивної карти робіт, у тому числі робіт з відновлення (модернізації) України, функціонал якої постійно удосконалюється та оновлюється. Водночас інтеграція між ЄДЕССБ та DREAM забезпечена лише частково, зокрема у розрізі відомостей про проектну документацію, відомостей про атестованих осіб і техніко-економічним показникам об’єкта будівництва (відновлення). Крім того, з огляду на звітну інформацію з виконання заходу передбаченого п. 2.5.10.3.4. Державної антикорупційної програми на 2023-2025, можемо констатувати, що робота спрямована на забезпечення повної інтеграції між ЄДЕССБ та DREAM триває, а на разі відбувається пошук фінансування на удосконалення технічних складових вказаних систем. | Partially implemented | 0.0