## Заходи
№ Напрямку | Напрямок | Проблема | № ОСР | Назва ОСР | № Заходу | Назва заходу | Дата початку | Дата завершення | Головний виконавець | Співвиконавці | Джерела фінансування | Обсяги фінансування, тис.грн. | Показник (індикатор) виконання | Стан виконання | Статус виконання | Оцінка досягнення ОСР
2.6 | Defense sector | 2.6.2 Procurement of goods, work, and services for defense purposes is carried out under conditions of excessive secrecy and has a low level of competition, which contributes to abuse and unjustified spending of budget funds. | 2.6.2.4 | The Electronic Register of Competitive Selection Bidders and Contractors Performing Government Contracts (Agreements) has been formed in a transparent manner, and transparent notification of potential suppliers about plans to purchase goods, work, or services for defense purposes has been ensured | 2.6.2.4.1 | Drafting and submitting to the Cabinet of Ministers of Ukraine a draft resolution of the Cabinet of Ministers of Ukraine proposing amendments to the Procedure for Creating, Operating, and Maintaining the Electronic Register of Competitive Selection Bidders and Contractors Performing Government Contracts (Agreement), and Adding Business Entities to this Register, approved by the resolution of the Cabinet of Ministers of Ukraine dated March 17, 2021, No. 233, which provides for: 1) ensuring that the register of competitive selection bidders and contractors performing government contracts (and not the register administrator) performs systematization and retrospective analysis of data on business entities in defense procurement processes in accordance with classification attributes defined in Part 2 of Article 37 of the Law of Ukraine On Defense Procurement; 2) automatic population of the register with data; 3) ensuring the online publication of register information that does not contain secrets of the state. | 01.01.2025 | 31.05.2025 | Ministry of Defenсe of Ukraine | Ministry of Economy, Environment and Agriculture of Ukraine, Joint Stock Company «Ukrainian Defense Industry» | state budget | within the established budget allocations for the relevant year | The resolution of the Cabinet of Ministers of Ukraine has been adopted. | Моніторинг заходу 2.6.2.4.1 Програми за IV квартал 2025 року. 1. Відповідно до інформації, що надана головним виконавцем: "Прийнято Постанову Кабінету Міністрів України від 17 грудня 2025 р. № 1683 "Про внесення змін до Порядку створення, функціонування та ведення електронного реєстру учасників відбору та виконавців державних контрактів (договорів), внесення до нього суб’єктів господарювання”. 2. З огляду на вищевказане, за результатами моніторингу за IV квартал 2025 року заходу 2.6.2.4.1 Програми присвоєно статус «виконано». | Implemented | 0.0
2.6 | Defense sector | 2.6.2 Procurement of goods, work, and services for defense purposes is carried out under conditions of excessive secrecy and has a low level of competition, which contributes to abuse and unjustified spending of budget funds. | 2.6.2.4 | The Electronic Register of Competitive Selection Bidders and Contractors Performing Government Contracts (Agreements) has been formed in a transparent manner, and transparent notification of potential suppliers about plans to purchase goods, work, or services for defense purposes has been ensured | 2.6.2.4.2 | Putting into operation the Electronic Register of Competitive Selection Bidders and Contractors Performing Government Contracts (Agreements), which will perform the functions indicated in subclause 2.6.2.4.1 and, among other things, contains systematized data on business entities based on classification attributes, and is populated with data automatically | 01.01.2025 | 31.12.2025 | Ministry of Defenсe of Ukraine | Ministry of Economy, Environment and Agriculture of Ukraine | state budget | within the established budget allocations for the relevant year | The Electronic Register of Competitive Selection Bidders and Contractors Performing Government Contracts (Agreements) has been put into operation. | 1. На виконання заходу, передбаченого п. 2.6.2.4.2 Державної антикорупційної програми на 2023-2025 роки, Міністерством оборони України повідомлено, що відповідно до Наказу начальника Головного управління інформаційних технологій від 26.05.2026 №41 введено в дослідну експлуатацію Електронний реєстр учасників відбору та виконавців державних контрактів (договорів) (ІКС "Реєстр зброярів") з використанням реальних даних. 2. Відповідно до Додатку 2 Програми показником виконання цього заходу є «електронний реєстр учасників відбору та виконавців державних контрактів (договорів) введено в експлуатацію». 3. Відповідно до Додатку 2 Програми строк виконання цього заходу визначений як 01.01.2025 (дата початку виконання) – 31.12.2025 (дата завершення виконання). 4. З огляду на інформацію, що міститься у пп. 1 – 3, за результатами моніторингу за IІ квартал 2026 року заходу 2.6.2.4.2 Програми присвоєно статус виконано невчасно та повністю». | Implemented | 0.0