## Заходи
№ Напрямку | Напрямок | Проблема | № ОСР | Назва ОСР | № Заходу | Назва заходу | Дата початку | Дата завершення | Головний виконавець | Співвиконавці | Джерела фінансування | Обсяги фінансування, тис.грн. | Показник (індикатор) виконання | Стан виконання | Статус виконання | Оцінка досягнення ОСР
2.7 | Healthcare, education, science, and social security | 2.7.1 Patients and doctors do not receive medications and medical devices in a timely manner and in full, in particular due to the incomplete transition to the new system of organization and control of medical procurement, and the incomplete regulation of the processes of identifying the needs for and accounting of medications | 2.7.1.1 | Procurement of medications and medical devices at the expense of the state and local budgets is carried out on a professional basis by centralized procurement organizations under transparent and detailed procedures in accordance with objective needs based on the quality and evidence of effectiveness of such products and devices. If necessary, specialized international organizations are also involved in centralized procurement | 2.7.1.1.1 | Development and submission to Cabinet of Ministers of Ukraine a draft regulation of Cabinet of Ministers of Ukraine ‘On implementation and operation of medical supplies and products electronic management system’ to ensure the following: 1) planning of procurement needs, including monitoring the delivery of goods in all stages; 2) performance of distribution and re-distribution of goods; 3) accounting and inventory of goods with indication of parameters; 4) goods monitoring (automation of operational reporting on goods availability in storages), inventory management with consideration of due distribution practice; 5) development of reporting documentation on goods availability and turnover in the storages and medical facilities, Pes with licenses to perform medical economic activities; 6) managing the goods stock with consideration of requirements, established by laws; 7) performance of electronic documentation turnover on goods accounting and distribution; 8) electronic accounting of targeted disposal of goods; 9) automated publication of the system data in the open data format. | 01.01.2024 | 31.08.2024 | Ministry of Health of Ukraine |  | state budget | within the established budget allocations for the relevant year | The resolution of the Cabinet of Ministers of Ukraine has been adopted. | На виконання заходу передбаченого п. 2.7.1.1.1. Державної антикорупційної програми на 2023-2025 роки, Міністерством охорони здоров'я України повідомлено, що: "на підставі успішної реалізації експериментального проекту з впровадження та функціонування електронної системи управління запасами лікарських засобів та медичних виробів “e-Stock” було прийнято постанову Кабінету Міністрів України від 07.03.2025 № 262 "Про затвердження Порядку функціонування електронної системи управління запасами лікарських засобів та медичних виробів “е-Stock”". З аналізу змісту вказаної постанови ідентифіковано, що останній корелюється із вимогами Державної антикорупційної програми на 2023-2025 роки. Разом із тим, з огляду на порушення строків виконання вказаного заходу, можемо констатувати, що останній виконаний повністю та невчасно. | Implemented | 0.0
2.7 | Healthcare, education, science, and social security | 2.7.1 Patients and doctors do not receive medications and medical devices in a timely manner and in full, in particular due to the incomplete transition to the new system of organization and control of medical procurement, and the incomplete regulation of the processes of identifying the needs for and accounting of medications | 2.7.1.1 | Procurement of medications and medical devices at the expense of the state and local budgets is carried out on a professional basis by centralized procurement organizations under transparent and detailed procedures in accordance with objective needs based on the quality and evidence of effectiveness of such products and devices. If necessary, specialized international organizations are also involved in centralized procurement | 2.7.1.1.2 | Development and approval of a technical task for functions of medical supplies and products electronic management system to ensure the following: 1) planning of needs, procurement and monitoring the delivery of goods in all stages; 2) performance of distribution and re-distribution of goods; 3) accounting and inventory of goods with indication of parameters; 4) goods monitoring (automation of operational reporting on goods availability in storages), inventory management with consideration of due distribution practice; 5) development of reporting documentation on goods availability and turnover in the storages and medical facilities, Pes with licenses to perform medical economic activities; 6) managing the goods stock with consideration of requirements, established by laws; 7) performance of electronic documentation turnover on goods accounting and distribution; 8) electronic accounting of targeted disposal of goods; 9) automated publication of the system data in the open data format. | 13.03.2025 | 13.06.2025 | Ministry of Health of Ukraine |  | state budget and/or international technical assistance funds | within the established budget allocations for the relevant year or amount of international technical assistance | The statement of work has been approved. | На виконання заходу передбаченого п. 2.7.1.1.2 Державної антикорупційної програми на 2023-2025 роки, Міністерством охорони здоров'я повідомлено, про розробку технічного завдання для функціоналу електронної системи обліку та управління запасами лікарських засобів і медичних виробів. Таким чином, можемо констатувати, що вказаний захід є виконаним вчасно та повністю. | Implemented | 0.0
2.7 | Healthcare, education, science, and social security | 2.7.1 Patients and doctors do not receive medications and medical devices in a timely manner and in full, in particular due to the incomplete transition to the new system of organization and control of medical procurement, and the incomplete regulation of the processes of identifying the needs for and accounting of medications | 2.7.1.1 | Procurement of medications and medical devices at the expense of the state and local budgets is carried out on a professional basis by centralized procurement organizations under transparent and detailed procedures in accordance with objective needs based on the quality and evidence of effectiveness of such products and devices. If necessary, specialized international organizations are also involved in centralized procurement | 2.7.1.1.3 | Designing software for expanding the functionality of the electronic system for registering and managing stocks of medications and medical devices in accordance with subclauses 2.7.1.1.2, 2.7.1.2.2 | 13.07.2025 | 31.12.2025 | Ministry of Health of Ukraine | Ministry of Digital Transformation of Ukraine, State Enterprise "Medical Procurement of Ukraine" | state budget and/or international technical assistance funds | within the established budget allocations for the relevant year and/or international technical assistance funds | The software design has been developed. | На виконання заходу передбаченого п. 2.7.1.1.3. Державної антикорупційної програми на 2023-2025 роки, Міністерством охорони здоров'я повідомлено, що: " 1. Потреба - Модуль розроблений та введений в експлуатацію. Функціонал включає збір, агрегування і затвердження потреб, зокрема: відкриття збору потреби по напрямках за різними методологіями згідно з переліком номенклатури; формування заявки ЗОЗ; узгодження заявок ДОЗ; формування зведеної потреби МОЗ. https://www.prostir.ua/?grants=stvorennya-avtomatyzovanoji-informatsijnoji-systemy-e-stock 2. Закупівля - Модуль розроблений та запущено пілот. Функціонал включає консолідацію закупівель відповідно до напрямів та відстеження закупівель за рахунок інтеграції з SAP Ariba та Prozorro, функціонал включатиме: операції з приймання лікарських засобів, медичних виробів та допоміжних засобів; операції з списання лікарських засобів, медичних виробів та допоміжних засобів на пацієнта та відділення та повернення медичних товарів; операції з переміщення товарів в межах закладу та передача між закладами (перерозподіл); операції з переміщення товарів в карантин, зняття з карантину, утилізація товарів; операції по інвентаризації товару. https://www.prostir.ua/?grants=tender-na-rozrobku-natsionalnoji-avtomatyzovanoji-informatsijnoji-systemy-e-stock-etap-2-modul-zakupivel 3. Облік - Розроблено. https://www.prostir.ua/?grants=tender-na-rozrobku-modulyu-e-stock-oblik 4. Логістика - Розроблено. https://www.prostir.ua/?grants=tender-na-rozrobku-modulyu-e-stock-lohistyka". З доданих виконавцем заходу скріншотів можливо констатувати, що відповідне програмне забезпечення функціоналу електронної системи обліку та управління запасами лікарських засобів та медичних виробів є розробленим. Відтак, наявне програмне забезпечення, що матиме можливість: 1) проводити збір потреб у лікарських виробах та медичних засобах від лікарень по всіх Україні; 2) агрегувати інформацію про проведенні закупівлі; 3) здійснювати моніторинг постачання медичних товарів і керування їх розподілом між лікарнями; 4) проводити облік наявних лікарських засобів та медичних виробів, їх рух та перерозподіл. З огляду на зазначене, захід передбачений п. 2.7.1.1.3 є виконаним вчасно та повністю. | Implemented | 0.0
2.7 | Healthcare, education, science, and social security | 2.7.1 Patients and doctors do not receive medications and medical devices in a timely manner and in full, in particular due to the incomplete transition to the new system of organization and control of medical procurement, and the incomplete regulation of the processes of identifying the needs for and accounting of medications | 2.7.1.1 | Procurement of medications and medical devices at the expense of the state and local budgets is carried out on a professional basis by centralized procurement organizations under transparent and detailed procedures in accordance with objective needs based on the quality and evidence of effectiveness of such products and devices. If necessary, specialized international organizations are also involved in centralized procurement | 2.7.1.1.4 | Implementing the functionality of the electronic system for registering and managing stocks of medications and medical devices in accordance with subclauses 2.7.1.1.2, 2.7.1.2.2 | 13.08.2026 | 31.12.2025 | Ministry of Health of Ukraine | Ministry of Digital Transformation of Ukraine, State Enterprise "Medical Procurement of Ukraine" | state budget and/or international technical assistance funds | within the established budget allocations for the relevant year or the amount of international technical assistance | The unified web portal is operating on an ongoing basis. | На виконання заходу передбаченого п. 2.7.1.1.4 Державної антикорупційної програми на 20234-2025 роки, Міністерством охорони здоров'я України, повідомлено, що: "наказом МОЗ від 31.12.2025 № 1994 було введено в дослідну експлуатацію модулі «Визначення потреби за номенклатурою», «Управління організаціями та користувачами», «Закупівлі», «Логістика», «Облік» Електронної системи управління запасами лікарських засобів та медичних виробів «e-Stock». Посилання на наказ: https://moz.gov.ua/uk/decrees/nakaz-moz-ukrayini-vid-31-12-2025-1994-pro-vvedennya-v-doslidnu-ekspluataciyu-elektronnoyi-sistemi-upravlinnya-zapasami-likarskih-zasobiv-ta-medichnih-virobiv-e-stock". Відповідно до вказаного наказу в дослідну експлуатацію введено Електронну систему управління запасами лікарських засобів та медичних виробів «e-Stock», зокрема модулі «Визначення потреби за номенклатурою», «Управління організаціями та користувачами», «Закупівлі», «Логістика», «Облік». З огляду на підтверджуючу інформацію, що надана від МОЗ, зокрема скріншоти, що відображають функціонування вказаних модулів, а також прийняте нормативно-правове регулювання вказаний захід може вважатися виконаним вчасно та повністю. | Implemented | 0.0
2.7 | Healthcare, education, science, and social security | 2.7.1 Patients and doctors do not receive medications and medical devices in a timely manner and in full, in particular due to the incomplete transition to the new system of organization and control of medical procurement, and the incomplete regulation of the processes of identifying the needs for and accounting of medications | 2.7.1.1 | Procurement of medications and medical devices at the expense of the state and local budgets is carried out on a professional basis by centralized procurement organizations under transparent and detailed procedures in accordance with objective needs based on the quality and evidence of effectiveness of such products and devices. If necessary, specialized international organizations are also involved in centralized procurement | 2.7.1.1.5 | Drafting and submitting to the Cabinet of Ministers of Ukraine a draft resolution of the Cabinet of Ministers of Ukraine, according to which local healthcare buyers (healthcare institutions, organizational units in charge of healthcare at regional state administrations and the Kyiv City State Administration) shall conduct procurement of the specified list of medications and medical devices with the use of an e-catalog | 01.03.2023 | 31.10.2023 | Ministry of Health of Ukraine | Ministry of Economy, Environment and Agriculture of Ukraine, State Enterprise "Medical Procurement of Ukraine" | state budget | within the established budget allocations for the relevant year or the amount of international technical assistance | The resolution of the Cabinet of Ministers of Ukraine has been adopted. | In order to implement the measure provided for in subclause 2.7.1.1.5 of the State Anti-Corruption Program for 2023-2025, the Ministry of Health of Ukraine has developed the Draft Resolution of the Cabinet of Ministers of Ukraine On Amendments to the Specifics of Public Procurement of Goods and Services for Customers Provided for by the Law of Ukraine On Public Procurement while Martial Law is in Effect in Ukraine and within 90 Days from the Day of Its Termination or Cancellation. On July 7, 2023, the Cabinet of Ministers of Ukraine adopted Resolution No. 686 On Amendments to the Specifics of Public Procurement of Goods and Services for Customers Provided for by the Law of Ukraine On Public Procurement while Martial Law is in Effect in Ukraine and within 90 Days from the Day of Its Termination or Cancellation. | Implemented | 0.0