## Заходи
№ Напрямку | Напрямок | Проблема | № ОСР | Назва ОСР | № Заходу | Назва заходу | Дата початку | Дата завершення | Головний виконавець | Співвиконавці | Джерела фінансування | Обсяги фінансування, тис.грн. | Показник (індикатор) виконання | Стан виконання | Статус виконання | Оцінка досягнення ОСР
1.1 | Shaping and implementing the state anticorruption policy | 1.1.3 Provisions of normative legal acts and their drafts need to be further improved in order to eliminate potential factors that foster corruption | 1.1.3.2 | The mandatory anticorruption expert examination of drafts and existing normative legal acts is carried out systemically by entities authorized to do so; the results of anticorruption (particularly public) expert examination are subject to publication and mandatory review | 1.1.3.2.1 | Drafting and submitting to the Cabinet of Ministers of Ukraine a draft law that: 1) stipulates that the results of anticorruption (particularly public) expert examination must be publicized and examined; 2) obligates the National Agency to carry out anticorruption expert examination of all acts submitted to the Cabinet of Ministers of Ukraine for review; 3) obligates the National Agency to carry out an anticorruption expert examination of the normative legal acts currently in effect. | 01.03.2023 | 30.11.2023 | National Agency on Corruption Prevention |  | state budget | within the established budget allocations for the relevant year | The draft law has been submitted to the Parliament of Ukraine. | 24.06.2023 Кабінет Міністрів України схвалив проект Закону України "Про внесення змін до Закону України «Про запобігання корупції» щодо удосконалення деяких антикорупційних механізмів" з необхідністю його доопрацювання. 27.06.2023 Національне агентство направило доопрацьований вищезазначений проект Закону України (лист № 10-03/13874-23) до Кабінету Міністрів України. Проект Закону України зареєстровано у Верховній Раді України 04.07.2023 (Реєстр. № 9457). 13.02.2024 надано висновок комітету ВРУ з питань антикорупційної політики про розгляд зазначеного законопроекту. 17.07.2025 законопроект реєстр. № 9457 від 04.07.2023 знято з розгляду (відкликано відповідно до ч. 3 ст. 105 Закону України "Про Регламент Верховної Ради України" у зв'язку з припиненням повноважень Кабінету Міністрів України). Тому у зв'язку з недосягненням показника (індикатора) виконання, відповідний захід не може вважатись виконаним повністю. | Partially implemented | 0.0
1.1 | Shaping and implementing the state anticorruption policy | 1.1.3 Provisions of normative legal acts and their drafts need to be further improved in order to eliminate potential factors that foster corruption | 1.1.3.2 | The mandatory anticorruption expert examination of drafts and existing normative legal acts is carried out systemically by entities authorized to do so; the results of anticorruption (particularly public) expert examination are subject to publication and mandatory review | 1.1.3.2.2 | Analyzing the practice of exercise by the National Agency in 2022-2024 of the powers to carry out anticorruption expert examinations of draft normative legal acts and periodic review of legislation for any provisions that could foster to corruption | 01.01.2025 | 31.03.2025 | National Agency on Corruption Prevention |  | state budget | within the established budget allocations for the relevant year | The analysis has been completed. | Станом на 31.12.2025 здійснюються підготовчі дії з метою організації проведення аналізу, передбаченого заходом 1.1.3.2.2. У зв’язку з обмеженістю доступних ресурсів та значним навантаженням на відповідальний самостійний структурний підрозділ, зумовленим виконанням пріоритетних завдань з підготовки проекту Антикорупційної стратегії на період після 2025 року, виконання заходу було відтерміновано. | Not implemented | 0.0
1.1 | Shaping and implementing the state anticorruption policy | 1.1.3 Provisions of normative legal acts and their drafts need to be further improved in order to eliminate potential factors that foster corruption | 1.1.3.2 | The mandatory anticorruption expert examination of drafts and existing normative legal acts is carried out systemically by entities authorized to do so; the results of anticorruption (particularly public) expert examination are subject to publication and mandatory review | 1.1.3.2.3 | Developing proposals for the National Agency to update the Anticorruption Expert Examination Procedure and Methodology | 01.04.2025 | 30.06.2025 | National Agency on Corruption Prevention |  | state budget | within the established budget allocations for the relevant year | Procedure and Methodology update proposals have been developed and publicized for a public discussion. | Виконання заходу 1.1.3.2.3. не розпочато, оскільки потребує завершення здійснення аналізу, передбаченого заходом 1.1.3.2.2. Станом на 31.12.2025 не завершено здійснення відповідного аналізу. У зв’язку з обмеженістю доступних ресурсів та значним навантаженням на відповідальний самостійний структурний підрозділ, зумовленим виконанням пріоритетних завдань з підготовки проекту Антикорупційної стратегії на період після 2025 року, виконання заходу було відтерміновано. | Not implemented | 0.0
1.1 | Shaping and implementing the state anticorruption policy | 1.1.3 Provisions of normative legal acts and their drafts need to be further improved in order to eliminate potential factors that foster corruption | 1.1.3.2 | The mandatory anticorruption expert examination of drafts and existing normative legal acts is carried out systemically by entities authorized to do so; the results of anticorruption (particularly public) expert examination are subject to publication and mandatory review | 1.1.3.2.4 | Conducting a public discussion of proposals for the National Agency to update the Anticorruption Expert Examination Procedure and Methodology | 01.07.2025 | 31.08.2025 | National Agency on Corruption Prevention |  | state budget | within the established budget allocations for the relevant year | The public discussion has been conducted and its results have been made public. | Виконання заходу 1.1.3.2.4. не розпочато, оскільки потребує завершення здійснення аналізу, передбаченого заходом 1.1.3.2.2, а також розроблення пропозицій, передбачених заходом 1.1.3.2.3. Станом на 31.12.2025 не завершено здійснення відповідного аналізу та не розпочато розроблення відповідних пропозицій. | Not implemented | 0.0
1.1 | Shaping and implementing the state anticorruption policy | 1.1.3 Provisions of normative legal acts and their drafts need to be further improved in order to eliminate potential factors that foster corruption | 1.1.3.2 | The mandatory anticorruption expert examination of drafts and existing normative legal acts is carried out systemically by entities authorized to do so; the results of anticorruption (particularly public) expert examination are subject to publication and mandatory review | 1.1.3.2.5 | Final revision (if needed) and approval of the updated Anticorruption Expert Examination Procedure and Methodology by the National Agency | 01.09.2025 | 31.10.2025 | National Agency on Corruption Prevention |  | state budget | within the established budget allocations for the relevant year | The Procedure and Methodology have been approved. | Виконання заходу 1.1.3.2.5. не розпочато, оскільки потребує завершення здійснення аналізу, передбаченого заходом 1.1.3.2.2, а також розроблення пропозицій, передбачених заходом 1.1.3.2.3. Станом на 31.12.2025 не завершено здійснення відповідного аналізу та не розпочато розроблення відповідних пропозицій. | Not implemented | 0.0
1.1 | Shaping and implementing the state anticorruption policy | 1.1.3 Provisions of normative legal acts and their drafts need to be further improved in order to eliminate potential factors that foster corruption | 1.1.3.2 | The mandatory anticorruption expert examination of drafts and existing normative legal acts is carried out systemically by entities authorized to do so; the results of anticorruption (particularly public) expert examination are subject to publication and mandatory review | 1.1.3.2.6 | Ensuring that the Ministry of Justice (prior to the delegation of these powers to the National Agency) and the National Agency (after receiving the relevant powers) carry out anticorruption expert examination of all draft acts submitted to the Cabinet of Ministers of Ukraine for review | 01.03.2023 | 31.12.2025 | Ministry of Justice of Ukraine | National Agency on Corruption Prevention | state budget | within the established budget allocations for the relevant year | Anticorruption expert examinations by the Ministry of Justice / National Agency cover 100 percent of draft laws submitted to the Cabinet of Ministers of Ukraine for review. | Протягом 2023-2025 років Міністерством юстиції України забезпечено проведення антикорупційної експертизи всіх проектів актів, поданих на розгляд Кабінету Міністрів України (в рамках проведення правової експертизи). Відповідні звіти розміщено на офіційному веб-сайті Міністерства юстиції України. | Implemented | 0.0