## Заходи
№ Напрямку | Напрямок | Проблема | № ОСР | Назва ОСР | № Заходу | Назва заходу | Дата початку | Дата завершення | Головний виконавець | Співвиконавці | Джерела фінансування | Обсяги фінансування, тис.грн. | Показник (індикатор) виконання | Стан виконання | Статус виконання | Оцінка досягнення ОСР
2.7 | Healthcare, education, science, and social security | 2.7.3 The electronic healthcare system is not sufficiently integrated with other databases, which creates opportunities for abuse during the use of specific functions (including the awarding of disability benefits, preventive and compulsory medical examinations, and assignment of the disability group) | 2.7.3.3 | Tools for assessing the functional status of a person according to the adapted International Classification of Functioning, Disability and Health have been introduced into the electronic healthcare system | 2.7.3.3.1 | Development and submission to Cabinet of Ministers of Ukraine a draft regulation of Cabinet of Ministers of Ukraine on amendments to the electronic medical care system operation procedure on the following: 1) electronic medical records on the system operational status involving the use of the National classified (NC) 030:2022 ‘Operation, vital functions limitations and health classifier’ are uploaded to electronic medical care system; 2) data from electronic medical care systems used by the person to obtain appropriate services based on individual rehabilitation plan with the use of the National classifier (NC) 030:2022 ‘Operation, vital functions limitations and health classifier’. | 01.03.2023 | 30.11.2023 | Ministry of Health of Ukraine | National Health Service of Ukraine | state budget | within the established budget allocations for the relevant year | The resolution of the Cabinet of Ministers of Ukraine has been adopted. | In order to implement the measure provided for in subclause 2.7.3.3.1 of the State Anti-Corruption Program for 2023-2025, the Ministry of Health of Ukraine reported that the Resolution of the Cabinet of Ministers of Ukraine dated March 30, 2023 No. 279 On Amendments to the Resolutions of the Cabinet of Ministers of Ukraine dated April 25, 2018 No. 411 and November 3, 2021 No. 1268 was adopted. From the analysis of the content of this resolution, it is stated that: 1) information and medical documentation (electronic medical records) necessary for establishing a person's disability shall be entered into the electronic healthcare system exclusively using the National Classifier 030:2022 named Classifier of Functioning, Disability and Health (which is identical to the International Classification of Functioning, Disability and Health); 2) when a person receives services for which the National Classifier 030:2022 named Classifier of Functioning, Disability and Health is used, the forms approved by the Ministry of Health of Ukraine shall be used in the electronic healthcare system. Thus, we can state that the measure was completed on time and in full. | Implemented | 0.0
2.7 | Healthcare, education, science, and social security | 2.7.3 The electronic healthcare system is not sufficiently integrated with other databases, which creates opportunities for abuse during the use of specific functions (including the awarding of disability benefits, preventive and compulsory medical examinations, and assignment of the disability group) | 2.7.3.3 | Tools for assessing the functional status of a person according to the adapted International Classification of Functioning, Disability and Health have been introduced into the electronic healthcare system | 2.7.3.3.4 | Approving the statement of work (“technical assignment”) for the expansion of the functionality of the electronic healthcare system with respect to: 1) implementation of the National classifier NC 030:2022 ‘Operation, vital functions limitations and health classifier’; 2) uploading electronic medical records on person’s performance involving the use of the National classifier NC 030:2022 ‘Operation, vital functions limitations and health classifier’; 3) possibility to use data from electronic medical care system for the person to obtain appropriate services based on individual rehabilitation plan involving the use of the National classifier NC 030:2022 ‘Operation, vital functions limitations and health classifier’. | 01.04.2024 | 31.10.2024 | Ministry of Health of Ukraine | National Health Service of Ukraine | state budget and/or international technical assistance funds | within the established budget allocations for the relevant year or amount of international technical assistance | The statement of work has been approved. | На виконання заходу передбаченого п. 2.7.3.3.4 Державної антикорупційної програми на 2023-2025 роки, Міністерством охорони здоров'я повідомлено, що: "розроблено технічне завдання та здійснено технічну розробку впровадження можливості застосування в ЕСОЗ Національного класифікатора НК 030:2022 “Класифікатор функціонування, обмеження життєдіяльності та здоров'я”; зазначений функціонал було включено до складу ЕСОЗ". З аналізу наданих на підтвердження виконання цього заходу документів можемо встановити, що на разі: - впроваджено в ЕСОЗ процеси по створенню та веденню індивідуального реабілітаційного плану фахівцями з реабілітації, які безпосередньо надають реабілітаційну допомогу; - впроваджено можливості застосування в ЕСОЗ Національного класифікатора НК 030:2022 “Класифікатор функціонування, обмеження життєдіяльності та здоров'я” та міжнародного Класифікатора ISO 9999 “Допоміжні засоби для осіб з обмеженням життєдіяльності”; - впроваджено в ЕСОЗ процесів щодо можливості реєстрації та використання результатів реабілітаційного обстеження, встановлення завдань реабілітації, планування та реалізація реабілітаційних втручань та оцінювання ефективності надання реабілітаційної допомоги. Таким чином, можемо констатувати, що захід передбачений п. 2.7.3.3.4 Державної антикорупційної програми на 2023-2025 роки є виконаним вчасно та повністю. | Implemented | 0.0
2.7 | Healthcare, education, science, and social security | 2.7.3 The electronic healthcare system is not sufficiently integrated with other databases, which creates opportunities for abuse during the use of specific functions (including the awarding of disability benefits, preventive and compulsory medical examinations, and assignment of the disability group) | 2.7.3.3 | Tools for assessing the functional status of a person according to the adapted International Classification of Functioning, Disability and Health have been introduced into the electronic healthcare system | 2.7.3.3.5 | Developing software for expansion of the functionality of the electronic healthcare system in accordance with subclause 2.7.3.3.4 | 01.06.2024 | 31.10.2024 | Ministry of Health of Ukraine | National Health Service of Ukraine | state budget and/or international technical assistance funds | within the established budget allocations for the relevant year or amount of international technical assistance | The software has been developed. | На виконання заходу передбаченого п. 2.7.3.3.5 Державної антикорупційної програми на 2023-2025 роки, Міністерством охорони здоров'я повідомлено, що: "розроблено технічне завдання та здійснено технічну розробку впровадження можливості застосування в ЕСОЗ Національного класифікатора НК 030:2022 “Класифікатор функціонування, обмеження життєдіяльності та здоров'я”; зазначений функціонал було включено до складу ЕСОЗ". З аналізу наданих на підтвердження виконання цього заходу документів можемо встановити, що на разі: - впроваджено в ЕСОЗ процеси по створенню та веденню індивідуального реабілітаційного плану фахівцями з реабілітації, які безпосередньо надають реабілітаційну допомогу; - впроваджено можливості застосування в ЕСОЗ Національного класифікатора НК 030:2022 “Класифікатор функціонування, обмеження життєдіяльності та здоров'я” та міжнародного Класифікатора ISO 9999 “Допоміжні засоби для осіб з обмеженням життєдіяльності”; - впроваджено в ЕСОЗ процесів щодо можливості реєстрації та використання результатів реабілітаційного обстеження, встановлення завдань реабілітації, планування та реалізація реабілітаційних втручань та оцінювання ефективності надання реабілітаційної допомоги. Таким чином, можемо констатувати, що захід передбачений п. 2.7.3.3.5 Державної антикорупційної програми на 2023-2025 роки є виконаним вчасно та повністю. | Implemented | 0.0
2.7 | Healthcare, education, science, and social security | 2.7.3 The electronic healthcare system is not sufficiently integrated with other databases, which creates opportunities for abuse during the use of specific functions (including the awarding of disability benefits, preventive and compulsory medical examinations, and assignment of the disability group) | 2.7.3.3 | Tools for assessing the functional status of a person according to the adapted International Classification of Functioning, Disability and Health have been introduced into the electronic healthcare system | 2.7.3.3.6 | Putting into operation the expanded functionality of the electronic healthcare system in accordance with subclause 2.7.3.3.4 | 01.09.2024 | 31.12.2024 | Ministry of Health of Ukraine | National Health Service of Ukraine | state budget and/or international technical assistance funds | within the established budget allocations for the relevant year or amount of international technical assistance | The expanded functionality of the electronic healthcare system has been put into operation. | На виконання заходу передбаченого п. 2.7.3.3.6 Державної антикорупційної програми на 2023-2025 роки, Міністерством охорони здоров'я повідомлено, що: "розроблено технічне завдання та здійснено технічну розробку впровадження можливості застосування в ЕСОЗ Національного класифікатора НК 030:2022 “Класифікатор функціонування, обмеження життєдіяльності та здоров'я”; зазначений функціонал було включено до складу ЕСОЗ". З аналізу наданих на підтвердження виконання цього заходу документів можемо встановити, що на разі: - впроваджено в ЕСОЗ процеси по створенню та веденню індивідуального реабілітаційного плану фахівцями з реабілітації, які безпосередньо надають реабілітаційну допомогу; - впроваджено можливості застосування в ЕСОЗ Національного класифікатора НК 030:2022 “Класифікатор функціонування, обмеження життєдіяльності та здоров'я” та міжнародного Класифікатора ISO 9999 “Допоміжні засоби для осіб з обмеженням життєдіяльності”; - впроваджено в ЕСОЗ процесів щодо можливості реєстрації та використання результатів реабілітаційного обстеження, встановлення завдань реабілітації, планування та реалізація реабілітаційних втручань та оцінювання ефективності надання реабілітаційної допомоги. Таким чином, можемо констатувати, що захід передбачений п. 2.7.3.3.6 Державної антикорупційної програми на 2023-2025 роки є виконаним вчасно та повністю | Implemented | 0.0