## Заходи
№ Напрямку | Напрямок | Проблема | № ОСР | Назва ОСР | № Заходу | Назва заходу | Дата початку | Дата завершення | Головний виконавець | Співвиконавці | Джерела фінансування | Обсяги фінансування, тис.грн. | Показник (індикатор) виконання | Стан виконання | Статус виконання | Оцінка досягнення ОСР
2.7 | Healthcare, education, science, and social security | 2.7.4 Insufficiently transparent recruitment procedures at healthcare institutions hinder competition and create opportunities for manifestations of corruption in appointments to such positions | 2.7.4.1 | A publicly accessible single web portal of vacancies at state and municipal healthcare institutions is functioning | 2.7.4.1.1 | Drafting and submitting to the Cabinet of Ministers of Ukraine a draft resolution of the Cabinet of Ministers of Ukraine on approval of the Regulation on the single website of vacancies at state and municipal healthcare institutions, which stipulates that: 1) open access to the website shall be granted in keeping with the requirements of legislation on the protection of personal data; 2) the website must contain complete information about all available vacancies along with the names and addresses of the relevant healthcare institutions; 3) the website must publish information about the dates of the competitive selection process, the deadline and address for submission of the application for the position; 4) recruitment for vacant positions (including managerial positions) at state and municipal healthcare institutions is carried out exclusively through the website; | 01.07.2023 | 31.10.2024 | Ministry of Health of Ukraine |  | state budget | within the established budget allocations for the relevant year | The resolution of the Cabinet of Ministers of Ukraine has been adopted. | На виконання заходу передбаченого п. 2.7.4.1.1. Державної антикорупційної програми на 2023-2025 роки, Міністерством охорони здоров'я України повідомлено, що: "затверджено постанову Кабінету Міністрів України від 29 березня 2024 р. № 358 "Про затвердження Положення про Єдиний веб-портал вакантних посад у державних та комунальних закладах охорони здоров’я та внесення змін до Порядку проведення конкурсу на зайняття посади керівника державного, комунального закладу охорони здоров’я". Відзначимо, що постанова Кабінету Міністрів Україн від 29 березня 2024 р. № 358 відповідає Державній антикорупційній програмі, зокрема останньою передбачаються те, що за допомогою єдиного веб-сайту вакантних посад: 1) надається відкритий доступ до веб-сайту з урахуванням вимог законодавства про захист персональних даних; 2) оприлюднюється повна інформація про всі наявні вакантні посади із вказівкою назв та адрес відповідних закладів охорони здоров’я; 3) оприлюднюється інформація про дати конкурсу, строки та адресу подання документів на зайняття посади; 4) проводиться добір на вакантні посади (у тому числі керівні) у державних та комунальних закладах охорони здоров’я. Таким чином, можемо констатувати, що захід передбачений п. 2.7.4.1.1. є виконаним вчасно та повністю. | Implemented | 0.0
2.7 | Healthcare, education, science, and social security | 2.7.4 Insufficiently transparent recruitment procedures at healthcare institutions hinder competition and create opportunities for manifestations of corruption in appointments to such positions | 2.7.4.1 | A publicly accessible single web portal of vacancies at state and municipal healthcare institutions is functioning | 2.7.4.1.2 | Developing and approving a statement of work (“technical assignment”) for the creation of the single website of vacancies at state and municipal healthcare institutions | 01.09.2023 | 31.10.2024 | Ministry of Health of Ukraine |  | state budget and/or international technical assistance funds | within the established budget allocations for the relevant year and/or international technical assistance funds | The statement of work has been approved. | На виконання заходу передбаченого п. 2.7.4.1.2 Державної антикорупційної програми на 2023-2025 роки, Міністерством охорони здоров'я повідомлено, що: "розроблено технічне завдання на створення програмного забезпечення інформаційно-комунікаційної системи «Єдиний портал вакансій працівників сфери охорони здоров’я», що опрацьовується структурними підрозділами МОЗ". На підтвердження виконання вказаного заходу до ознайомлення Міністерством охорони здоров'я надано відповідне технічне завдання з описом необхідного функціоналу для реалізації робіт з розробки програмного забезпечення електронної системи для реалізації сервісу "Єдиний портал вакансій працівників сфери охорони здоров'я". З огляду на це, можемо констатувати, що захід передбачений п. 2.7.4.1.2 є виконаним вчасно та повністю. | Implemented | 0.0
2.7 | Healthcare, education, science, and social security | 2.7.4 Insufficiently transparent recruitment procedures at healthcare institutions hinder competition and create opportunities for manifestations of corruption in appointments to such positions | 2.7.4.1 | A publicly accessible single web portal of vacancies at state and municipal healthcare institutions is functioning | 2.7.4.1.3 | Developing the design of the single web portal of vacancies at state and municipal healthcare institutions | 01.01.2024 | 30.11.2024 | Ministry of Health of Ukraine |  | state budget and/or international technical assistance funds | within the established budget allocations for the relevant year and/or international technical assistance funds | The draft has been developed. | In pursuance of the measure provided by clause 2.7.4.1.3 of the State Anti-Corruption Program for 2023–2025, the Ministry of Health of Ukraine reported that: “Technical requirements were developed for the creation of the unified website of job openings at public and municipal healthcare facilities are developed, resources are allocated, and contract for development of the terms of reference for software development for information and communication system ‘Unified Portal of Healthcare Job Openings.’ The software development process is at the final stage.” In previous periods, the Ministry of Health provided for review Contract No. EGAP 6/02-24/41 dated March 1, 2024, on the provision of consulting services regarding digitalization matters, namely: preparation of the terms of reference and software development to ensure the operation of the information and communication system “Unified Portal of Healthcare Job Openings.” An annex to this contract contains the Technical Requirements for Software Development for the information and communication system “Unified Portal of Healthcare Job Openings.” Therefore, based on the information provided by the Ministry of Health of Ukraine, we may conclude that consistent work is being carried out to implement the measure provided by clause 2.7.4.1.3. of the State Anti-Corruption Program for 2023–2025. The monitoring conducted during the reporting period revealed that the Portal of Job Openings for Healthcare Professionals was launched into operations and allowed all healthcare professionals to search for job openings by applying various filters (healthcare facility location, medical specialty, healthcare facility ownership form). Therefore, we may conclude that the measure is fully and timely implemented. | Implemented | 0.0
2.7 | Healthcare, education, science, and social security | 2.7.4 Insufficiently transparent recruitment procedures at healthcare institutions hinder competition and create opportunities for manifestations of corruption in appointments to such positions | 2.7.4.1 | A publicly accessible single web portal of vacancies at state and municipal healthcare institutions is functioning | 2.7.4.1.4 | Launching the single web portal of vacancies at state and municipal healthcare institutions | 01.05.2024 | 30.11.2024 | Ministry of Health of Ukraine |  | state budget and/or international technical assistance funds | within the established budget allocations for the relevant year and/or international technical assistance funds | The single website of vacancies at state and municipal healthcare institutions has been launched. | На виконання заходу передбаченого п. 2.7.4.1.4 Державної антикорупційної програми на 2023-2025 роки, Міністерством охорони здоров'я України повідомлено, що: "програмне забезпечення «Єдиний веб-портал вакантних посад у державних та комунальних закладах охорони здоров’я» введено в дослідну експлуатацію Наказом МОЗ №1384 від 06.08.2024". З аналізу інформації, що надана Міністерством охорони здоров'я України, а також з відкритих джерел стало відомо, що єдиний веб-портал вакантних посад у державних та комунальних закладах охорони здоров'я функціонує. Зокрема, можливий пошук за назвою вакансії, назвою закладу охорони здоров'я, його місцезнаходженням, ідентифікатором вакансії, кінцевим терміном подачі резюме. Таким чином, можемо констатувати, що захід передбачений п. 2.7.4.1.4 Державної антикорупційної програми є виконаним вчасно та повністю | Implemented | 0.0