## Заходи
№ Напрямку | Напрямок | Проблема | № ОСР | Назва ОСР | № Заходу | Назва заходу | Дата початку | Дата завершення | Головний виконавець | Співвиконавці | Джерела фінансування | Обсяги фінансування, тис.грн. | Показник (індикатор) виконання | Стан виконання | Статус виконання | Оцінка досягнення ОСР
3.2 | Administrative liability | 3.2.1 Some of the rules, prohibitions, and restrictions established by anticorruption legislation are not backed up by legal liability measures. Articles 1724—1729, 21215, 21221 of the Code of Ukraine on Administrative Offenses contain a number of shortcomings that significantly impair their injunctive and preventive potential as well as the effectiveness of the National Agency, the National Police, prosecutorial authorities and courts. | 3.2.1.2 | Based on the findings of the analysis and consolidation of the practice of bringing perpetrators to justice for administrative offenses involving corruption, the relevant prohibitions have been systematically improved | 3.2.1.2.1 | Analyzing the legislation and consolidating the practice of prosecution of entities subject to the Law of Ukraine On Prevention of Corruption for committing corruption-related administrative offenses in 2014-2024 with respect to: 1) the systemic, complete, and legally correct definition at the legislative level of the grounds on which such liability arises; 2) alignment of the penalties imposed with the principles of fairness, proportionality, and individualization, as well as the capability to accomplish the objective of the administrative penalty. Preparing an analytical report with proposals of systemic improvements to the relevant prohibitions under administrative law, the kinds and amounts of penalties prescribed by them, as well as correct and consistent application of the relevant legislation by the National Agency, the National Police, the prosecutorial authorities, and courts | 01.01.2025 | 30.06.2025 | National Agency on Corruption Prevention |  | state budget and/or international technical assistance funds | within the established budget allocations for the relevant year and/or international technical assistance funds | The analysis has been completed. The analytical report with proposals and recommendations has been prepared. | Національне агентство спільно з колегами з Центру політико-правових реформ провело аналіз судової практики притягнення до відповідальності за адміністративні правопорушення, пов’язані з корупцією, за 2014 – 2024 роки, а також у листопаді 2025 року завершило підготовку аналітичного звіту з пропозиціями щодо системного удосконалення відповідних адміністративно-правових заборон, передбачених ними видів і розмірів стягнень, а також щодо правильного та однакового застосування відповідного законодавства Національним агентством, Національною поліцією, прокуратурою та судами. | Implemented | 0.0
3.2 | Administrative liability | 3.2.1 Some of the rules, prohibitions, and restrictions established by anticorruption legislation are not backed up by legal liability measures. Articles 1724—1729, 21215, 21221 of the Code of Ukraine on Administrative Offenses contain a number of shortcomings that significantly impair their injunctive and preventive potential as well as the effectiveness of the National Agency, the National Police, prosecutorial authorities and courts. | 3.2.1.2 | Based on the findings of the analysis and consolidation of the practice of bringing perpetrators to justice for administrative offenses involving corruption, the relevant prohibitions have been systematically improved | 3.2.1.2.2 | Drafting and submitting to the Cabinet of Ministers of Ukraine a draft law on amendments to the Code of Ukraine on Administrative Offenses aimed at systemic improvement of the grounds for holding offenders liable for corruption-related administrative offenses, as well as stipulating the kinds and amounts of penalties to be imposed on such offenders | 01.07.2025 | 31.12.2025 | National Agency on Corruption Prevention |  | state budget | within the established budget allocations for the relevant year | The draft law has been submitted to the Parliament of Ukraine. | Здійснюється підготовка зазначеного законопроекту. З огляду на те, що настала дата завершення строку виконання відповідного заходу, а законопроект станом на момент звітування не розроблено та не забезпечувалось його подання Кабінетові Міністрів України, такий захід вважається не виконаним. | Not implemented | 0.0
3.2 | Administrative liability | 3.2.1 Some of the rules, prohibitions, and restrictions established by anticorruption legislation are not backed up by legal liability measures. Articles 1724—1729, 21215, 21221 of the Code of Ukraine on Administrative Offenses contain a number of shortcomings that significantly impair their injunctive and preventive potential as well as the effectiveness of the National Agency, the National Police, prosecutorial authorities and courts. | 3.2.1.2 | Based on the findings of the analysis and consolidation of the practice of bringing perpetrators to justice for administrative offenses involving corruption, the relevant prohibitions have been systematically improved | 3.2.1.2.3 (1) | Implementation of measures (identified after studying the proposals formulated in the report indicated in subclauses 3.2.1.2.1, 3.2.1.3.1) by the National Agency, the National Police, the prosecutorial authorities, and courts towards ensuring the correct and consistent application of the relevant legislation in practice | 01.01.2025 | 31.12.2025 | National Agency on Corruption Prevention |  | state budget | within the established budget allocations for the relevant year | The measures have been implemented. | Виконання заходу не розпочато з огляду на те, що підготовка вищезазначеного звіту (передбаченого п. п. 3.2.1.2.1, 3.2.1.3.1 додатка 2 до Державної антикорупційної програми на 2023 - 2025 роки) завершилась у листопаді 2025 року. Відсутність достатнього часу для вививчення пропозицій, сформованих у звіті, та вжиття заходів, спрямованих на забезпечення правильного та однакового застосування відповідного законодавства на практиці, унеможливило виконання відповідного заходу Державної антикорупційної програми на 2023 - 2025 роки у IV кварталі 2025 року. Водночас з огляду на настання дати завершення строку виконання, зважаючи на недосягнення показника (індикатора) виконання, відповідний захід не може вважатися виконаним. | Not implemented | 0.0
3.2 | Administrative liability | 3.2.1 Some of the rules, prohibitions, and restrictions established by anticorruption legislation are not backed up by legal liability measures. Articles 1724—1729, 21215, 21221 of the Code of Ukraine on Administrative Offenses contain a number of shortcomings that significantly impair their injunctive and preventive potential as well as the effectiveness of the National Agency, the National Police, prosecutorial authorities and courts. | 3.2.1.2 | Based on the findings of the analysis and consolidation of the practice of bringing perpetrators to justice for administrative offenses involving corruption, the relevant prohibitions have been systematically improved | 3.2.1.2.3 (2) | Implementation of measures (identified after studying the proposals formulated in the report indicated in subclauses 3.2.1.2.1, 3.2.1.3.1) by the National Agency, the National Police, the prosecutorial authorities, and courts towards ensuring the correct and consistent application of the relevant legislation in practice | 01.01.2025 | 31.12.2025 | National Police of Ukraine |  | state budget | within the established budget allocations for the relevant year | The measures have been implemented. | Виконання заходу не розпочато з огляду на те, що підготовка вищезазначеного звіту (передбаченого п. п. 3.2.1.2.1, 3.2.1.3.1 додатка 2 до Державної антикорупційної програми на 2023 - 2025 роки) завершилась у листопаді 2025 року. Відсутність достатнього часу для вививчення пропозицій, сформованих у звіті, та вжиття заходів, спрямованих на забезпечення правильного та однакового застосування відповідного законодавства на практиці, унеможливило виконання відповідного заходу Державної антикорупційної програми на 2023 - 2025 роки у IV кварталі 2025 року. Водночас з огляду на настання дати завершення строку виконання, зважаючи на недосягнення показника (індикатора) виконання, відповідний захід не може вважатися виконаним. | Not implemented | 0.0
3.2 | Administrative liability | 3.2.1 Some of the rules, prohibitions, and restrictions established by anticorruption legislation are not backed up by legal liability measures. Articles 1724—1729, 21215, 21221 of the Code of Ukraine on Administrative Offenses contain a number of shortcomings that significantly impair their injunctive and preventive potential as well as the effectiveness of the National Agency, the National Police, prosecutorial authorities and courts. | 3.2.1.2 | Based on the findings of the analysis and consolidation of the practice of bringing perpetrators to justice for administrative offenses involving corruption, the relevant prohibitions have been systematically improved | 3.2.1.2.3 (3) | Implementation of measures (identified after studying the proposals formulated in the report indicated in subclauses 3.2.1.2.1, 3.2.1.3.1) by the National Agency, the National Police, the prosecutorial authorities, and courts towards ensuring the correct and consistent application of the relevant legislation in practice | 01.01.2025 | 31.12.2025 | Prosecutor General’s Office of Ukraine |  | state budget | within the established budget allocations for the relevant year | The measures have been implemented. | Виконання заходу не розпочато з огляду на те, що підготовка вищезазначеного звіту (передбаченого п. п. 3.2.1.2.1, 3.2.1.3.1 додатка 2 до Державної антикорупційної програми на 2023 - 2025 роки) завершилась у листопаді 2025 року. Відсутність достатнього часу для вививчення пропозицій, сформованих у звіті, та вжиття заходів, спрямованих на забезпечення правильного та однакового застосування відповідного законодавства на практиці, унеможливило виконання відповідного заходу Державної антикорупційної програми на 2023 - 2025 роки у IV кварталі 2025 року. Водночас з огляду на настання дати завершення строку виконання, зважаючи на недосягнення показника (індикатора) виконання, відповідний захід не може вважатися виконаним. | Not implemented | 0.0
3.2 | Administrative liability | 3.2.1 Some of the rules, prohibitions, and restrictions established by anticorruption legislation are not backed up by legal liability measures. Articles 1724—1729, 21215, 21221 of the Code of Ukraine on Administrative Offenses contain a number of shortcomings that significantly impair their injunctive and preventive potential as well as the effectiveness of the National Agency, the National Police, prosecutorial authorities and courts. | 3.2.1.2 | Based on the findings of the analysis and consolidation of the practice of bringing perpetrators to justice for administrative offenses involving corruption, the relevant prohibitions have been systematically improved | 3.2.1.2.3 (4) | Implementation of measures (identified after studying the proposals formulated in the report indicated in subclauses 3.2.1.2.1, 3.2.1.3.1) by the National Agency, the National Police, the prosecutorial authorities, and courts towards ensuring the correct and consistent application of the relevant legislation in practice | 01.01.2025 | 31.12.2025 | Supreme Court |  | state budget | within the established budget allocations for the relevant year | The measures have been implemented. | Виконання заходу не розпочато з огляду на те, що підготовка вищезазначеного звіту (передбаченого п. п. 3.2.1.2.1, 3.2.1.3.1 додатка 2 до Державної антикорупційної програми на 2023 - 2025 роки) завершилась у листопаді 2025 року. Відсутність достатнього часу для вививчення пропозицій, сформованих у звіті, та вжиття заходів, спрямованих на забезпечення правильного та однакового застосування відповідного законодавства на практиці, унеможливило виконання відповідного заходу Державної антикорупційної програми на 2023 - 2025 роки у IV кварталі 2025 року. Водночас з огляду на настання дати завершення строку виконання, зважаючи на недосягнення показника (індикатора) виконання, відповідний захід не може вважатися виконаним. | Not implemented | 0.0