## Заходи
№ Напрямку | Напрямок | Проблема | № ОСР | Назва ОСР | № Заходу | Назва заходу | Дата початку | Дата завершення | Головний виконавець | Співвиконавці | Джерела фінансування | Обсяги фінансування, тис.грн. | Показник (індикатор) виконання | Стан виконання | Статус виконання | Оцінка досягнення ОСР
3.3 | Criminal liability | 3.3.1 Certain provisions of criminal law relating to criminal liability for corruption-related criminal offenses contradict international standards in this field, are not coordinated with each other and with the provisions of the criminal procedure legislation and the Law of Ukraine On Prevention of Corruption. As a result, in a significant number of cases, perpetrators of corruption-related criminal offenses are relieved of criminal liability and/or punishment | 3.3.1.1 | Discrepancies between the provisions of the Criminal Code of Ukraine and the Law of Ukraine On Prevention of Corruption regarding the definition of crimes of corruption have been eliminated | 3.3.1.1.1 | Arranging an analytical study whose scope includes, in particular: identification of terminological discrepancies, conflicts, and manifestations of unjustified competition arising among the Criminal Code of Ukraine, the Law of Ukraine On Prevention of Corruption, and the Criminal Procedure Code of Ukraine when it comes to defining crimes of corruption and corruption-related offenses; alignment of legislative provisions governing relief of criminal liability for corruption and corruption-related criminal offenses, measures taken with respect to legal entities under criminal law, as well as identifying the subjects of crimes of corruption and corruption-related criminal offenses, with international anticorruption standards | 01.01.2025 | 31.05.2025 | National Agency on Corruption Prevention | National Anti-Corruption Bureau of Ukraine | state budget and/or international technical assistance funds | within the established budget allocations for the relevant year | The analytical study has been conducted and a report on its findings has been published. | Продовжується підготовка до проведення аналітичного дослідження. З огляду на те, що настала дата завершення строку виконання відповідного заходу, а аналітичне дослідження станом на момент звітування не проведено, такий захід вважається не виконаним. | Not implemented | 0.0
3.3 | Criminal liability | 3.3.1 Certain provisions of criminal law relating to criminal liability for corruption-related criminal offenses contradict international standards in this field, are not coordinated with each other and with the provisions of the criminal procedure legislation and the Law of Ukraine On Prevention of Corruption. As a result, in a significant number of cases, perpetrators of corruption-related criminal offenses are relieved of criminal liability and/or punishment | 3.3.1.1 | Discrepancies between the provisions of the Criminal Code of Ukraine and the Law of Ukraine On Prevention of Corruption regarding the definition of crimes of corruption have been eliminated | 3.3.1.1.2 | Holding a presentation of the report on the findings of the analytical study indicated in subclause 3.3.1.1.1, followed by its expert discussion | 01.06.2025 | 30.06.2025 | National Agency on Corruption Prevention | National Anti-Corruption Bureau of Ukraine | state budget | within the established budget allocations for the relevant year | The expert discussion has been conducted and its results have been published. | Проведення презентації та експертного обговорення звіту відбудеться після проведення аналітичного дослідження, передбаченого заходом 3.3.1.1.1 Державної антикорупційної програми на 2023 - 2025 роки. З огляду на те, що настала дата завершення строку виконання відповідного заходу, такий захід вважається не виконаним. | Not implemented | 0.0
3.3 | Criminal liability | 3.3.1 Certain provisions of criminal law relating to criminal liability for corruption-related criminal offenses contradict international standards in this field, are not coordinated with each other and with the provisions of the criminal procedure legislation and the Law of Ukraine On Prevention of Corruption. As a result, in a significant number of cases, perpetrators of corruption-related criminal offenses are relieved of criminal liability and/or punishment | 3.3.1.1 | Discrepancies between the provisions of the Criminal Code of Ukraine and the Law of Ukraine On Prevention of Corruption regarding the definition of crimes of corruption have been eliminated | 3.3.1.1.3 | Drafting and submitting to the Cabinet of Ministers of Ukraine a draft law proposing to eliminate the existing terminological discrepancies, conflicts, and manifestations of unjustified competition arising among the Criminal Code of Ukraine, the Law, and the Criminal Procedure Code of Ukraine when it comes to defining crimes of corruption and corruption-related offenses, taking into account the findings of the analytical study indicated in subclause 3.3.1.1.1 | 01.07.2025 | 31.12.2025 | National Agency on Corruption Prevention | National Anti-Corruption Bureau of Ukraine, Prosecutor General’s Office of Ukraine | state budget | within the established budget allocations for the relevant year | The draft law has been submitted to the Parliament of Ukraine. | Розроблення зазначеного законопроекту розпочнеться після проведення аналітичного дослідження, передбаченого заходом 3.3.1.1.1 Державної антикорупційної програми на 2023 - 2025 роки. З огляду на те, що настала дата завершення строку виконання відповідного заходу, а законопроект станом на момент звітування не розроблено та не забезпечувалось його подання Кабінетові Міністрів України, такий захід вважається не виконаним. | Not implemented | 0.0