## Заходи
№ Напрямку | Напрямок | Проблема | № ОСР | Назва ОСР | № Заходу | Назва заходу | Дата початку | Дата завершення | Головний виконавець | Співвиконавці | Джерела фінансування | Обсяги фінансування, тис.грн. | Показник (індикатор) виконання | Стан виконання | Статус виконання | Оцінка досягнення ОСР
3.3 | Criminal liability | 3.3.3 The legislation governing the activity of the ARMA contains numerous gaps and corruption risks. Low effectiveness of the processes of transferring assets to ARMA for management to preserve their economic value, as well as the processes of combating and preventing money laundering | 3.3.3.11 | Measures to prevent the laundering of money obtained through corruption are determined based on the results of risk assessment and are duly implemented. FATF recommendations are being consistently implemented | 3.3.3.11.1 | Submitting to the Cabinet of Ministers of Ukraine the draft law on the creation of the Unified Register of Accounts of Individuals and Legal Entities and Individual Bank Safe Deposit Boxes in accordance with EU Directive 2015/849 on the prevention of the use of the financial system for the purposes of money laundering or terrorist financing and on amendments to Directives 2009/138/EU and 2013/36/EU (as subsequently amended), and supporting its passage | 01.03.2023 | 01.01.1970 | Ministry of Finance of Ukraine |  | state budget | within the established budget allocations for the relevant year | The draft law has been submitted to the Parliament of Ukraine. | На виконання заходу, передбаченого п.п. 3.3.3.11.1 додатка 2 до Державної антикорупційної програми на 2023-2025 роки, Міністерством фінансів України розроблено проект Закону України «Про внесення змін до Податкового кодексу України та деяких законодавчих актів України щодо створення єдиного реєстру рахунків фізичних і юридичних осіб та індивідуальних банківських сейфів», який 02.03.2023 подано на розгляд Уряду. Кабінет Міністрів України повернув Мінфіну зазначену законодавчу ініціативу для додаткового опрацювання, оцінки актуальності, внесення змін з урахуванням норм прийнятих нормативно-правових актів. Питання щодо доопрацювання законопроекту та відповідності його актам права ЄС розглядалось в рамках Міжвідомчої робочої групи з питань впровадження змін до законодавства у сфері запобігання та протидії легалізації (відмиванню) доходів, одержаних злочинним шляхом, фінансуванню тероризму та фінансуванню розповсюдження зброї масового знищення з метою приєднання України до Єдиної зони платежів у євро (SEPA), утвореної відповідно до постанови Кабінету Міністрів України від 01.11.2024 № 1257. Міністерство фінансів України інформувало, що в рамках відповідної Міжвідомчої робочої групи розроблено проект Закону України «Про внесення змін до деяких законів України щодо забезпечення відповідності актам права Європейського Союзу та відповідним критеріям, встановленим Європейською платіжною радою, з метою приєднання України до Єдиної зони платежів у євро (SEPA)», положення якого передбачають вимоги щодо створення реєстру рахунків та індивідуальних банківських сейфів фізичних осіб, визначення: Державної податкової служба України держателем та адміністратором цього реєстру, відомостей, які вносяться до нього тощо. Зазначений законопроект 10.04.2025 направлено на розгляд Кабінету Міністрів України, схвалено Урядом та зареєстровано у Верховній Раді України 30.04.2025 за реєстр. № 13233. 03.07.2025 Комітетом Верховної Ради України з питань фінансів, податкової та митної політики рекомендовано Верховній Раді України законопроект № 13233 прийняти за основу. З огляду на те, що станом на кінець другого кварталу показник (індикатор) виконання відповідного заходу було досягнуто, захід вважався таким, що виконаний повністю. Водночас 17.07.2025 законопроект реєстр. № 13233 від 30.04.2025 знято з розгляду (відкликано відповідно до ч. 3 ст. 105 Закону України "Про Регламент Верховної Ради України" у зв'язку з припиненням повноважень Кабінету Міністрів України). Міністерство фінансів України забезпечило доопрацювання відповідного законопроекту, за результатом якого законодавчу ініціативу подано Кабінету Міністрів України. Уряд схвалив зазначений законопроект, який згодом подано до Верховної Ради України та зареєстровано від 23.12.2025 № 14327. | Implemented | 0.0
3.3 | Criminal liability | 3.3.3 The legislation governing the activity of the ARMA contains numerous gaps and corruption risks. Low effectiveness of the processes of transferring assets to ARMA for management to preserve their economic value, as well as the processes of combating and preventing money laundering | 3.3.3.11 | Measures to prevent the laundering of money obtained through corruption are determined based on the results of risk assessment and are duly implemented. FATF recommendations are being consistently implemented | 3.3.3.11.2 | Drafting and submitting to the Cabinet of Ministers of Ukraine a draft law that stipulates that property shall be deemed to have been obtained by criminal means for the purposes of Article 209 of the Criminal Code of Ukraine taking into account the factual circumstances and does not require a court decision issued in Ukraine or abroad, which has established the fact of the commission of the crime that resulted in the acquisition of such property or has criminally prosecuted the defendant for this crime | 01.07.2024 | 31.12.2024 | National Agency on Corruption Prevention | Ministry of Finance of Ukraine, State Financial Monitoring Service of Ukraine, National Police of Ukraine, Prosecutor General’s Office of Ukraine , State Bureau of Investigation , National Anti-Corruption Bureau of Ukraine, Security Service of Ukraine , Economic Security Bureau of Ukraine | state budget | within the established budget allocations for the relevant year | The draft law has been submitted to the Parliament of Ukraine. | Національне агентство за результатами опрацювання змісту зазначеного заходу на предмет існування проблеми, на вирішення якої він спрямований, підготувало аналітичний звіт, у якому констатована відсутність потреби у розробленні та прийнятті законопроекту, передбаченого цим заходом. | Not implemented | 0.0
3.3 | Criminal liability | 3.3.3 The legislation governing the activity of the ARMA contains numerous gaps and corruption risks. Low effectiveness of the processes of transferring assets to ARMA for management to preserve their economic value, as well as the processes of combating and preventing money laundering | 3.3.3.11 | Measures to prevent the laundering of money obtained through corruption are determined based on the results of risk assessment and are duly implemented. FATF recommendations are being consistently implemented | 3.3.3.11.3 | Supporting the consideration of the draft law that updates the provisions of the Criminal Procedure Code of Ukraine pertaining to international cooperation in a criminal proceeding, taking into account critical feedback provided in MONEYVAL reports, in the Parliament of Ukraine (particularly if the President of Ukraine vetoes the draft law) | 01.03.2023 | 01.01.1970 | Ministry of Justice of Ukraine |  | state budget | within the established budget allocations for the relevant year | The law has been signed by the President of Ukraine. | Проект Закону України «Про внесення змін до Кримінального процесуального кодексу України та інших законодавчих актів України щодо міжнародного співробітництва під час кримінального провадження» внесено Кабінетом Міністрів України на розгляд Верховної Ради України 15.09.2022 (р.н. 8038). 21.07.2023 законопроект розглянуто на Комітеті Верховної Ради України з питань правоохоронної діяльності. За результатами розгляду Комітет ухвалив рішення рекомендувати Верховній Раді України повернути законопроект суб'єкту права законодавчої ініціативи на доопрацювання. Міністерство юстиції України розробило законопроект «Про внесення змін до Кримінального процесуального кодексу України та інших законодавчих актів України щодо міжнародного співробітництва під час кримінального провадження», який є доопрацьованою версією законопроекту від 15.09.2022 № 8038. 18.03.2024 доопрацьований законопроект у встановленому законом порядку внесено на розгляд Кабінету Міністрів України. 25.04.2024 Урядовим комітетом з питань економічної, фінансової і правової політики, паливно-енергетичного комплексу, стратегічних галузей промисловості та правоохоронної діяльності було вирішено подати відповідний законопроект для розгляду на засідання Кабінету Міністрів України у запропонованій редакції. 26.04.2024 законопроект схвалено за результатами засідання Уряду та у встановленому законом порядку внесено до Верховної Ради України. 29.04.2024 відповідна законодавча ініціатива була зареєстрована у Верховній Раді України за № 11223. Головним комітетом визначено Комітет Верховної Ради України з питань правоохоронної діяльності. 17.07.2025 законопроект реєстр. № 11223 від 29.04.2024 знято з розгляду (відкликано відповідно до ч. 3 ст. 105 Закону України «Про Регламент Верховної Ради України» у зв'язку з припиненням повноважень Кабінету Міністрів України). З метою підготовки до повторного ініціювання внесення відповідних змін та для забезпечення оптимізації законодавчого процесу Міністерство юстиції України об’єднало зміни, що пропонувалися вищезазначеним законопроектом та проектом Закону України «Про внесення змін до Кримінального процесуального кодексу України щодо використання технічних засобів електронних комунікацій при надісланні запитів про міжнародне співробітництво» (реєстр. № 12140 від 21.10.2024). 10.12.2025 законопроект схвалено за результатами засідання Уряду, а 11.12.2025 законопроект зареєстровано у Верховній Раді України за номером 14292. Міністерство юстиції України повідомляє, що відповідний законопроект 06.02.2026 розглянуто Комітетом Верховної Ради України з питань інтеграції України до ЄС (висновок: не суперечить міжнародно-правовим зобов’язанням України у сфері європейської інтеграції); 19.02.2026 отримано висновок Комітету Верховної Ради України з питань бюджету; 11.03.2026 отримано висновок Головного науково-експертного управління Апарату Верховної Ради України. З огляду на обсяг вжитих дій Міністерством юстиції України, спрямованих на супроводження розгляду проекту закону, яким уточнюються положення Кримінального процесуального кодексу України щодо міжнародного співробітництва у кримінальному провадженні, водночас у зв’язку з недосягненням показника (індикатора) виконання (закон не прийнято і не підписано Президентом України), відповідний захід не може вважатись таким, що виконаний повністю. | Partially implemented | 0.0
3.3 | Criminal liability | 3.3.3 The legislation governing the activity of the ARMA contains numerous gaps and corruption risks. Low effectiveness of the processes of transferring assets to ARMA for management to preserve their economic value, as well as the processes of combating and preventing money laundering | 3.3.3.11 | Measures to prevent the laundering of money obtained through corruption are determined based on the results of risk assessment and are duly implemented. FATF recommendations are being consistently implemented | 3.3.3.11.4 (1) | Aligning bylaws with the Laws of Ukraine dated December 6, 2019, No. 361-IX On Preventing and Combating the Laundering of Proceeds of Crime, Financing of Terrorism, and Financing of Proliferation of Weapons of Mass Destruction, dated November 4, 2022, No. 2736-IX On Amendments to Select Laws of Ukraine Towards Protection of the Financial System of Ukraine Against Actions of the State Engaging in Armed Aggression Against Ukraine, and Adaptation of Ukrainian Legislation to Specific Standards of the Financial Action Task Force and the Requirements of EU Directive 2018/843, and EU Directive 2015/849 | 01.03.2023 | 31.12.2023 | Ministry of Finance of Ukraine |  | state budget | within the established budget allocations for the relevant year | The bylaw normative legal acts have been aligned with said laws and EU Directive 2015/849. | According to the information provided by the Ministry of Finance of Ukraine, the following normative legal acts have been adopted, directly or indirectly aimed at implementing the above measure: - Resolution of the Government and the National Bank of Ukraine dated September 19, 2023 No. 1011 On Approval of the Methodology for Determining the Ultimate Beneficial Owner by a Legal Entity; - Resolution of the Government dated June 16, 2023 No. 662 On Approval of the Procedure for Supervision in the Area of Preventing and Combating the Laundering of Proceeds of Crime, Financing of Terrorism, and Financing of Proliferation of Weapons of Mass Destruction over the Activities of Primary Financial Monitoring Entities, State Regulation and Supervision of which is carried out by the Ministry of Finance, the Ministry of Justice, the Ministry of Digital Transformation, dated June 13, 2023 No. 602 On Approval of the Procedure for Forming the List of Foreign Stock Exchanges (Regulated Markets) Subject to the Requirements for Disclosure of Information on Ultimate Beneficial Owners, dated February 14, 2023 No. 130 On Amendments to the Regulation on the Ministry of Finance of Ukraine; - decree of the Government dated December 27, 2023 No. 1207-r On Approval of the Action Plan Aimed at Preventing and/or Mitigating the Negative Consequences of Risks Identified by the Third National Risk Assessment in the Area of Preventing and Combating the Laundering of Proceeds of Crime, Financing of Terrorism, and Financing of Proliferation of Weapons of Mass Destruction for the Period up to 2026; - orders of the Ministry of Finance of Ukraine dated December 28, No. 465 On Approval of the Criteria for the Risks of the Laundering of Proceeds of Crime, Financing of Terrorism, and Financing of Proliferation of Weapons of Mass Destruction, registered with the Ministry of Justice of Ukraine on February 09, 2022 under No. 258/39314, dated December 09, 2022 No. 422 named Some Issues of Formation of Administrative Reporting by the Ministry of Finance of Ukraine as a State Financial Monitoring Entity in the Area of Preventing and Combating the Laundering of Proceeds of Crime, Financing of Terrorism, and Financing of Proliferation of Weapons of Mass Destruction, registered with the Ministry of Justice on December 22, 2022 under No. 1664/39000. | Implemented | 0.0
3.3 | Criminal liability | 3.3.3 The legislation governing the activity of the ARMA contains numerous gaps and corruption risks. Low effectiveness of the processes of transferring assets to ARMA for management to preserve their economic value, as well as the processes of combating and preventing money laundering | 3.3.3.11 | Measures to prevent the laundering of money obtained through corruption are determined based on the results of risk assessment and are duly implemented. FATF recommendations are being consistently implemented | 3.3.3.11.4 (2) | Aligning bylaws with the Laws of Ukraine dated December 6, 2019, No. 361-IX On Preventing and Combating the Laundering of Proceeds of Crime, Financing of Terrorism, and Financing of Proliferation of Weapons of Mass Destruction, dated November 4, 2022, No. 2736-IX On Amendments to Select Laws of Ukraine Towards Protection of the Financial System of Ukraine Against Actions of the State Engaging in Armed Aggression Against Ukraine, and Adaptation of Ukrainian Legislation to Specific Standards of the Financial Action Task Force and the Requirements of EU Directive 2018/843, and EU Directive 2015/849 | 01.03.2023 | 31.12.2023 | National Commission on Securities and Stock Market |  | state budget | within the established budget allocations for the relevant year | The bylaw normative legal acts have been aligned with said laws and EU Directive 2015/849. | According to the information provided by the National Commission on Securities and Stock Market, the bylaws of the National Commission on Securities and Stock Market have been aligned with the Laws of Ukraine dated December 6, 2019, No. 361-IX On Preventing and Combating the Laundering of Proceeds of Crime, Financing of Terrorism, and Financing of Proliferation of Weapons of Mass Destruction, dated November 4, 2022 No. 2736-IX On Amendments to Certain Laws of Ukraine Regarding the Protection of the Financial System of Ukraine from the Actions of the State Conducting Armed Aggression against Ukraine and Adaptation of Ukrainian Legislation to Certain Standards of the Financial Action Task Force on Money Laundering (FATF) and Requirements of EU Directive 2018/843 and EU Directive 2015/849. | Implemented | 0.0
3.3 | Criminal liability | 3.3.3 The legislation governing the activity of the ARMA contains numerous gaps and corruption risks. Low effectiveness of the processes of transferring assets to ARMA for management to preserve their economic value, as well as the processes of combating and preventing money laundering | 3.3.3.11 | Measures to prevent the laundering of money obtained through corruption are determined based on the results of risk assessment and are duly implemented. FATF recommendations are being consistently implemented | 3.3.3.11.4 (3) | Aligning bylaws with the Laws of Ukraine dated December 6, 2019, No. 361-IX On Preventing and Combating the Laundering of Proceeds of Crime, Financing of Terrorism, and Financing of Proliferation of Weapons of Mass Destruction, dated November 4, 2022, No. 2736-IX On Amendments to Select Laws of Ukraine Towards Protection of the Financial System of Ukraine Against Actions of the State Engaging in Armed Aggression Against Ukraine, and Adaptation of Ukrainian Legislation to Specific Standards of the Financial Action Task Force and the Requirements of EU Directive 2018/843, and EU Directive 2015/849 | 01.03.2023 | 31.12.2023 | State Financial Monitoring Service of Ukraine |  | state budget | within the established budget allocations for the relevant year | The bylaw normative legal acts have been aligned with said laws and EU Directive 2015/849. | The State Financial Monitoring Service of Ukraine (hereinafter referred to as the SFMSU) in accordance with the Regulation on the State Financial Monitoring Service of Ukraine approved by the Cabinet of Ministers of Ukraine dated July 29, 2015 No. 537 (hereinafter referred to as the Regulation) has no authority to develop its own regulations. However, in accordance with subclause 9 of clause 4 of the Regulation, the SFMSU, in accordance with its tasks, approves in the prescribed manner draft normative legal acts of the state financial monitoring entities on preventing and combating the laundering of proceeds of crime, financing of terrorism, and financing of proliferation of weapons of mass destruction. According to the information provided by the SFMSU, two draft Resolutions of the Cabinet of Ministers of Ukraine aimed at aligning the bylaws with the Laws of Ukraine dated December 6, 2019 No. 361-IX and November 4, 2022 No. 2736-IX were processed, namely - On Approval of the Procedure of Oversight in the Area of Preventing and Combating the Laundering of Proceeds of Crime, Financing of Terrorism, and Financing of Proliferation of Weapons of Mass Destruction of the Activities of Primary Financial Monitoring Entities, State Regulation and Oversight of Which is Carried Out by the Ministry of Finance of Ukraine, the Ministry of Justice of Ukraine, and the Ministry of Digital Transformation of Ukraine (developed by the Ministry of Finance of Ukraine). - On Approval of Evidentiary Standards of Reasonable Suspicion for Inclusion/Exclusion to/from the UN Security Council Sanctions Lists, Foreign States' Sanctions Lists and the List of Persons Associated with Terrorist Activities or Subject to International Sanctions (developed by the Ministry of Justice of Ukraine). Taking into account the above, the status of "implemented " was assigned due to the achievement of the indicator of the measure. | Implemented | 0.0
3.3 | Criminal liability | 3.3.3 The legislation governing the activity of the ARMA contains numerous gaps and corruption risks. Low effectiveness of the processes of transferring assets to ARMA for management to preserve their economic value, as well as the processes of combating and preventing money laundering | 3.3.3.11 | Measures to prevent the laundering of money obtained through corruption are determined based on the results of risk assessment and are duly implemented. FATF recommendations are being consistently implemented | 3.3.3.11.4 (4) | Aligning bylaws with the Laws of Ukraine dated December 6, 2019, No. 361-IX On Preventing and Combating the Laundering of Proceeds of Crime, Financing of Terrorism, and Financing of Proliferation of Weapons of Mass Destruction, dated November 4, 2022, No. 2736-IX On Amendments to Select Laws of Ukraine Towards Protection of the Financial System of Ukraine Against Actions of the State Engaging in Armed Aggression Against Ukraine, and Adaptation of Ukrainian Legislation to Specific Standards of the Financial Action Task Force and the Requirements of EU Directive 2018/843, and EU Directive 2015/849 | 01.03.2023 | 31.12.2023 | National Bank of Ukraine |  | state budget | within the established budget allocations for the relevant year | The bylaw normative legal acts have been aligned with said laws and EU Directive 2015/849. | According to the information provided by the National Bank of Ukraine, in order to align the bylaws with the Laws of Ukraine dated December 06, 2019 No. 361-IX, dated November 04, 2022 No. 2736-IX and EU Directive 2015/849 (hereinafter referred to as the anti-money laundering area), the following normative legal acts were adopted: - Resolution of the Board of the National Bank of Ukraine dated June 15, 2023 No. 74 On Amendments to the Regulation on Financial Monitoring by Banks approved amendments that require banks to use a risk-based approach when servicing politically exposed persons; - Resolution of the Board of the National Bank of Ukraine dated June 21, 2023 No. 80 On Approval of Amendments to the Regulation on the Application of Enforcement Measures by the National Bank of Ukraine updated the approaches to imposing fines on banks for violations in the area of anti-money laundering and currency legislation; - Resolution of the Board of the National Bank of Ukraine dated September 5, 2023 No. 108 On Amendments to the Regulation on Financial Monitoring by Institutions and Invalidation of Resolution of the Board of the National Bank of Ukraine dated December 17, 2021 No. 145 approved amendments that require institutions to use a risk-based approach when servicing politically exposed persons; - Resolution of the Board of the National Bank of Ukraine dated September 05, 2023, No. 110 On Amendments to the Regulation on Financial Monitoring by Banks approved new requirements for financial monitoring by banks; - Resolution of the Board of the National Bank of Ukraine dated December 29, 2023, No. 198 On Approval of Amendments to Certain Normative Legal Acts of the National Bank of Ukraine on Financial Monitoring, in order to implement the requirements of the Law of Ukraine dated October 17, 2023, No. 3419-IX, introduced relevant amendments to the Regulation on Financial Monitoring by Banks, approved by the Resolution of the Board of the National Bank of Ukraine dated May 19, 2020, No. 65, and to the Regulation on Financial Monitoring by Institutions, approved by Resolution of the Board of the National Bank of Ukraine dated July 28, 2020, No. 107. | Implemented | 0.0
3.3 | Criminal liability | 3.3.3 The legislation governing the activity of the ARMA contains numerous gaps and corruption risks. Low effectiveness of the processes of transferring assets to ARMA for management to preserve their economic value, as well as the processes of combating and preventing money laundering | 3.3.3.11 | Measures to prevent the laundering of money obtained through corruption are determined based on the results of risk assessment and are duly implemented. FATF recommendations are being consistently implemented | 3.3.3.11.4 (5) | Aligning bylaws with the Laws of Ukraine dated December 6, 2019, No. 361-IX On Preventing and Combating the Laundering of Proceeds of Crime, Financing of Terrorism, and Financing of Proliferation of Weapons of Mass Destruction, dated November 4, 2022, No. 2736-IX On Amendments to Select Laws of Ukraine Towards Protection of the Financial System of Ukraine Against Actions of the State Engaging in Armed Aggression Against Ukraine, and Adaptation of Ukrainian Legislation to Specific Standards of the Financial Action Task Force and the Requirements of EU Directive 2018/843, and EU Directive 2015/849 | 01.03.2023 | 31.12.2023 | Ministry of Justice of Ukraine |  | state budget | within the established budget allocations for the relevant year | The bylaw normative legal acts have been aligned with said laws and EU Directive 2015/849. | In order to implement this measure, the order of the Ministry of Justice of Ukraine dated December 29, 2023 No. 4501/5 On Amendments to Certain Normative Legal Acts of the Ministry of Justice of Ukraine was adopted, registered with the Ministry of Justice of Ukraine on January 2, 2024 No. 4/41349. | Implemented | 0.0
3.3 | Criminal liability | 3.3.3 The legislation governing the activity of the ARMA contains numerous gaps and corruption risks. Low effectiveness of the processes of transferring assets to ARMA for management to preserve their economic value, as well as the processes of combating and preventing money laundering | 3.3.3.11 | Measures to prevent the laundering of money obtained through corruption are determined based on the results of risk assessment and are duly implemented. FATF recommendations are being consistently implemented | 3.3.3.11.4 (6) | Aligning bylaws with the Laws of Ukraine dated December 6, 2019, No. 361-IX On Preventing and Combating the Laundering of Proceeds of Crime, Financing of Terrorism, and Financing of Proliferation of Weapons of Mass Destruction, dated November 4, 2022, No. 2736-IX On Amendments to Select Laws of Ukraine Towards Protection of the Financial System of Ukraine Against Actions of the State Engaging in Armed Aggression Against Ukraine, and Adaptation of Ukrainian Legislation to Specific Standards of the Financial Action Task Force and the Requirements of EU Directive 2018/843, and EU Directive 2015/849 | 01.03.2023 | 31.12.2023 | Ministry of Digital Transformation of Ukraine |  | state budget | within the established budget allocations for the relevant year | The bylaw normative legal acts have been aligned with said laws and EU Directive 2015/849. | The bylaws of the Ministry of Digital Transformation of Ukraine do not need to be aligned with the laws mentioned in the measure. The status of "implemented" was assigned due to the achievement of the measure's performance indicator. | Implemented | 0.0
3.3 | Criminal liability | 3.3.3 The legislation governing the activity of the ARMA contains numerous gaps and corruption risks. Low effectiveness of the processes of transferring assets to ARMA for management to preserve their economic value, as well as the processes of combating and preventing money laundering | 3.3.3.11 | Measures to prevent the laundering of money obtained through corruption are determined based on the results of risk assessment and are duly implemented. FATF recommendations are being consistently implemented | 3.3.3.11.5 | Preparing and submitting to the Cabinet of Ministers of Ukraine in the prescribed manner the consolidated proposals from participants of the national assessment of risks regarding the implementation of measures towards prevention and/or mitigation of adverse consequences of the risks identified | 01.03.2023 | 31.08.2023 | State Financial Monitoring Service of Ukraine |  | state budget | within the established budget allocations for the relevant year | The consolidated proposals have been submitted to the Cabinet of Ministers of Ukraine. | The draft decree of the Cabinet of Ministers of Ukraine On Approval of the Action Plan Aimed at Preventing and/or Mitigating the Negative Consequences of Risks Identified by the Third Round of the National Risk Assessment in the Area of Preventing and Combating the Laundering of Proceeds of Crime, Financing of Terrorism, and Financing of Proliferation of Weapons of Mass Destruction for the Period up to 2026 was agreed with the concerned authorities, the opinion of the Ministry of Justice of Ukraine was received, and by letter dated November 3, 2023 No. 26120-02-3/30140 the draft decree was sent to the Cabinet of Ministers of Ukraine for review. | Implemented | 0.0
3.3 | Criminal liability | 3.3.3 The legislation governing the activity of the ARMA contains numerous gaps and corruption risks. Low effectiveness of the processes of transferring assets to ARMA for management to preserve their economic value, as well as the processes of combating and preventing money laundering | 3.3.3.11 | Measures to prevent the laundering of money obtained through corruption are determined based on the results of risk assessment and are duly implemented. FATF recommendations are being consistently implemented | 3.3.3.11.6 | Approving the consolidated proposals from participants of the national assessment of risks regarding the implementation of measures towards prevention and/or mitigation of adverse consequences of the risks identified | 01.08.2023 | 30.09.2023 | State Financial Monitoring Service of Ukraine |  | state budget | within the established budget allocations for the relevant year | The consolidated proposals have been approved by the Cabinet of Ministers of Ukraine. | On December 27, 2023, the Cabinet of Ministers of Ukraine approved the Resolution No. 1207-r On Approval of the Action Plan Aimed at Preventing and/or Mitigating the Negative Consequences of Risks Identified by the Third Round of the National Risk Assessment in the Area of Preventing and Combating the Laundering of Proceeds of Crime, Financing of Terrorism, and Financing of Proliferation of Weapons of Mass Destruction for the Period up to 2026 (the Action Plan). The Action Plan was developed by the State Financial Monitoring Service of Ukraine jointly with the Ministry of Finance of Ukraine and other concerned state authorities based on the results of the third National Risk Assessment in the Area Preventing and Combating the Laundering of Proceeds of Crime, Financing of Terrorism, and Financing of Proliferation of Weapons of Mass Destruction. The Action Plan contains a set of institutional, legislative, organizational, and practical measures to improve the national system of preventing and combating money laundering in accordance with international standards and the system of strategic planning in this area, aimed at - effective risk management in preventing and combating money laundering system; - effective formation and implementation of state policy in the area of preventing and combating money laundering in accordance with international standards; - aligning the national system of preventing and combating money laundering with international standards; - improvement of information technologies, effective cooperation and information exchange between government agencies, as well as with the competent authorities of foreign countries and international organizations in this area; - ongoing methodological support of the activities of the primary financial monitoring entities and providing feedback to them; - innovative solutions for professional development of specialists in the area of preventing and combating money laundering; - deepening cooperation with the private sector and the public. | Implemented | 0.0
3.3 | Criminal liability | 3.3.3 The legislation governing the activity of the ARMA contains numerous gaps and corruption risks. Low effectiveness of the processes of transferring assets to ARMA for management to preserve their economic value, as well as the processes of combating and preventing money laundering | 3.3.3.11 | Measures to prevent the laundering of money obtained through corruption are determined based on the results of risk assessment and are duly implemented. FATF recommendations are being consistently implemented | 3.3.3.11.7 | Preparing and conducting a scheduled national risk assessment in accordance with the Methodology of National Assessment of Risks of Money Laundering and Financing of Terrorism in Ukraine | 01.01.2025 | 30.11.2025 | State Financial Monitoring Service of Ukraine | Council on Prevention and Counteraction to Legalization (Laundering) of the Proceeds of Crime or Terrorist Financing and Financing Proliferation of Weapons of Mass Destruction | state budget | within the established budget allocations for the relevant year | The report on the findings of the scheduled national risk assessment has been prepared. | Національна оцінка ризиків проводиться згідно з методикою національної оцінки ризиків відмивання коштів та фінансування тероризму в Україні (далі – методика), підготовленою Державною службою фінансового моніторингу України (далі - Держфінмоніторинг), узгодженою з Міністерством фінансів України та схваленою Радою з питань запобігання та протидії легалізації (відмиванню) доходів, одержаних злочинним шляхом, фінансуванню тероризму та фінансуванню розповсюдження зброї масового знищення (далі – Рада) на її черговому засіданні (див. п. 9 Порядку, затвердженого постановою Кабінету Міністрів України від 05.08.2020 № 690). За інформацією, наданою Держфінмоніторингом, 26.12.2024 на черговому засіданні Ради, було схвалено оновлену Методику. Відповідно до п. 4.3 Протоколу засідання Ради № 2(18) від 26.12.2024 учасники національної оцінки ризиків (далі – НОР), визначили та надали Держфінмоніторингу інформацію про особу на рівні заступника керівника органу (або керівника самостійного структурного підрозділу), відповідальну за взаємодію з Держфінмоніторингом з питань проведення НОР. Держфінмоніторинг інформує, що з метою підготовки та проведення НОР організовано проведення 28.02.2025 засідання Робочої групи з питань проведення НОР за участю представників центральних органів виконавчої влади, інших державних органів, відповідальних за взаємодію з Держфінмоніторингом з питань проведення НОР. Держфінмоніторинг зазначає, що 28.02.2025 на засіданні Робочої групи з питань проведення НОР розглянуто та схвалено Орієнтовний план проведення НОР та обговорено міру (ступінь) залученості кожного учасника НОР до зазначеного процесу. Держфінмоніторинг інформував, що 09.04.2025 забезпечено проведення засідання Робочої підгрупи з питань оцінки ризиків використання неприбуткового сектору з метою відмивання коштів (ВК) та фінансування тероризму (ФТ). Участь у засіданні взяли представники Держфінмоніторингу, Міністерства фінансів України, Національного банку України, Міністерства юстиції України, Національної комісії з цінних паперів та фондового ринку, Державної податкової служби України, Офісу Генерального прокурора, представники неприбуткового сектору. За результатами засідання: - обговорено та схвалено Перелік типів НПО, які будуть включені в оцінку ризиків використання неприбуткових організацій (НПО) з метою ВК/ФТ; - обговорено необхідність уточнення механізму оцінки ризиків використання неприбуткового сектору з метою ВК/ФТ, визначеного оновленою у 2024 році Методикою НОР; - обговорено подальші кроки, спрямовані для визначення та оцінку ризиків ВК/ФТ, на які наражаються представники різних типів НПО. Під час звітування за 3 квартал 2025 року Держфінмоніторинг повідомляв, що здійснювалось узагальнення ризиків за результатами проведення НОР з урахуванням професійних суджень представників центральних органів виконавчої влади, інших державних органів, відповідальних за взаємодію з Держфінмоніторингом з питань проведення НОР. Держфінмоніторинг повідомляє, що листом від 18.11.2025 року № 5302/310-04 направив проект Звіту про проведення НОР учасникам на узгодження. 10.12.2025 проект Звіту про проведення НОР було направлено Міністерству фінансів України на погодження. Листом № 53020-08-5/37309 від 18.12.2025 року Міністерство фінансів України повідомило про не погодження проекту Звіту та надало відповідні зауваження та рекомендації. Держфінмоніторинг інформує, що у зв’язку з тим, що для усунення окремих зауважень і врахування відповідних рекомендацій потрібна додаткова інформація від інших учасників, що беруть участь у роботі системи запобігання та протидії легалізації (відмиванню) доходів, одержаних злочинним шляхом, фінансуванню тероризму та фінансуванню розповсюдження зброї масового знищення, було надіслано відповідні запити. Держфінмоніторинг повідомляє, що збір та аналіз такої інформації зумовив затримку в підготовці проекту Звіту про проведення НОР. Окремо Держфінмоніторинг зазначає, що проект Звіту про проведення НОР в листопаді 2025 року був обговорений з представниками Ради Європи і Європейської Комісії (DG ENEST) та отримані відповідні відгуки (Review of Ukraine’s Draft National Risk Assessment 2025 against the revised FATF NRA Guidance and Toolkit), в яких був наданий в цілому позитивний відгук на проект Звіту про проведення НОР. Держфінмоніторинг також інформує, що 05.03.2026 відбулось засідання Робочої підгрупи з питань оцінки ризиків використання неприбуткового сектору з метою ВК/ФТ щодо обговорення та схвалення єдиної позиції щодо ризиків використання неприбуткового сектору. Листом Міністерства фінансів України від 08.07.2026 № 53020-08-5/19162 повідомлено про надання Держфінмоніторингу суттєвих зауважень до проєкту звіту про проведення НОР. У відповідному листі також зазначається, що до Міністерства фінансів України доопрацьований проєкт звіту станом на 07.07.2026 на погодження не надходив. З огляду на те, що показник (індикатор) виконання відповідного заходу не досягнуто (звіт за результатами чергової національної оцінки ризиків не підготовлено), такий захід не може вважатись виконаним. | Not implemented | 0.0
3.3 | Criminal liability | 3.3.3 The legislation governing the activity of the ARMA contains numerous gaps and corruption risks. Low effectiveness of the processes of transferring assets to ARMA for management to preserve their economic value, as well as the processes of combating and preventing money laundering | 3.3.3.11 | Measures to prevent the laundering of money obtained through corruption are determined based on the results of risk assessment and are duly implemented. FATF recommendations are being consistently implemented | 3.3.3.11.8 | Approving the report of the scheduled national assessment of risks of money laundering and financing of terrorism in Ukraine | 01.12.2025 | 31.12.2025 | Council on Prevention and Counteraction to Legalization (Laundering) of the Proceeds of Crime or Terrorist Financing and Financing Proliferation of Weapons of Mass Destruction | State Financial Monitoring Service of Ukraine | state budget | within the established budget allocations for the relevant year | The report on the findings of the scheduled national risk assessment has been approved and at least the report conclusions have been made public. | За інформацією, наданою Міністерством фінансів України у листі від 08.07.2026 № 53020-08-5/19162, триває підготовка звіту за результатами чергової національної оцінки ризиків відмивання коштів та фінансування тероризму в Україні. У відповідному листі також зазначається, що Міністерство фінансів України надало Держфінмоніторингу суттєві зауваження до проєкту звіту про проведення національної оцінки ризиків відмивання коштів та фінансування тероризму в Україні. Також повідомлено про те, що до Міністерства фінансів України доопрацьований проєкт звіту станом на 07.07.2026 на погодження не надходив. З огляду на те, що звіт за результатами чергової національної оцінки ризиків не затверджено та не оприлюднено, відповідний захід вважається не виконаним. | Not implemented | 0.0