## Заходи
№ Напрямку | Напрямок | Проблема | № ОСР | Назва ОСР | № Заходу | Назва заходу | Дата початку | Дата завершення | Головний виконавець | Співвиконавці | Джерела фінансування | Обсяги фінансування, тис.грн. | Показник (індикатор) виконання | Стан виконання | Статус виконання | Оцінка досягнення ОСР
1.2 | Instilling a negative attitude towards corruption | 1.2.1 Everyday corrupt practices are an established norm of conduct and are not perceived as violations of moral or legal norms. There is no consistent demand from the population for public officials to uphold the prescribed rules of ethical conduct and integrity | 1.2.1.1 | The overall level of tolerance of corruption in Ukraine has decreased owing to the integration of anticorruption topics into educational curricula at all levels, which includes instilling in society a stable perception of corruption as a phenomenon that significantly slows down the socioeconomic development of the country, of corrupt officials as persons who make public administration ineffective, and the realization that dishonest practices, even when they look like a convenient opportunity to solve their issues in the short term, are always disadvantageous for individuals and society in the medium and long term | 1.2.1.1.1 | Supplementing the State Standard of Vocational Secondary Education: a) with a list of value orientations aimed at instilling intolerance of corruption and manifestations of dishonesty; b) with a list of tasks essential to acquiring civic and social competencies as part of instilling intolerance of corruption in all of its manifestations, an understanding of the inadmissibility of tolerating inequality and dishonesty, as well as the readiness to abandon unscrupulous practices when solving problems | 01.03.2023 | 31.12.2023 | Ministry of Education and Science of Ukraine |  | state budget | within the established budget allocations for the relevant year | The state standard has been supplemented with value orientations aimed at instilling intolerance of corruption and manifestations of dishonesty, as well as tasks essential to acquiring civic and social competencies as part of instilling intolerance of corruption in all of its manifestations. | За повідомленням Міністерства освіти і науки України, станом на 30.09.2024 р. Державний стандарт профільної середньої освіти затверджено постановою КМУ від 25 липня 2024 р. № 851 "Про затвердження Державного стандарту профільної середньої освіти" https://www.kmu.gov.ua/npas/pro-zatverdzhennia-derzhavnoho-standartu-profilnoi-serednoi-osvity-851-250724 | Implemented | 0.0
1.2 | Instilling a negative attitude towards corruption | 1.2.1 Everyday corrupt practices are an established norm of conduct and are not perceived as violations of moral or legal norms. There is no consistent demand from the population for public officials to uphold the prescribed rules of ethical conduct and integrity | 1.2.1.1 | The overall level of tolerance of corruption in Ukraine has decreased owing to the integration of anticorruption topics into educational curricula at all levels, which includes instilling in society a stable perception of corruption as a phenomenon that significantly slows down the socioeconomic development of the country, of corrupt officials as persons who make public administration ineffective, and the realization that dishonest practices, even when they look like a convenient opportunity to solve their issues in the short term, are always disadvantageous for individuals and society in the medium and long term | 1.2.1.1.2 | Supplementing the objective of the “Civic Accountability” cross-cutting content thread with concepts essential to instilling intolerance of corruption and adherence to integrity strategies | 01.03.2023 | 31.12.2023 | Ministry of Education and Science of Ukraine | State Scientific Institution “Institute of Education Content Modernization” | state budget | within the established budget allocations for the relevant year | Amendments have been introduced into the Model Curriculum of General Secondary Education Institutions of the 2nd Degree, approved by the order of the Ministry of Education and Science dated April 20, 2018, No. 405 | The order of the Ministry of Education and Science of Ukraine On Amendments to Certain Orders of the Ministry of Education and Science of Ukraine dated February 07, 2024 No. 142 amended the Model Educational Program of General Secondary Education Institutions of the Secondary Level approved by the order of the Ministry of Education and Science of Ukraine dated April 20, 2018 No. 405 (as amended) regarding the content line "Civic Accountability", which includes provisions on the instilling intolerance of corruption and adherence to integrity strategies, the establishment of a culture of integrity and respect for the rule of law, prevention of corruption and corruption-related offences. | Implemented | 0.0
1.2 | Instilling a negative attitude towards corruption | 1.2.1 Everyday corrupt practices are an established norm of conduct and are not perceived as violations of moral or legal norms. There is no consistent demand from the population for public officials to uphold the prescribed rules of ethical conduct and integrity | 1.2.1.1 | The overall level of tolerance of corruption in Ukraine has decreased owing to the integration of anticorruption topics into educational curricula at all levels, which includes instilling in society a stable perception of corruption as a phenomenon that significantly slows down the socioeconomic development of the country, of corrupt officials as persons who make public administration ineffective, and the realization that dishonest practices, even when they look like a convenient opportunity to solve their issues in the short term, are always disadvantageous for individuals and society in the medium and long term | 1.2.1.1.3 | Developing educational and methodological materials to be used to accomplish the objective of the “Civic Accountability” cross-cutting content thread in terms of instilling in the context of corruption and adherence to integrity strategies (with the possible involvement of NGOs and international technical assistance projects in this activity) | 01.03.2023 | 31.01.2024 | National Agency on Corruption Prevention |  | state budget and/or international technical assistance funds | within the established budget allocations for the relevant year | The teaching methods materials have been developed. | According to the National Agency on Corruption Prevention, as of March 31, 2024, "a complex of exercises that teachers can use in the educational process has been prepared. Comprehensive work was carried out to disseminate the developed materials". | Implemented | 0.0
1.2 | Instilling a negative attitude towards corruption | 1.2.1 Everyday corrupt practices are an established norm of conduct and are not perceived as violations of moral or legal norms. There is no consistent demand from the population for public officials to uphold the prescribed rules of ethical conduct and integrity | 1.2.1.1 | The overall level of tolerance of corruption in Ukraine has decreased owing to the integration of anticorruption topics into educational curricula at all levels, which includes instilling in society a stable perception of corruption as a phenomenon that significantly slows down the socioeconomic development of the country, of corrupt officials as persons who make public administration ineffective, and the realization that dishonest practices, even when they look like a convenient opportunity to solve their issues in the short term, are always disadvantageous for individuals and society in the medium and long term | 1.2.1.1.4 | Submitting documents to obtain the stamp of approval for use in the educational process for the educational and methodological handbook on instilling intolerance of corruption and adherence to integrity strategies | 01.02.2024 | 30.06.2024 | National Agency on Corruption Prevention | Ministry of Education and Science of Ukraine | state budget and/or international technical assistance funds | within the established budget allocations for the relevant year and/or international technical assistance funds | The educational and methodological handbook have passed expert examination. The expert committee has reviewed the expert opinions on the feasibility of using the handbook in the educational process. | Навчально-методичний посібник «PRO доброчесність» із рекомендаціями щодо досягнення мети наскрізної змістової лінії «Громадянська відповідальність» в частині формування нетерпимості до корупції та слідуванням доброчесних стратегій поведінки пройшов експертизу та отримав гриф «Схвалено до використання в освітньому процесі» (рішення експертної комісії з громадянської та історичної освітньої галузі від 08.07.2025 (протокол № 9), зареєстрований в Каталозі надання грифів навчальній літературі та навчальним програмам за № БО-0226-25). | Implemented | 0.0
1.2 | Instilling a negative attitude towards corruption | 1.2.1 Everyday corrupt practices are an established norm of conduct and are not perceived as violations of moral or legal norms. There is no consistent demand from the population for public officials to uphold the prescribed rules of ethical conduct and integrity | 1.2.1.1 | The overall level of tolerance of corruption in Ukraine has decreased owing to the integration of anticorruption topics into educational curricula at all levels, which includes instilling in society a stable perception of corruption as a phenomenon that significantly slows down the socioeconomic development of the country, of corrupt officials as persons who make public administration ineffective, and the realization that dishonest practices, even when they look like a convenient opportunity to solve their issues in the short term, are always disadvantageous for individuals and society in the medium and long term | 1.2.1.1.5 | Developing recommendations on the implementation of the “Civic Accountability” cross-cutting content thread in the educational process to the extent of instilling intolerance of corruption and adherence to integrity strategies | 01.07.2024 | 30.09.2024 | Ministry of Education and Science of Ukraine | National Agency on Corruption Prevention | state budget | within the established budget allocations for the relevant year | The recommendation has been communicated to institutions of general secondary education and vocational secondary education. | За повідомленням Міністерства освіти і науки України, станом на 30.09.2024 р. "в інструктивно-методичних рекомендаціях щодо викладання навчальних предметів / інтегрованих курсів у закладах загальної середньої освіти у 2024/2025 навчальному році до розділу «Громадянська та історична освітня галузь» включено необхідність висвітлення в освітньому процесі питань з формування нетерпимості до корупції та слідування доброчесним стратегіям поведінки, які надіслано листом МОН від 30.08.2024 № 1.1/15776-24 до департаментів (управлінь) освіти і науки обласних, Київської міської (військових) державних адміністрацій, закладів післядипломної педагогічної та загальної середньої освіти". | Implemented | 0.0
1.2 | Instilling a negative attitude towards corruption | 1.2.1 Everyday corrupt practices are an established norm of conduct and are not perceived as violations of moral or legal norms. There is no consistent demand from the population for public officials to uphold the prescribed rules of ethical conduct and integrity | 1.2.1.1 | The overall level of tolerance of corruption in Ukraine has decreased owing to the integration of anticorruption topics into educational curricula at all levels, which includes instilling in society a stable perception of corruption as a phenomenon that significantly slows down the socioeconomic development of the country, of corrupt officials as persons who make public administration ineffective, and the realization that dishonest practices, even when they look like a convenient opportunity to solve their issues in the short term, are always disadvantageous for individuals and society in the medium and long term | 1.2.1.1.6 | Developing the curriculum and the educational and methodological handbook of the optional course on the prevention of corruption and social integrity for the 9th grade (with the possible involvement of NGOs and international technical assistance projects in this activity) | 01.03.2023 | 30.06.2023 | National Agency on Corruption Prevention |  | state budget | within the established budget allocations for the relevant year | The curriculum and the educational and methodological handbook have been developed. | Навчально-методичний посібник курсу за вибором про запобігання корупції та суспільну доброчесність для 9 класів підготовлено, пропілотовано та поширено серед закладів загальної середньої освіти. Зовнішнім експертом розроблено навчальну програму для курсу за вибором «Протидія корупції», якій відповідає посібник «Антикорупційний курс для 9 класу» | Implemented | 0.0
1.2 | Instilling a negative attitude towards corruption | 1.2.1 Everyday corrupt practices are an established norm of conduct and are not perceived as violations of moral or legal norms. There is no consistent demand from the population for public officials to uphold the prescribed rules of ethical conduct and integrity | 1.2.1.1 | The overall level of tolerance of corruption in Ukraine has decreased owing to the integration of anticorruption topics into educational curricula at all levels, which includes instilling in society a stable perception of corruption as a phenomenon that significantly slows down the socioeconomic development of the country, of corrupt officials as persons who make public administration ineffective, and the realization that dishonest practices, even when they look like a convenient opportunity to solve their issues in the short term, are always disadvantageous for individuals and society in the medium and long term | 1.2.1.1.7 | Submitting documents to obtain the stamp of approval for use in the educational process for the curriculum and the educational and methodological handbook of the optional course on the prevention of corruption and social integrity for the 9th grade | 01.07.2023 | 30.09.2023 | National Agency on Corruption Prevention | Ministry of Education and Science of Ukraine | state budget and/or international technical assistance funds | within the established budget allocations for the relevant year and/or international technical assistance funds | The curriculum and the educational and methodological handbook have passed expert examination. The expert committee has reviewed the expert opinions on the feasibility of using it in the educational process. | Навчальна програма і навчально-методичний посібник пройшли експертизу. Рішенням експертної комісії з громадянської освіти та правознавства від 26.04.2024 (протокол № 3) навчально-методичному посібнику «Антикорупційний курс» для 9 класу закладів загальної середньої освіти (авт. колектив Офісу доброчесності НАЗК та ГО «ЕдКемп Україна» в межах проекту «Прозора школа») надано гриф «Схвалено для використання в освітньому процесі», який зареєстрований у Каталозі надання грифів навчальній літературі та навчальним програмам за № 3.0272-2024. Рішенням експертної комісії з громадянської та історичної освітньої галузі від 13.08.2025 (протокол № 10) навчальній програмі «Навчальна програма «Антикорупційний курс для 9 класу» надано гриф «Схвалено для використання в освітньому процесі», який зареєстрований у Каталозі надання грифів навчальній літературі та навчальним програмам за № БО - 0311-25. | Implemented | 0.0
1.2 | Instilling a negative attitude towards corruption | 1.2.1 Everyday corrupt practices are an established norm of conduct and are not perceived as violations of moral or legal norms. There is no consistent demand from the population for public officials to uphold the prescribed rules of ethical conduct and integrity | 1.2.1.1 | The overall level of tolerance of corruption in Ukraine has decreased owing to the integration of anticorruption topics into educational curricula at all levels, which includes instilling in society a stable perception of corruption as a phenomenon that significantly slows down the socioeconomic development of the country, of corrupt officials as persons who make public administration ineffective, and the realization that dishonest practices, even when they look like a convenient opportunity to solve their issues in the short term, are always disadvantageous for individuals and society in the medium and long term | 1.2.1.1.12 | Developing educational and methodological materials on anticorruption topics (anticorruption and integrity) for students pursuing professional (vocational) education, focusing on the development of cross-cutting civic and social competencies (with the possible involvement of NGOs and international technical assistance projects in this activity). | 01.01.2025 | 30.06.2025 | National Agency on Corruption Prevention |  | state budget | within the established budget allocations for the relevant year | The educational and methodological materials have been developed. | За інформацією наданою за попередні звітні періоди Управлінням просвітницької роботи та навчальних програм апарату Національного агентства з питань запобігання корупції, наказом Національного агентства з питань запобігання корупції (далі - Національне агентство) від 02.06.2025 №152/25 утворено робочу групу з розроблення навчально-методичних матеріалів з антикорупційної тематики (запобігання корупції та доброчесність) для здобувачів професійної (професійно-технічної) освіти в частині розвитку наскрізних громадянських та соціальних компетентностей. Підготовлено проект навчально-методичних матеріалів та передано на ознайомлення Голові Національного агентства (службова записка №120-06/5970-25 від 30.06.2025). За інформацією, наданою виконавцем у IV кварталі 2025 року, навчально-методичні матеріали фіналізовані та готові до апробації пілотними закладами професійної освіти та подальшого використання. Упродовж січня-лютого буде завершено верстку та дизайн посібника. Разом з тим, надані для ознайомлення матеріали містять окремі редакційні та технічні коментарі, що свідчить про перебування документа на стадії редакційного доопрацювання. Таким чином, зважаючи на ступінь відповідності фактично вжитих дій вимогам ДАП щодо змісту та способу виконання заходу, вважаємо за можливе констатувати, що захід є виконаним частково. | Partially implemented | 0.0
1.2 | Instilling a negative attitude towards corruption | 1.2.1 Everyday corrupt practices are an established norm of conduct and are not perceived as violations of moral or legal norms. There is no consistent demand from the population for public officials to uphold the prescribed rules of ethical conduct and integrity | 1.2.1.1 | The overall level of tolerance of corruption in Ukraine has decreased owing to the integration of anticorruption topics into educational curricula at all levels, which includes instilling in society a stable perception of corruption as a phenomenon that significantly slows down the socioeconomic development of the country, of corrupt officials as persons who make public administration ineffective, and the realization that dishonest practices, even when they look like a convenient opportunity to solve their issues in the short term, are always disadvantageous for individuals and society in the medium and long term | 1.2.1.1.13 | Designation by the Ministry of Education and Science of anticorruption topics (anticorruption and integrity) as a mandatory component of state standards of professional (vocation) education (as a separate educational component or a cross-cutting component within other components) | 01.04.2025 | 31.07.2025 | National Agency on Corruption Prevention | Ministry of Education and Science of Ukraine, State Scientific Institution “Institute of Education Content Modernization” | state budget and/or international technical assistance funds | within the established budget allocations for the relevant year and/or international technical assistance funds | The Ministry of Education and Science has designated anticorruption topics (anticorruption and integrity) as a mandatory component of state standards of professional (vocation) education (as a separate educational component or a cross-cutting component within other components). | За інформацією наданою за попередні звітні періоди Управлінням просвітницької роботи та навчальних програм апарату Національного агентства з питань запобігання корупції, з прийняттям Закону України «Про професійну освіту» (№ 4574-IX від 21.08.2025), який набрав чинності 12.09.2025 року, розпочалась робота по розробці нового Державного стандарту професійної освіти, у якому тематика запобігання корупції та доброчесності отримає системне закріплення як окремий освітній компонент або наскрізна лінія. Листом від 15.10.2025 № 137103003-25 Міністерство освіти і науки України повідомило НАЗК, що прийняття нового Закону України «Про професійну освіту» № 4574-IX започаткувало системне оновлення змісту професійної освіти. Одним із ключових нововведень є запровадження єдиного державного стандарту професійної освіти, який визначає спільні підходи до структури, змісту, результатів навчання та формування наскрізних компетентностей для всіх професійних кваліфікацій. Разом з тим, станом на кінець звітного періоду єдиний державний стандарт професійної освіти не затверджено, а отже відсутній нормативний акт, яким антикорупційну тематику визначено МОН як обов’язкову складову державних стандартів професійної (професійно-технічної) освіти. Також у державних стандартах професійної (професійно-технічної) освіти, затверджених до вересня 2025 року для окремих професій можна простежити антикорупційну тематику як обов’язкову складову освітнього процесу. Проте, це не свідчить про її системне визначення як обов’язкової складової державних стандартів у розумінні показника виконання заходу. Разом з тим, антикорупційна тематика інтегрується до: • освітніх програм, що реалізуються у закладах П(ПТ)О, з урахуванням можливості їх адаптації відповідно до типових та авторських навчальних планів; • навчальних предметів та модулів, зокрема: «Громадянська освіта», «Правознавство», «Основи трудового законодавства», «Охорона праці», «Етика ділових відносин» тощо. Також антикорупційна тематика реалізується в рамках виховної роботи, тренінгів, інтерактивних заходів у співпраці з представниками громадських організацій, проектів міжнародної технічної допомоги, НАЗК. Таким чином, зважаючи на ступінь відповідності фактично вжитих дій вимогам ДАП щодо змісту та способу виконання заходу, вважаємо, що захід є виконаним частково, оскільки станом на кінець звітного періоду єдиний державний стандарт професійної освіти не затверджено. | Partially implemented | 0.0
1.2 | Instilling a negative attitude towards corruption | 1.2.1 Everyday corrupt practices are an established norm of conduct and are not perceived as violations of moral or legal norms. There is no consistent demand from the population for public officials to uphold the prescribed rules of ethical conduct and integrity | 1.2.1.1 | The overall level of tolerance of corruption in Ukraine has decreased owing to the integration of anticorruption topics into educational curricula at all levels, which includes instilling in society a stable perception of corruption as a phenomenon that significantly slows down the socioeconomic development of the country, of corrupt officials as persons who make public administration ineffective, and the realization that dishonest practices, even when they look like a convenient opportunity to solve their issues in the short term, are always disadvantageous for individuals and society in the medium and long term | 1.2.1.1.14 | Updating the curricula of professional (vocational) education to incorporate the anticorruption topics (anticorruption and integrity) as a mandatory component (as a separate educational component or a cross-cutting component within other components). | 01.08.2025 | 31.10.2025 | Ministry of Education and Science of Ukraine | National Agency on Corruption Prevention | state budget | within the established budget allocations for the relevant year | Anticorruption topics have been incorporated into a separate educational component. | У зв’язку з набранням чинності 12.09.2025 Закону України «Про професійну освіту» від 21.08.2025 № 4574-IX розробляється єдиний стандарт професійної освіти. Єдиний стандарт професійної освіти визначить базові та наскрізні компетентності які інтегруються в освітніх програмах, та мають формуватися у кожного здобувача освіти. Новий єдиний стандарт професійної освіти створить можливість системно інтегрувати антикорупційну тематику в освітній процес та освітні програми. Після затвердження єдиного державного стандарту професійної освіти будуть розробляться та затверджуватись освітні прогами. Отже, виконання заходу буде можливе після остаточного виконання заходу 1.2.1.1.13. Враховуючи зазначене вище, а також зважаючи на те, що дата завершення строку виконання заходу вже настала, констатуємо, що захід не є виконаним. | Not implemented | 0.0
1.2 | Instilling a negative attitude towards corruption | 1.2.1 Everyday corrupt practices are an established norm of conduct and are not perceived as violations of moral or legal norms. There is no consistent demand from the population for public officials to uphold the prescribed rules of ethical conduct and integrity | 1.2.1.1 | The overall level of tolerance of corruption in Ukraine has decreased owing to the integration of anticorruption topics into educational curricula at all levels, which includes instilling in society a stable perception of corruption as a phenomenon that significantly slows down the socioeconomic development of the country, of corrupt officials as persons who make public administration ineffective, and the realization that dishonest practices, even when they look like a convenient opportunity to solve their issues in the short term, are always disadvantageous for individuals and society in the medium and long term | 1.2.1.1.15 | Developing educational and methodological materials on anticorruption topics (anticorruption, social and academic integrity) for first-year students pursuing a higher education (with the possible involvement of NGOs and international technical assistance projects in this activity) | 01.03.2023 | 31.10.2024 | National Agency on Corruption Prevention |  | state budget and/or international technical assistance funds | within the established budget allocations for the relevant year | The educational and methodological materials have been developed. | According to the National Agency on Corruption Prevention, as of March 31, 2024, teaching materials have been developed, and “piloting of the discipline in 10 Ukrainian higher education institutions has been completed. The discipline is already being extended to other Ukrainian higher education institutions.” | Implemented | 0.0
1.2 | Instilling a negative attitude towards corruption | 1.2.1 Everyday corrupt practices are an established norm of conduct and are not perceived as violations of moral or legal norms. There is no consistent demand from the population for public officials to uphold the prescribed rules of ethical conduct and integrity | 1.2.1.1 | The overall level of tolerance of corruption in Ukraine has decreased owing to the integration of anticorruption topics into educational curricula at all levels, which includes instilling in society a stable perception of corruption as a phenomenon that significantly slows down the socioeconomic development of the country, of corrupt officials as persons who make public administration ineffective, and the realization that dishonest practices, even when they look like a convenient opportunity to solve their issues in the short term, are always disadvantageous for individuals and society in the medium and long term | 1.2.1.1.16 | Developing amendments to the Procedural Recommendations on the Development of Standards of Higher Education, approved by the order of the Ministry of Education and Science dated June 1, 2016, No. 600, which would supplement the list of mandatory general competencies for the academic degree of a bachelor with the competency defined as intolerance of corruption in all of its manifestations, an understanding of the inadmissibility of tolerating inequality and dishonesty | 01.02.2024 | 30.04.2024 | Ministry of Education and Science of Ukraine | National Agency on Corruption Prevention | state budget | within the established budget allocations for the relevant year | The draft order amending the order of the Ministry of Education and Science has been developed. | Amendments to the Methodological Recommendations for the Development of Higher Education Standards, approved by the order of the Ministry of Education and Science of Ukraine dated June 1, 2016, No. 600, were developed and approved. The amendments include in the list of mandatory general competencies for the bachelor's degree the competence related to intolerance to corruption in all its manifestations, understanding the inadmissibility of tolerating inequality and dishonesty (Order of the Ministry of Education and Science of Ukraine dated April 3, 2024, No. 441). | Implemented | 0.0
1.2 | Instilling a negative attitude towards corruption | 1.2.1 Everyday corrupt practices are an established norm of conduct and are not perceived as violations of moral or legal norms. There is no consistent demand from the population for public officials to uphold the prescribed rules of ethical conduct and integrity | 1.2.1.1 | The overall level of tolerance of corruption in Ukraine has decreased owing to the integration of anticorruption topics into educational curricula at all levels, which includes instilling in society a stable perception of corruption as a phenomenon that significantly slows down the socioeconomic development of the country, of corrupt officials as persons who make public administration ineffective, and the realization that dishonest practices, even when they look like a convenient opportunity to solve their issues in the short term, are always disadvantageous for individuals and society in the medium and long term | 1.2.1.1.17 | Conducting a public discussion of the draft order indicated in subclause 1.2.1.1.16 | 01.05.2024 | 31.05.2024 | Ministry of Education and Science of Ukraine |  | state budget | within the established budget allocations for the relevant year | The public discussion has been conducted. | Міністерство освіти і науки України провело громадське обговорення проєкт наказу "Про внесення змін до Методичних рекомендацій щодо розроблення стандартів вищої освіти". МОН затверджено звіт з громадського обговорення проєкту акта | Implemented | 0.0
1.2 | Instilling a negative attitude towards corruption | 1.2.1 Everyday corrupt practices are an established norm of conduct and are not perceived as violations of moral or legal norms. There is no consistent demand from the population for public officials to uphold the prescribed rules of ethical conduct and integrity | 1.2.1.1 | The overall level of tolerance of corruption in Ukraine has decreased owing to the integration of anticorruption topics into educational curricula at all levels, which includes instilling in society a stable perception of corruption as a phenomenon that significantly slows down the socioeconomic development of the country, of corrupt officials as persons who make public administration ineffective, and the realization that dishonest practices, even when they look like a convenient opportunity to solve their issues in the short term, are always disadvantageous for individuals and society in the medium and long term | 1.2.1.1.18 | Revising (if needed) and issuing the order indicated in subclause 1.2.1.1.16 | 01.06.2024 | 31.07.2024 | Ministry of Education and Science of Ukraine |  | state budget | within the established budget allocations for the relevant year | The order has been issued. | Amendments to the Guidelines for the Development of Higher Education Standards, approved by the Order of the Ministry of Education and Science (MES) No. 600 of June 1, 2016, were developed and approved. These amendments include in the list of mandatory general competencies for the Bachelor’s degree the competence related to intolerance to corruption in all its manifestations and understanding the inadmissibility of tolerating inequality and dishonesty (MES Order No. 441 of April 3, 2024). | Implemented | 0.0
1.2 | Instilling a negative attitude towards corruption | 1.2.1 Everyday corrupt practices are an established norm of conduct and are not perceived as violations of moral or legal norms. There is no consistent demand from the population for public officials to uphold the prescribed rules of ethical conduct and integrity | 1.2.1.1 | The overall level of tolerance of corruption in Ukraine has decreased owing to the integration of anticorruption topics into educational curricula at all levels, which includes instilling in society a stable perception of corruption as a phenomenon that significantly slows down the socioeconomic development of the country, of corrupt officials as persons who make public administration ineffective, and the realization that dishonest practices, even when they look like a convenient opportunity to solve their issues in the short term, are always disadvantageous for individuals and society in the medium and long term | 1.2.1.1.19 | Developing amendments to standards of higher education, approved by orders of the Ministry of Education and Science, taking into account the amendments to the Procedural Recommendations indicated in subclause 1.2.1.1.16 | 04.05.2024 | 04.07.2024 | Ministry of Education and Science of Ukraine | National Agency on Corruption Prevention | state budget | within the established budget allocations for the relevant year | The draft order amending the normative legal acts has been developed. | The Order of the Ministry of Education and Science No. 842 of June 13, 2024, “On Amending Certain Higher Education Standards,” was developed and approved, providing for certain specialties to include in the list of mandatory general competencies for the Bachelor’s degree the competence related to intolerance to corruption in all its manifestations, understanding the inadmissibility of tolerating inequality and dishonesty. | Implemented | 0.0
1.2 | Instilling a negative attitude towards corruption | 1.2.1 Everyday corrupt practices are an established norm of conduct and are not perceived as violations of moral or legal norms. There is no consistent demand from the population for public officials to uphold the prescribed rules of ethical conduct and integrity | 1.2.1.1 | The overall level of tolerance of corruption in Ukraine has decreased owing to the integration of anticorruption topics into educational curricula at all levels, which includes instilling in society a stable perception of corruption as a phenomenon that significantly slows down the socioeconomic development of the country, of corrupt officials as persons who make public administration ineffective, and the realization that dishonest practices, even when they look like a convenient opportunity to solve their issues in the short term, are always disadvantageous for individuals and society in the medium and long term | 1.2.1.1.20 | Conducting a public discussion of the draft order indicated in subclause 1.2.1.1.19 | 04.08.2024 | 04.09.2024 | Ministry of Education and Science of Ukraine |  | state budget | within the established budget allocations for the relevant year | The public discussion has been conducted. | Міністерство освіти і науки України провело громадського обговорення проєкт наказу "Про всесення змін до деяких стандартів вищої освіти". | Implemented | 0.0
1.2 | Instilling a negative attitude towards corruption | 1.2.1 Everyday corrupt practices are an established norm of conduct and are not perceived as violations of moral or legal norms. There is no consistent demand from the population for public officials to uphold the prescribed rules of ethical conduct and integrity | 1.2.1.1 | The overall level of tolerance of corruption in Ukraine has decreased owing to the integration of anticorruption topics into educational curricula at all levels, which includes instilling in society a stable perception of corruption as a phenomenon that significantly slows down the socioeconomic development of the country, of corrupt officials as persons who make public administration ineffective, and the realization that dishonest practices, even when they look like a convenient opportunity to solve their issues in the short term, are always disadvantageous for individuals and society in the medium and long term | 1.2.1.1.21 | Revising (if needed) and issuing the order indicated in subclause 1.2.1.1.19 | 04.10.2024 | 04.11.2024 | Ministry of Education and Science of Ukraine |  | state budget | within the established budget allocations for the relevant year | The order has been issued. | “The Order of the Ministry of Education and Science No. 842 of June 13, 2024, “On Amending Certain Higher Education Standards,” was approved, stipulating certain specialties to include in the list of mandatory general competencies for the Bachelor’s degree the competence related to intolerance to corruption in all its manifestations, understanding the inadmissibility of tolerating inequality and dishonesty.” | Implemented | 0.0