## Заходи
№ Напрямку | Напрямок | Проблема | № ОСР | Назва ОСР | № Заходу | Назва заходу | Дата початку | Дата завершення | Головний виконавець | Співвиконавці | Джерела фінансування | Обсяги фінансування, тис.грн. | Показник (індикатор) виконання | Стан виконання | Статус виконання | Оцінка досягнення ОСР
1.2 | Instilling a negative attitude towards corruption | 1.2.1 Everyday corrupt practices are an established norm of conduct and are not perceived as violations of moral or legal norms. There is no consistent demand from the population for public officials to uphold the prescribed rules of ethical conduct and integrity | 1.2.1.4 | The overall level of tolerance of corruption in Ukraine has decreased owing to the implementation of comprehensive measures aimed at instilling in public servants a perception of themselves as people serving the interests of the Ukrainian nation, as well as public trust in public servants as the key reason of why they hold their office | 1.2.1.4.1 | Developing an online course on the general provisions of anticorruption legislation for civil servants | 01.03.2023 | 30.04.2023 | National Agency on Corruption Prevention |  | state budget | within the established budget allocations for the relevant year | The course has been developed and published on the NAZK.Study learning platform. | According to the National Agency on Corruption Prevention, in pursuance of measure 1.2.1.4.1, “the integrity civil service course was launched with a delayed deadline in accordance with the State Anti-Corruption Program due to the understaffing of the civil servants training department and the training product development department, so the course devising actually started in March 2013, and the course was launched in June.” | Implemented | 0.0
1.2 | Instilling a negative attitude towards corruption | 1.2.1 Everyday corrupt practices are an established norm of conduct and are not perceived as violations of moral or legal norms. There is no consistent demand from the population for public officials to uphold the prescribed rules of ethical conduct and integrity | 1.2.1.4 | The overall level of tolerance of corruption in Ukraine has decreased owing to the implementation of comprehensive measures aimed at instilling in public servants a perception of themselves as people serving the interests of the Ukrainian nation, as well as public trust in public servants as the key reason of why they hold their office | 1.2.1.4.2 | Developing an online course on the particularities of anticorruption legislation for representatives of local self-government bodies (with the possible involvement of NGOs and international technical assistance projects in this activity) | 01.03.2023 | 30.06.2023 | National Agency on Corruption Prevention |  | state budget | within the established budget allocations for the relevant year | The course has been developed and published on the NAZK.Study learning platform. | According to the notification of the National Agency on Corruption Prevention, in order to implement measure 1.2.1.4.2., "the course was developed and published on the Study.NAZK platform. A public presentation of the course was held at the Forum of Virtuous Communities." | Implemented | 0.0
1.2 | Instilling a negative attitude towards corruption | 1.2.1 Everyday corrupt practices are an established norm of conduct and are not perceived as violations of moral or legal norms. There is no consistent demand from the population for public officials to uphold the prescribed rules of ethical conduct and integrity | 1.2.1.4 | The overall level of tolerance of corruption in Ukraine has decreased owing to the implementation of comprehensive measures aimed at instilling in public servants a perception of themselves as people serving the interests of the Ukrainian nation, as well as public trust in public servants as the key reason of why they hold their office | 1.2.1.4.3 | Developing an online course devoted to the particularities of anticorruption legislation for judges | 01.03.2023 | 31.07.2023 | National Agency on Corruption Prevention |  | state budget | within the established budget allocations for the relevant year | The course has been developed and published on the NAZK.Study learning platform. | The course was developed and published on the Study.NAZK platform. As of the end of the third quarter of 2023, more than 400 users completed the course. | Implemented | 0.0
1.2 | Instilling a negative attitude towards corruption | 1.2.1 Everyday corrupt practices are an established norm of conduct and are not perceived as violations of moral or legal norms. There is no consistent demand from the population for public officials to uphold the prescribed rules of ethical conduct and integrity | 1.2.1.4 | The overall level of tolerance of corruption in Ukraine has decreased owing to the implementation of comprehensive measures aimed at instilling in public servants a perception of themselves as people serving the interests of the Ukrainian nation, as well as public trust in public servants as the key reason of why they hold their office | 1.2.1.4.4 | Developing an online course devoted to the particularities of anticorruption legislation for representatives of the law enforcement sector | 01.03.2023 | 31.08.2023 | National Agency on Corruption Prevention |  | state budget | within the established budget allocations for the relevant year | The course has been developed and published on the NAZK.Study learning platform. | The course was developed and published on the Study.NAZK platform. | Implemented | 0.0
1.2 | Instilling a negative attitude towards corruption | 1.2.1 Everyday corrupt practices are an established norm of conduct and are not perceived as violations of moral or legal norms. There is no consistent demand from the population for public officials to uphold the prescribed rules of ethical conduct and integrity | 1.2.1.4 | The overall level of tolerance of corruption in Ukraine has decreased owing to the implementation of comprehensive measures aimed at instilling in public servants a perception of themselves as people serving the interests of the Ukrainian nation, as well as public trust in public servants as the key reason of why they hold their office | 1.2.1.4.5 | Developing an online course devoted to the particularities of anticorruption legislation for parliament members | 01.03.2023 | 31.08.2023 | National Agency on Corruption Prevention |  | state budget | within the established budget allocations for the relevant year | The course has been developed and published on the NAZK.Study learning platform. | The course was developed and published on the Study.NAZK platform. | Implemented | 0.0
1.2 | Instilling a negative attitude towards corruption | 1.2.1 Everyday corrupt practices are an established norm of conduct and are not perceived as violations of moral or legal norms. There is no consistent demand from the population for public officials to uphold the prescribed rules of ethical conduct and integrity | 1.2.1.4 | The overall level of tolerance of corruption in Ukraine has decreased owing to the implementation of comprehensive measures aimed at instilling in public servants a perception of themselves as people serving the interests of the Ukrainian nation, as well as public trust in public servants as the key reason of why they hold their office | 1.2.1.4.6 | Developing an online course devoted to the functioning of government agencies and local self-government bodies and their interaction with various social groups (businesses, the public, etc.) (with the possible involvement of NGOs and international technical assistance projects in this activity) | 01.03.2023 | 31.08.2023 | National Agency on Corruption Prevention |  | state budget | within the established budget allocations for the relevant year | The course has been developed and published on the NAZK.Study learning platform. | The course was developed and published on the Study.NAZK platform. At the time of reporting, 25,746 people were registered for the course, and 23,705 people received certificates of successful completion. | Implemented | 0.0
1.2 | Instilling a negative attitude towards corruption | 1.2.1 Everyday corrupt practices are an established norm of conduct and are not perceived as violations of moral or legal norms. There is no consistent demand from the population for public officials to uphold the prescribed rules of ethical conduct and integrity | 1.2.1.4 | The overall level of tolerance of corruption in Ukraine has decreased owing to the implementation of comprehensive measures aimed at instilling in public servants a perception of themselves as people serving the interests of the Ukrainian nation, as well as public trust in public servants as the key reason of why they hold their office | 1.2.1.4.7 | Conducting systemic training of civil servants and local self-government officials on anticorruption topics (anticorruption, standards of integrity and ethical conduct) in civil service and service at local self-government bodies | 01.03.2023 | 31.12.2025 | National Agency of Ukraine on Civil Service |  | state budget and/or international technical assistance funds | within the established budget allocations for the relevant year | At least 2,000 individuals have completed training in anticorruption and standards of integrity and ethical conduct. | За інформацією, наданою Національним агентством з питань державної служби України (далі - НАДС), за результатами конкурсного відбору було визначено виконавців державного замовлення НАДС на підвищення кваліфікації державних службовців та посадових осіб місцевого самоврядування у 2025 році та затверджено їм обсяги державного замовлення, у тому числі на підвищення кваліфікації з питань антикорупційної тематики (наказ НАДС від 15.08.2025 № 112-25 «Про затвердження обсягів державного замовлення НАДС на підвищення кваліфікації державних службовців та посадових осіб місцевого самоврядування у 2025 році»). Упродовж серпня-вересня 2025 року в закладах освіти, відібраних на конкурсній основі, за державним замовленням НАДС підвищили кваліфікацію 1093 державних службовців, які займають посади державної служби категорій «Б» та «В», посадових осіб місцевого самоврядування з питань антикорупційної тематики (доброчесність, запобігання корупції, стандарти доброчесної та етичної поведінки). Загалом протягом 2025 року навчання з питань антикорупційної тематики (доброчесність, запобігання корупції, стандарти доброчесної та етичної поведінки) пройшли 3 056 державних службовців, які займають посади державної служби категорій «Б» та «В», та посадових осіб місцевого самоврядування. Інформаційно-аналітичний звіт про результати надання освітніх послуг закладами освіти на підвищення кваліфікації державних службовців, голів місцевих державних адміністрацій, їх перших заступників та заступників, посадових осіб місцевого самоврядування у 2025 році буде підготовлено та розміщено на офіційному вебсайті НАДС у лютому 2026 року. Таким чином, зважаючи на ступінь відповідності фактично вжитих дій вимогам ДАП щодо змісту та способу виконання заходу, вважаємо за можливе констатувати, що захід є виконаним повністю. | Implemented | 0.0
1.2 | Instilling a negative attitude towards corruption | 1.2.1 Everyday corrupt practices are an established norm of conduct and are not perceived as violations of moral or legal norms. There is no consistent demand from the population for public officials to uphold the prescribed rules of ethical conduct and integrity | 1.2.1.4 | The overall level of tolerance of corruption in Ukraine has decreased owing to the implementation of comprehensive measures aimed at instilling in public servants a perception of themselves as people serving the interests of the Ukrainian nation, as well as public trust in public servants as the key reason of why they hold their office | 1.2.1.4.8 | Ensuring the development of a model general professional (certification) program of professional development for civil servants and officials of local self-government bodies with a focus on anticorruption topics (anticorruption, standards of integrity and ethical conduct) | 01.04.2023 | 31.12.2025 | National Agency of Ukraine on Civil Service | National Agency on Corruption Prevention | state budget | within the established budget allocations for the relevant year | The model general program has been developed. | According to the National Agency of Ukraine on Civil Service (NAUCS), in pursuance of measure 1.2.1.4.8, “a standard general professional (certificate) advanced training program “Prevention of Corruption and Implementation of Integrity Standards in the Civil Service and Local Government Bodies” was developed, approved by NAUCS Order No. 81-23 of June 09, 2023 and posted on the NAUCS official website at: http://surl.li/hvers.” | Implemented | 0.0
1.2 | Instilling a negative attitude towards corruption | 1.2.1 Everyday corrupt practices are an established norm of conduct and are not perceived as violations of moral or legal norms. There is no consistent demand from the population for public officials to uphold the prescribed rules of ethical conduct and integrity | 1.2.1.4 | The overall level of tolerance of corruption in Ukraine has decreased owing to the implementation of comprehensive measures aimed at instilling in public servants a perception of themselves as people serving the interests of the Ukrainian nation, as well as public trust in public servants as the key reason of why they hold their office | 1.2.1.4.9 | Systemically staging communications and awareness raising events devoted to the issues of integrity in civil service, the role of civil servants, the functioning of the state apparatus, interactions with citizens and businesses, etc. (with the possible involvement of NGOs and international technical assistance projects in this activity) | 01.07.2023 | 31.12.2025 | National Agency on Corruption Prevention | National Agency of Ukraine on Civil Service | state budget and/or international technical assistance funds | within the established budget allocations for the relevant year and/or international technical assistance funds | At least four events are staged each year. | Системне проведення інформаційно-просвітницьких заходів, присвячених питанням доброчесності на публічній службі, ролі публічних службовців, функціонуванню державного апарату, взаємодії з громадянами та бізнесом здійснювалося протягом 2023, 2024, 2025 років. У 2023 році було проведено 4 інформаційно-просвітницькі заходи: Форум доброчесних громад; інформаційно-просвітницький захід з теми доброчесності та презентація курсу для суддів; Доброчесність на практиці: важливі питання від поліцейських; Вирішення ситуацій конфлікту інтересів та моральних дилем для поліцейських. Протягом 2024 року було: • проведено інформаційно-просвітницький захід для слідчих та оперуповноважених НПУ “Необґрунтовані активи та незаконне збагачення”. До навчання долучились понад 900 правоохоронців; • 2 квітня 2024 року НАДС взято участь в Ярмарці вакансій «Career week-2024». Під час заходу висвітлено питання процедури стажування на публічній службі, вступу на публічну службу, а також можливостей щодо проходження публічної служби. Участь у заході взяли більше 200 студентів; • 18 квітня 2024 року в рамках навчання за програмою підвищення кваліфікації «Роль керівника у побудові доброчесного середовища організації», що проходив для публічних службовців вищого корпусу державної служби, Голова НАДС Наталія Алюшина розповіла про важливість формування доброчесного іміджу органів влади та яким чином цього можна досягти; • 26 червня 2024 року відбулась зустріч Голови НАДС Наталії Алюшиної зі студентами Університету «КРОК» та фахового коледжу Університету «КРОК»; • проведено навчально-просвітницький захід “Практичні поради: як запобігти порушенню антикорупційного законодавства та як розслідувати антикорупційні справи” для керівників структурних підрозділів центрального органу управління Національної поліції України; • 19 грудня 2024 року проведено підсумковий у 2024 році координаційний форум фахівців з державних комунікацій, представників медіа, громадських організацій та проектів міжнародної технічної допомоги; • та ін. У рамках виконання даного заходу у І кварталі 2025 року основні зусилля були зосереджені на проведені інформаційно-просвітницьких заходів з питань декларування і дотримання законодавства про запобігання конфлікту інтересів на публічній службі. Також було проведено три регіональні поїздки до Кропивницького, Тернополя, Запоріжжя. У II кварталі 2025 року було проведено та прокомуніковано просвітницькі заходи з питань доброчесності на публічній службі, зокрема під час поїздок до регіонів, навчання для публічних службовців, зустрічей з освітянами та студентами, кампанії декларування тощо. Протягом III кварталу 2025 року системні інформаційно-просвітницькі заходи охопили публічну службу та взаємодію з бізнесом. Важливим кроком стало впровадження нового антикорупційного інструмента – Реєстру прозорості. Зокрема, 01.09.2025 було проведено презентацію його можливостей та функцій, а також опубліковано детальну інструкцію для забезпечення відкритої та прозорої роботи інституту лобіювання. Для підвищення доброчесності в держсекторі НАЗК проводило регіональні поїздки на Миколаївщину та Київщину, де обговорювалися та ідентифікувалися корупційні ризики у важливих сферах для регіонів (відбудова, закупівлі, земельні відносини). Інформаційна кампанія доповнена роз’ясненнями щодо правил отримання подарунків державними службовцями та висвітленням позитивних результатів цифровізації, зокрема економічного та антикорупційного ефекту сервісу «Дія». Також було прокомуніковано запуск нового онлайн-курсу з корпоративного управління та антикорупційного комплаєнсу, що спрямований на підвищення професійної доброчесності комунальних підприємств тощо. У IV кварталі 2025 року для підвищення доброчесності в держсекторі НАЗК провело регіональну поїздку на Сумщину, де обговорювалися та ідентифікувалися корупційні ризики у важливих сферах для регіону (відбудова, закупівлі, земельні відносини). 30 жовтня 2025 року проведено третій Форум доброчесності громад, який є щорічною платформою НАЗК для обміну досвідом і координації дій у розбудові доброчесності на місцевому рівні. Таким чином, зважаючи на ступінь відповідності фактично вжитих дій вимогам ДАП щодо змісту та способу виконання заходу, вважаємо за можливе констатувати, що захід є виконаним повністю. | Implemented | 0.0