## Заходи
№ Напрямку | Напрямок | Проблема | № ОСР | Назва ОСР | № Заходу | Назва заходу | Дата початку | Дата завершення | Головний виконавець | Співвиконавці | Джерела фінансування | Обсяги фінансування, тис.грн. | Показник (індикатор) виконання | Стан виконання | Статус виконання | Оцінка досягнення ОСР
1.3 | Resolution of the conflicts of interest, observance of general restrictions and bans, rules of ethical conduct | 1.3.1 Flaws of legislation and the lack of effective risk-based mechanisms for detecting conflicts of interest limit the ability to minimize corruption by preventing and resolving conflicts of interest. | 1.3.1.2 | Improvements have been made to legislative procedures for reporting a conflict of interest and the mechanisms used to resolve it, particularly in relation to officials who do not have an immediate superior or occupy elective positions | 1.3.1.2.1 | Drafting and submitting to the Cabinet of Ministers of Ukraine a draft law that: 1) establishes requirements with respect to the form of the conflict of interest statement; 2) provides for the algorithm of actions of the immediate superior of the person who has a conflict of interest, where the superior has no powers to apply a specific method of external resolution of the conflict of interest (such as transfer or dismissal); 3) aligns the provisions of the Law of Ukraine On Prevention of Corruption, specifically with respect to the person who must be informed about the conflict of interest and the person who must resolve the conflict of interest; 4) improves the mechanism of resolution of the conflict of interest for individuals who do not have an immediate superior, particularly those filling elective positions; 5) extends the term for making a decision on the resolution of the conflict of interest. | 01.07.2023 | 31.03.2025 | National Agency on Corruption Prevention |  | state budget | within the established budget allocations for the relevant year | The draft law has been submitted to the Parliament of Ukraine. | Продовжується підготовка законопроекту на підставі концепції, яку розробило Національне агентство. З огляду на те, що настала дата завершення строку виконання відповідного заходу, а законопроект станом на момент звітування не розроблено та не забезпечено його подання Кабінетові Міністрів України, такий захід вважається не виконаним. | Not implemented | 0.0