## Заходи
№ Напрямку | Напрямок | Проблема | № ОСР | Назва ОСР | № Заходу | Назва заходу | Дата початку | Дата завершення | Головний виконавець | Співвиконавці | Джерела фінансування | Обсяги фінансування, тис.грн. | Показник (індикатор) виконання | Стан виконання | Статус виконання | Оцінка досягнення ОСР
1.4 | Implementation of financial control measures | 1.4.3 Previous efforts involving oversight and verification of declaration as well as monitoring of the lifestyle were not sufficiently effective. | 1.4.3.5 | The National Agency has effective tools to prevent abuse of financial control measures against persons who are staff members of intelligence agencies and/or are directly involved in intelligence, counterintelligence, and field detective activities | 1.4.3.5.1 | Developing the draft Procedure for conducting logical and arithmetic control and control of the completeness of the declaration of a person authorized to carry out the functions of state or local self-government, submitted by specific categories of individuals defined in Article 521 of the Law | 01.03.2023 | 30.04.2023 | National Agency on Corruption Prevention | Ministry of Justice of Ukraine, Administration of the State Border Guard Service, Administration of State Service of Special Commucations and Information Protection of Ukraine, State Tax Service of Ukraine, National Police of Ukraine, State Bureau of Investigation , National Anti-Corruption Bureau of Ukraine, Security Service of Ukraine , Foreign Intelligence Service of Ukraine, State Security Administration, Economic Security Bureau of Ukraine, Ministry of Defenсe of Ukraine | state budget | within the established budget allocations for the relevant year | The draft Procedure has been developed and submitted to the concerned state authorities for processing. | На виконання заходу 1.4.3.5.1., було розроблено відповідний проект Порядку та надано його для опрацювання заінтересованим органам державної влади. | Implemented | 0.0
1.4 | Implementation of financial control measures | 1.4.3 Previous efforts involving oversight and verification of declaration as well as monitoring of the lifestyle were not sufficiently effective. | 1.4.3.5 | The National Agency has effective tools to prevent abuse of financial control measures against persons who are staff members of intelligence agencies and/or are directly involved in intelligence, counterintelligence, and field detective activities | 1.4.3.5.2 | Clearing the draft Procedure indicated in subclause 1.4.3.5.1 with the concerned authorities and reworking the draft (if necessary) | 01.04.2023 | 30.06.2023 | National Agency on Corruption Prevention | Ministry of Justice of Ukraine, Administration of the State Border Guard Service, Administration of State Service of Special Commucations and Information Protection of Ukraine, State Tax Service of Ukraine, National Police of Ukraine, State Bureau of Investigation , National Anti-Corruption Bureau of Ukraine, Security Service of Ukraine , Foreign Intelligence Service of Ukraine, State Security Administration | state budget | within the established budget allocations for the relevant year | The draft Procedure has been submitted to the concerned state authorities for processing. | На виконання заходу 1.4.3.5.2., було розроблено проект Порядку та надіслано для погодження та опрацювання органам державної влади. | Implemented | 0.0
1.4 | Implementation of financial control measures | 1.4.3 Previous efforts involving oversight and verification of declaration as well as monitoring of the lifestyle were not sufficiently effective. | 1.4.3.5 | The National Agency has effective tools to prevent abuse of financial control measures against persons who are staff members of intelligence agencies and/or are directly involved in intelligence, counterintelligence, and field detective activities | 1.4.3.5.3 | Adoption of the Procedure indicated in subclause 1.4.3.5.1 and its state registration with the Ministry of Justice | 01.07.2023 | 31.08.2023 | National Agency on Corruption Prevention | Ministry of Justice of Ukraine | state budget | within the established budget allocations for the relevant year | The Procedure has been registered with the Ministry of Justice and sent out to the concerned state authorities to be used in their work. | Порядок, зазначений у підпункті 1.4.3.5.1, прийнято та зареєстровано у Міністерстві юстиції України (наказ Національного агентства з питань запобігання корупції від 16.06.2023 № 1-ДСК, зареєстрований в Міністерстві юстиції України 26.06.2023 за № 1059/40115.), а також надіслано для використання в роботі заінтересованим органам державної влади | Implemented | 0.0
1.4 | Implementation of financial control measures | 1.4.3 Previous efforts involving oversight and verification of declaration as well as monitoring of the lifestyle were not sufficiently effective. | 1.4.3.5 | The National Agency has effective tools to prevent abuse of financial control measures against persons who are staff members of intelligence agencies and/or are directly involved in intelligence, counterintelligence, and field detective activities | 1.4.3.5.4 | Forming a working group tasked with the implementation of a system(s) supporting electronic logical and arithmetic control and control of the correctness and completeness of the relevant declarations | 01.09.2023 | 31.10.2023 | National Agency on Corruption Prevention | Ministry of Justice of Ukraine, Administration of the State Border Guard Service, Administration of State Service of Special Commucations and Information Protection of Ukraine, State Tax Service of Ukraine, National Police of Ukraine, State Bureau of Investigation , National Anti-Corruption Bureau of Ukraine, Security Service of Ukraine , Foreign Intelligence Service of Ukraine, State Security Administration, Economic Security Bureau of Ukraine, Ministry of Defenсe of Ukraine | state budget | within the established budget allocations for the relevant year | The work group has been formed. | By order of the National Agency on Corruption Prevention dated September 21, 2023 No. 3-DSK, a working group was formed to implement a system that supporting electronic logical and arithmetic control and control of the correctness and completeness of the declarations of a person authorized to carry out the functions of state or local self-government, submitted by specific categories of individuals. | Implemented | 0.0
1.4 | Implementation of financial control measures | 1.4.3 Previous efforts involving oversight and verification of declaration as well as monitoring of the lifestyle were not sufficiently effective. | 1.4.3.5 | The National Agency has effective tools to prevent abuse of financial control measures against persons who are staff members of intelligence agencies and/or are directly involved in intelligence, counterintelligence, and field detective activities | 1.4.3.5.5 | Holding consultations, developing technical specifications for the system indicated in subclause 1.4.3.5.4 | 01.11.2023 | 31.12.2024 | National Agency on Corruption Prevention | Ministry of Justice of Ukraine, Administration of the State Border Guard Service, Administration of State Service of Special Commucations and Information Protection of Ukraine, State Tax Service of Ukraine, National Police of Ukraine, State Bureau of Investigation , National Anti-Corruption Bureau of Ukraine, Security Service of Ukraine , Foreign Intelligence Service of Ukraine, State Security Administration, Economic Security Bureau of Ukraine, Ministry of Defenсe of Ukraine | state budget | within the established budget allocations for the relevant year | The technical specifications for the system have been approved. | Проблема, визначена у п. 1.4.3.5 Заходів з виконання Державної антикорупційної програми на 2023–2025 роки (далі – Заходи ДАП), полягає у необхідності запровадження Національним агентством ефективних інструментів, які унеможливлювали б зловживання особливим порядком здійснення фінансового контролю щодо осіб, що належать до кадрового складу розвідувальних органів або здійснюють розвідувальну, контррозвідувальну чи оперативно-розшукову діяльність. За умови дотримання вимог власної безпеки очікуваним результатом має стати впровадження системи (або систем), що забезпечуватиме логічний і арифметичний контроль, а також перевірку правильності й повноти заповнення електронних декларацій. Передбачалося впровадження таких систем у 12 державних органах або військових формуваннях. Водночас, за інформацією, отриманою у квітні–травні 2025 року, через вимоги власної безпеки реалізація системи у розвідувальних органах України є неможливою. Разом з тим у межах роботи робочої групи проведено консультації щодо технічних вимог і затверджено Перелік невідповідностей (ризиків) та вагових коефіцієнтів, що застосовуються під час контролю декларацій. Крім іншого, 24.12.2025 виконання робіт з розробки та впровадження системи Логічного та арифметичного контролю щодо правильності та повноти заповнення декларацій в електронному вигляді в Службі безпеки України завершено, що свідчить про часткове виконання заходу. Станом на квітень 2026 року Службою безпеки України введено експлуатацію систему, яка має забезпечувати логічний і арифметичний контроль, а також контроль правильності та повноти заповнення електронних декларацій осіб, визначених у ст. 52-1 Закону. Зазначений захід реалізований в межах виконання договору на закупівлю програмно-апаратного комплексу «Перевірка декларацій» за результатами проведених публічних торгів (UA-2024-11-29-015277-a). Цей проєкт можна вважати пілотним, а отриманий досвід – таким, що може бути масштабований для подальшого впровадження аналогічних систем в інших державних органах або військових формуваннях з метою остаточної реалізації підпункту 1.4.3.5.5 та 1.4.3.5.6 Заходів ДАП. | Partially implemented | 0.0
1.4 | Implementation of financial control measures | 1.4.3 Previous efforts involving oversight and verification of declaration as well as monitoring of the lifestyle were not sufficiently effective. | 1.4.3.5 | The National Agency has effective tools to prevent abuse of financial control measures against persons who are staff members of intelligence agencies and/or are directly involved in intelligence, counterintelligence, and field detective activities | 1.4.3.5.6 | Putting the system(s) supporting logical and arithmetic control and control of the correctness and completeness of the relevant declarations in electronic form into commercial operation on condition of conformity to internal security requirements | 01.01.2025 | 01.01.1970 | National Agency on Corruption Prevention | Ministry of Justice of Ukraine, Administration of the State Border Guard Service, Administration of State Service of Special Commucations and Information Protection of Ukraine, State Tax Service of Ukraine, National Police of Ukraine, State Bureau of Investigation , National Anti-Corruption Bureau of Ukraine, Security Service of Ukraine , Foreign Intelligence Service of Ukraine, State Security Administration, Economic Security Bureau of Ukraine, Ministry of Defenсe of Ukraine | state budget | within the established budget allocations for the relevant year | The system has been put into commercial operation. | Проблема, визначена у п. 1.4.3.5 Заходів з виконання Державної антикорупційної програми на 2023–2025 роки (далі – Заходи ДАП), полягає у необхідності запровадження Національним агентством ефективних інструментів, які унеможливлювали б зловживання особливим порядком здійснення фінансового контролю щодо осіб, що належать до кадрового складу розвідувальних органів або здійснюють розвідувальну, контррозвідувальну чи оперативно-розшукову діяльність. За умови дотримання вимог власної безпеки очікуваним результатом має стати впровадження системи (або систем), що забезпечуватиме логічний і арифметичний контроль, а також перевірку правильності й повноти заповнення електронних декларацій. Передбачалося впровадження таких систем у 12 державних органах або військових формуваннях. Водночас, за інформацією, отриманою у квітні–травні 2025 року, через вимоги власної безпеки реалізація системи у розвідувальних органах України є неможливою. Разом з тим у межах роботи робочої групи проведено консультації щодо технічних вимог і затверджено Перелік невідповідностей (ризиків) та вагових коефіцієнтів, що застосовуються під час контролю декларацій. Крім іншого, 24.12.2025 виконання робіт з розробки та впровадження системи Логічного та арифметичного контролю щодо правильності та повноти заповнення декларацій в електронному вигляді в Службі безпеки України завершено, що свідчить про часткове виконання заходу. Станом на квітень 2026 року Службою безпеки України введено експлуатацію систему, яка має забезпечувати логічний і арифметичний контроль, а також контроль правильності та повноти заповнення електронних декларацій осіб, визначених у ст. 52-1 Закону. Зазначений захід реалізований в межах виконання договору на закупівлю програмно-апаратного комплексу «Перевірка декларацій» за результатами проведених публічних торгів (UA-2024-11-29-015277-a). Цей проєкт можна вважати пілотним, а отриманий досвід – таким, що може бути масштабований для подальшого впровадження аналогічних систем в інших державних органах або військових формуваннях з метою остаточної реалізації підпункту 1.4.3.5.5 та 1.4.3.5.6 Заходів ДАП. | Partially implemented | 0.0