## Заходи
№ Напрямку | Напрямок | Проблема | № ОСР | Назва ОСР | № Заходу | Назва заходу | Дата початку | Дата завершення | Головний виконавець | Співвиконавці | Джерела фінансування | Обсяги фінансування, тис.грн. | Показник (індикатор) виконання | Стан виконання | Статус виконання | Оцінка досягнення ОСР
1.5 | Ensuring the integrity of political parties and election campaigns | 1.5.3 The system for monitoring the funding of activities of political parties and the funding of their participation in elections needs improving | 1.5.3.5 | Effective division of powers between the Central Electoral Commission and the National Agency involving control over political financing and election campaigning has been ensured | 1.5.3.5.1 | Supporting the consideration of the draft amendments to the Election Code of Ukraine in the Parliament of Ukraine (particularly if the President of Ukraine vetoes it), which would: 1) mandate the electronic submission and disclosure of all financial statements of participants of the election process on the political finances portal of the National Agency; 2) mandate a complete audit of financial statements submitted by administrators of election funds of candidates for the position of the President of Ukraine and political parties, and random monitoring of the funding of election campaigns of other entities participating in the election process; 3) stipulate that the National Agency shall carry out the function of review (analysis) of financial statements reflecting the proceeds and spending of election funds. | 01.03.2023 | 31.12.2025 | National Agency on Corruption Prevention |  | state budget and/or international technical assistance funds | within the established budget allocations for the relevant year | The law has been signed by the President of Ukraine. | Питаннями розробки проекту закону про внесення змін до Виборчого кодексу України опікувалась парламентська робоча група, створена Комітетом Верховної Ради України з питань організації державної влади, місцевого самоврядування, регіонального розвитку та містобудування. За результатами діяльності такої робочої групи народними депутатами України 05.08.2024 було зареєстровано у Верховній Раді України проект Закону України "Про внесення змін до деяких законодавчих актів України щодо вдосконалення правил фінансування виборчих кампаній та здійснення контролю виборчих фондів" (реєстр. № 11462). При цьому, Національне агентство висловило позицію, що в цілому підтримує запропонований законопроект задля продовження реформування сфери фінансування політичних партій та виборчих кампаній (лист № 50-02/62814-24 від 29.08.2024). З огляду на обсяг вжитих дій та водночас у зв’язку недосягненням показника (індикатора) виконання (закон не підписано Президентом України), відповідний захід не може вважатись таким, що виконаний повністю. | Partially implemented | 0.0
1.5 | Ensuring the integrity of political parties and election campaigns | 1.5.3 The system for monitoring the funding of activities of political parties and the funding of their participation in elections needs improving | 1.5.3.5 | Effective division of powers between the Central Electoral Commission and the National Agency involving control over political financing and election campaigning has been ensured | 1.5.3.5.2 | Drafting and submitting to the Cabinet of Ministers of Ukraine a draft law proposing to entirely delegate the function of review (analysis) of financial statements of participants of referendums to the National Agency | 01.07.2023 | 30.04.2025 | National Agency on Corruption Prevention | The Central Election Commission of Ukraine | state budget | within the established budget allocations for the relevant year | The draft law has been submitted to the Parliament of Ukraine. | На виконання відповідного заходу Національне агентство розробило законопроект. 29.04.2025 було проведено його громадське обговорення. Станом на 31.03.2026 здійснюється доопрацювання законопроекту з урахуванням результатів обговорення та підготовка його до надсилання заінтересованим органам на погодження. З огляду на те, що настала дата завершення строку виконання відповідного заходу, а законопроект станом на момент звітування не фіналізовано та не забезпечувалось його подання Кабінетові Міністрів України, такий захід вважається не виконаним. | Not implemented | 0.0