## Заходи
№ Напрямку | Напрямок | Проблема | № ОСР | Назва ОСР | № Заходу | Назва заходу | Дата початку | Дата завершення | Головний виконавець | Співвиконавці | Джерела фінансування | Обсяги фінансування, тис.грн. | Показник (індикатор) виконання | Стан виконання | Статус виконання | Оцінка досягнення ОСР
1.3 | Resolution of the conflicts of interest, observance of general restrictions and bans, rules of ethical conduct | 1.3.3 The activities of entities that influence (lobby) the parliamentary decision-making process are non-transparent and non-public. | 1.3.3.1 | Owing to regulatory and legal regulation, the activities of agents influence (lobbying) are carried out within the legal framework and have become understandable and transparent for the whole society | 1.3.3.1.1 | Conducting an analytical study of the legal mechanisms of lobbying employed in other countries in order to determine the model that could be applied in the legal system of Ukraine and would ensure a procedure of transparent influence on the process of administrative decision making exerted by the concerned commercial entities, NGOs, public associations, or separate individuals | 01.03.2023 | 31.08.2023 | National Agency on Corruption Prevention |  | state budget | within the established budget allocations for the relevant year | The analytical study has been conducted. | Based on the results of the analytical study, the concept of the Draft Law On Transparency of Lobbying was prepared | Implemented | 0.0
1.3 | Resolution of the conflicts of interest, observance of general restrictions and bans, rules of ethical conduct | 1.3.3 The activities of entities that influence (lobby) the parliamentary decision-making process are non-transparent and non-public. | 1.3.3.1 | Owing to regulatory and legal regulation, the activities of agents influence (lobbying) are carried out within the legal framework and have become understandable and transparent for the whole society | 1.3.3.1.2 | Drafting and submitting to the Cabinet of Ministers of Ukraine a draft law proposing to define: 1) the rules to be followed by officials of government agencies and local self-government bodies in interacting with stakeholders and agents of influence (lobbyists); 2) transparent mechanisms for influencing officials of government agencies and local self-government bodies; 3) mechanisms used to control lobbying activities and the agency authorized to exercise such control; 4) liability of the parties to lobbyist relationships for violation of rules governing their interaction and transparency of the lobbying process | 01.09.2023 | 30.04.2024 | National Agency on Corruption Prevention |  | state budget | within the established budget allocations for the relevant year | The draft law has been submitted to the Parliament of Ukraine. | The National Agency on Corruption Prevention has developed Draft Laws On Amendments to the Code of Ukraine on Administrative Offences on Violation of Legislation in the Area of Lobbying and On Fair Lobbying and Advocacy in Ukraine. Public discussions of the respective draft laws were held on November 10 and 23, 2023. The Draft Laws were sent to the Cabinet of Ministers of Ukraine by letter dated December 01, 2023 No. 27-02/29325-23. By letter dated December 08, 2023, No. 31651/0/2-23, the Secretariat of the Cabinet of Ministers of Ukraine returned the Draft Laws. The Draft Laws were resubmitted to the Cabinet of Ministers of Ukraine by letter dated December 11, 2023 No. 27-02/30801-23. On December 13, 2023, the Draft Law was received by the Verkhovna Rada of Ukraine. The Law of Ukraine On Lobbying (hereinafter referred to as the Law of February 23, 2024 No. 3606-IX) was adopted on February 23, 2024. On March 12, 2024, the President of Ukraine signed the Law of February 23, 2024 No. 3606-IX. | Implemented | 0.0