## Заходи
№ Напрямку | Напрямок | Проблема | № ОСР | Назва ОСР | № Заходу | Назва заходу | Дата початку | Дата завершення | Головний виконавець | Співвиконавці | Джерела фінансування | Обсяги фінансування, тис.грн. | Показник (індикатор) виконання | Стан виконання | Статус виконання | Оцінка досягнення ОСР
1.6 | Protection of corruption whistleblowers | 1.6.3 Whistleblower protection is not properly implemented due to insufficient institutional capacity of the authorized bodies and shortcomings in legislative regulation | 1.6.3.1 | The National Agency and other authorized bodies (units), within their scope of authority, properly implement whistleblower protection in practice through: monitoring the activities of authorized units (authorized officers) in matters of prevention and detection of corruption regarding their work with whistleblowers; proper coordination among agencies authorized to provide whistleblower protection; a proper level of legal protection of whistleblowers; facilitating the provision of psychological assistance to whistleblowers | 1.6.3.1.1 | Developing the concept of the system for annual monitoring of the activities of authorized units (authorized officers) in matters of prevention and detection of corruption regarding their work with whistleblowers, particularly with respect to: 1) the number of whistleblowers who have requested the protection of the authorized unit (authorized officer) in matters of prevention and detection of corruption; 2) violations of the rights of whistleblowers at an institution; 3) the measures taken towards the protection of a whistleblower by the authorized unit (authorized officer) in matters of prevention and detection of corruption. | 01.09.2023 | 30.11.2023 | National Agency on Corruption Prevention |  | state budget and/or international technical assistance funds | within the established budget allocations for the relevant year | The concept has been developed. | The National Agency on Corruption Prevention has developed the concept of the system for annual monitoring of the activities of authorized units (authorized officers) in matters of prevention and detection of corruption regarding their work with whistleblowers. According to this concept, the monitoring of the activities of authorized units (authorized officers) in matters of prevention and detection of corruption regarding their work with whistleblowers is conducted by analyzing the quality and effectiveness of the exercise of their powers in the area of whistleblower protection, which, among other criteria, includes the presence/absence of information on the appeal of whistleblowers to the authorized unit (authorized officers) for their protection due to the violation (threat of violation) of their rights and guarantees; measures taken by the authorized unit (authorized officers) to ensure cooperation with whistleblowers, respect for their rights and protection guarantees provided by law. | Implemented | 0.0
1.6 | Protection of corruption whistleblowers | 1.6.3 Whistleblower protection is not properly implemented due to insufficient institutional capacity of the authorized bodies and shortcomings in legislative regulation | 1.6.3.1 | The National Agency and other authorized bodies (units), within their scope of authority, properly implement whistleblower protection in practice through: monitoring the activities of authorized units (authorized officers) in matters of prevention and detection of corruption regarding their work with whistleblowers; proper coordination among agencies authorized to provide whistleblower protection; a proper level of legal protection of whistleblowers; facilitating the provision of psychological assistance to whistleblowers | 1.6.3.1.2 | Implementing the system for annual monitoring of the activities of authorized units (authorized officers) in matters of prevention and detection of corruption regarding their work with whistleblowers | 01.12.2023 | 31.01.2025 | National Agency on Corruption Prevention |  | state budget and/or international technical assistance funds | within the established budget allocations for the relevant year | The monitoring system has been implemented. | Національне агентство з питань запобігання корупції застосовує систему моніторингу діяльності уповноважених підрозділів (осіб) з питань запобігання та виявлення корупції щодо роботи з викривачами шляхом проведення планових/позапланових перевірок організації роботи в організаціях. У 2024 році підготовлено Аналітичне дослідження у сфері захисту викривачів, яке враховує результати запровадження системи моніторингу діяльності уповноважених підрозділів (осіб) з питань запобігання та виявлення корупції щодо роботи з викривачами за 2023 рік. Відповідно до розробленої Концепції системи щорічного моніторингу діяльності уповноважених підрозділів (осіб) з питань запобігання та виявлення корупції щодо роботи з викривачами, моніторинг діяльності уповноважених підрозділів (осіб) щодо роботи з викривачами проводиться один раз на рік у першому кварталі (півріччі) року, наступному за роком, за який необхідно провести моніторинг такої діяльності. За результатами проведення моніторингу Національним агентством з питань запобігання корупції в довільній формі складається звіт оцінки діяльності уповноважених підрозділів (осіб) щодо роботи з викривачами. У звіті оцінки діяльності робота уповноважених підрозділів (осіб) щодо роботи з викривачами може визначається як ефективна або неефективна. У першому кварталі 2025 року розпочато моніторинг виконання закону в сфері захисту викривачів, за результатами якого сформовано аналітичний звіт у сфері захисту викривачів за 2024 рік. | Implemented | 0.0
1.6 | Protection of corruption whistleblowers | 1.6.3 Whistleblower protection is not properly implemented due to insufficient institutional capacity of the authorized bodies and shortcomings in legislative regulation | 1.6.3.1 | The National Agency and other authorized bodies (units), within their scope of authority, properly implement whistleblower protection in practice through: monitoring the activities of authorized units (authorized officers) in matters of prevention and detection of corruption regarding their work with whistleblowers; proper coordination among agencies authorized to provide whistleblower protection; a proper level of legal protection of whistleblowers; facilitating the provision of psychological assistance to whistleblowers | 1.6.3.1.4 | Developing procedural recommendations on how to provide psychological assistance to whistleblowers | 01.03.2024 | 30.06.2024 | National Agency on Corruption Prevention | Ministry of Education and Science of Ukraine, Ministry of Health of Ukraine, Ministry of Social Policy, Family and Unity of Ukraine, Ministry of Veterans Affairs of Ukraine | state budget and/or international technical assistance funds | within the established budget allocations for the relevant year | The recommendations have been developed. | Methodological recommendations for providing psychological assistance to whistleblowers have been developed. | Implemented | 0.0
1.6 | Protection of corruption whistleblowers | 1.6.3 Whistleblower protection is not properly implemented due to insufficient institutional capacity of the authorized bodies and shortcomings in legislative regulation | 1.6.3.2 | Courts and free secondary legal assistance centers are a reliable mechanism for protecting whistleblower rights due to the increased level of qualifications and competencies of judges, free secondary legal assistance center staff and free secondary legal assistance lawyers in whistleblower cases | 1.6.3.2.1 | Developing training materials for courses for judges, prosecutors, police officers, employees of the State Bureau of Investigations, attorneys providing secondary legal assistance free of charge, and employees of centers providing free secondary legal assistance, in matters of legal protection of whistleblowers | 01.09.2023 | 31.12.2023 | National Agency on Corruption Prevention | Ministry of Justice of Ukraine, Prosecutor General’s Office of Ukraine , Coordination Centre for Legal Aid Provision, National School of Judges of Ukraine | state budget and/or international technical assistance funds | within the established budget allocations for the relevant year | The training materials have been developed. | The National Agency on Corruption Prevention has developed a Practical Guide on Working with Whistleblowers, which establishes a clear algorithm of actions for authorized departments (persons) in working with whistleblowers to ensure compliance with their rights and protection guarantees as stipulated by law, as well as providing recommendations on existing limitations in the area of professional ethics for authorized persons regarding whistleblowers. The guide is structured from general to specific, i.e., from explaining the general aspects of organizing work for authorized departments (persons) with whistleblowers to addressing specific issues related to working with whistleblowers and their reports. Based on this guide, corresponding informational and educational materials have been created for training courses for judges, prosecutors, police officers, employees of the State Bureau of Investigations, lawyers providing free secondary legal aid, and employees of centers for providing free secondary legal aid on whistleblower legal protection. Additionally, from September to December 2023, the Coordination Center for Legal Aid reached agreements with partners of the USAID project “Support for Anti-Corruption Organizations in Ukraine ‘Interaction’” to update previously developed materials and prepare new training program materials for lawyers providing free secondary legal assistance to whistleblowers, including adding a block on current issues for lawyers at centers for providing free secondary legal aid. As of June 30, 2024: - a training program for prosecutors titled “The Role of Whistleblowers in Preventing Corruption and Their Legal Protection” has been developed; - educational materials on corruption prevention and detection have been consolidated in the Practical Guide on Working with Whistleblowers for authorized departments (persons). | Implemented | 0.0
1.6 | Protection of corruption whistleblowers | 1.6.3 Whistleblower protection is not properly implemented due to insufficient institutional capacity of the authorized bodies and shortcomings in legislative regulation | 1.6.3.2 | Courts and free secondary legal assistance centers are a reliable mechanism for protecting whistleblower rights due to the increased level of qualifications and competencies of judges, free secondary legal assistance center staff and free secondary legal assistance lawyers in whistleblower cases | 1.6.3.2.2 | Ensuring that at least six training courses focusing on legal protection of whistleblowers are organized for judges, prosecutors, police officers, employees of the State Bureau of Investigations, attorneys providing secondary legal assistance free of charge, and employees of centers providing free secondary legal assistance | 01.01.2024 | 31.12.2024 | National Agency on Corruption Prevention | Ministry of Justice of Ukraine, Higher Qualification Commission of Judges of Ukraine , Prosecutor General’s Office of Ukraine , Coordination Centre for Legal Aid Provision | state budget and/or international technical assistance funds | within the established budget allocations for the relevant year | The courses have been organized. | За інформацією, наданою виконавцем, сукупно Національним агентством з питань запобігання корупції проведено 7 тренінгів (навчальних курсів з питань правового захисту викривачів) для прокурорів, 2 - для слідчих Національної поліції України та працівників Державного бюро розслідувань та 2 онлайн-курси для юристів та адвокатів. Спільно з Тренінговим центром прокурорів розроблено та запущено обов'язкову сертифіковану програму для прокурорів (яка є діючою і у 2025 році, включено в тему антикорупційних механізмів). Також у червні 2025 року спільно з Асоціацією правників України проведено вебінар для адвокатів на тему «Правовий захист трудових прав викривачів корупції: теорія і практика правозастосування». Разом з тим, кількісний показник (проведення щонайменше шести навчальних курсів) виконано, проте інформація щодо проведення НАЗК навчальних курсів з питань правового захисту викривачів для суддів та працівників центрів з надання безоплатної вторинної правової допомоги відсутня, що дає підстави вважати захід таким, що виконаний частково. | Partially implemented | 0.0
1.6 | Protection of corruption whistleblowers | 1.6.3 Whistleblower protection is not properly implemented due to insufficient institutional capacity of the authorized bodies and shortcomings in legislative regulation | 1.6.3.3 | Ukrainian legislation is aligned with international standards of protection of whistleblowers; effective mechanisms for implementing legislation on whistleblower protection, including security measures, have been created | 1.6.3.3.1 | Drafting and submitting to the Cabinet of Ministers of Ukraine a draft law proposing to align the legislation of Ukraine with international standards governing the protection of whistleblowers, which would specifically provide for: 1) the adoption of a broad definition of the term “whistleblowers”; 2) extending the guarantees of protection of the whistleblower to individuals who facilitated the report; 3) refining the procedure for reviewing the reports submitted via regular channels, particularly to the National Agency; 4) designating the National Agency as the authority responsible for coordinating the activities of agencies authorized to provide protection for whistleblowers; 5) ensuring the safety of whistleblowers by expanding the category of individuals entitled to safety measures and implementing new safety measures. | 01.02.2024 | 30.06.2025 | National Agency on Corruption Prevention | Ministry of Foreign Affairs of Ukraine, Ministry of Justice of Ukraine | state budget | within the established budget allocations for the relevant year | The draft law has been submitted to the Parliament of Ukraine. | Продовжується підготовка законопроекту. З огляду на те, що настала дата завершення строку виконання відповідного заходу, а законопроект станом на момент звітування не розроблено та не забезпечувалось його подання Кабінетові Міністрів України, такий захід вважається не виконаним. | Not implemented | 0.0
1.6 | Protection of corruption whistleblowers | 1.6.3 Whistleblower protection is not properly implemented due to insufficient institutional capacity of the authorized bodies and shortcomings in legislative regulation | 1.6.3.4 | The law prescribes the particularities of protection of whistleblowers among military personnel. | 1.6.3.4.1 | Drafting and submitting to the Cabinet of Ministers of Ukraine a draft law providing for: 1) the ability of whistleblowers in the army to freely choose the report channels; 2) the rights and guarantees of protection of military personnel; 3) the implementation of a mechanism of incentives of whistleblowers in the army. | 01.08.2023 | 31.10.2024 | Ministry of Defenсe of Ukraine | Security Service of Ukraine , Foreign Intelligence Service of Ukraine, National Agency on Corruption Prevention | state budget | within the established budget allocations for the relevant year | The draft law has been submitted to the Parliament of Ukraine. | На виконання заходу 1.6.3.4.1 Державної антикорупційної програми на 2023-2025 роки, затвердженої Постановою Кабінету Міністрів України від 04.03.2023 № 220 (далі – ДАП), Міністерство оборони України розробило проект закону «Про внесення змін до Дисциплінарного статуту Збройних Сил України щодо забезпечення гарантій захисту та прав військовослужбовців, які повідомили про можливі факти корупційних або пов’язаних з корупцією правопорушень, інших порушень Закону України «Про запобігання корупції» (далі – проект Закону). Зазначений проект Закону відповідно до пояснювальної записки розроблено з метою приведення окремих положень Закону України «Про Дисциплінарний статут Збройних Сил України» у відповідність до положень Закону України «Про національну безпеку України» в частині внесення змін до Дисциплінарного статуту Збройних Сил України щодо забезпечення гарантій захисту та прав військовослужбовців, які повідомили про можливі факти корупційних або пов’язаних з корупцією правопорушень, інших порушень Закону України «Про запобігання корупції». 04.09.2024 Міністерство оборони України направило проект Закону до Кабінету Міністрів України. 17.09.2024 проект Закону був поданий до Верховної Ради України (зареєстрований у Верховній Раді України за №12040). У зв’язку із відставкою Уряду законопроект № 12040 було відкликано 17.07.2025. У свою чергу, 07.08.2025 новий проект Закону був поданий до Верховної Ради України (зареєстрований у Верховній Раді України за №13605). Проаналізувавши проект Закону, захід 1.6.3.4.1 ДАП виконано повністю оскільки поданий до Верховної Ради України проект Закону передбачає: 1) вільне обрання каналів повідомлення викривачами-військовослужбовцями (зазначена норма передбачена у проекті Закону шляхом доповнення Дисциплінарного статуту Збройних Сил України новою ст. 114-1, яка передбачає самостійне обрання каналів повідомлення для викривачів з числа військовослужбовців, у т.ч. і під час подання ними повідомлень, які містять інформацію з обмеженим доступом; окрім цього, запропоновано зміни до ст. 114 щодо уточнення та приведення норм цієї статті до вимог Закону України «Про запобігання корупції»); 2) права та гарантії захисту військовослужбовців (зазначена норма передбачена у проекті Закону шляхом внесення змін до ст. 87-1 Дисциплінарного статуту Збройних Сил України, яка передбачає поширення також інших прав та гарантій захисту на викривачів з числа військовослужбовців, встановленні Законом України «Про запобігання корупції», до ст. 110 щодо розширення переліку суб’єктів до яких має право звертатися військовослужбовець особисто або надсилати заяви, скарги чи повідомлення, у т.ч. і розширено перелік підстав, з яких він може звертатися); 3) запровадження механізму заохочення викривачів-військовослужбовців (зазначена норма передбачена у проекті Закону шляхом внесення змін до ст. 87-1 Дисциплінарного статуту Збройних Сил України зміни, які передбачають, що викривачі із числа військовослужбовців можуть бути заохочені відповідно до вимог розділу ІІ Дисциплінарного статуту Збройних Сил України). | Implemented | 0.0
1.6 | Protection of corruption whistleblowers | 1.6.3 Whistleblower protection is not properly implemented due to insufficient institutional capacity of the authorized bodies and shortcomings in legislative regulation | 1.6.3.4 | The law prescribes the particularities of protection of whistleblowers among military personnel. | 1.6.3.4.2 | Conducting a communications and awareness raising campaign among military personnel on how they can acquire status as a whistleblower, on the channels through which reports can be made, and on the guarantees of protection for whistleblowers in the army | 01.03.2024 | 30.11.2024 | Ministry of Defenсe of Ukraine | Security Service of Ukraine , Foreign Intelligence Service of Ukraine | state budget and/or international technical assistance funds | within the established budget allocations for the relevant year and/or international technical assistance funds | The campaign has been conducted. | За інформацією, наданою Міністерством оборони України, протягом звітного періоду забезпечувалося проведення інформаційно-просвітницької кампанії серед військовослужбовців. Зокрема, на офіційному сайті Міністерства оборони України розміщено відповідні інформаційні матеріали, а саме: Наказ Міноборони від 12.08.2025 №541/нм “Про затвердження Положення щодо впровадження в системі Міністерства оборони України механізмів заохочення викривачів та формування культури повідомлення про можливі факти корупційних або пов’язаних із корупцією правопорушень, інших порушень Закону України “Про запобігання корупції””; пам’ятки викривачам корупції в ЗСУ серед яких: пам’ятка щодо порушень про які можна повідомити, пам'ятка, куди повідомляти про корупцію, пам’ятка про порядок розгляду повідомлень, пам’ятка щодо прав та гарантій захисту прав викривачів; гайд для викривачів корупції НАЗК; посилання на роз’яснення НАЗК як викривачі можуть повідомити про корупцію. 18.01.2024 року на сайті було розміщено новину, що Міноборони підключено до Єдиного порталу викривачів. А також поінформовано, що військовослужбовець може повідомити про можливі факти корупційних або пов’язаних з корупцією правопорушень можна через спеціальну телефонну лінію Міноборони, електронну пошту, офіційний веб-сайт відомства. За повідомленням Міністерства оборони України, інформацію про їх розміщення доведено до особового складу. У приміщеннях казарм, штабів військових частин на інформаційних стендах оновлено інформацію із зазначеного питання. Зазначені інформаційні матеріали надають роз’яснення щодо каналів для здійснення повідомлення, гарантій захисту викривачів-військовослужбовців та інформацію щодо набуття статусу викривача. Враховуючи зазначене вище, а також зважаючи на ступінь відповідності фактично вжитих дій вимогам ДАП щодо змісту та способу виконання заходу, вважаємо за можливе констатувати, що захід є виконаним повністю. | Implemented | 0.0