## Заходи
№ Напрямку | Напрямок | Проблема | № ОСР | Назва ОСР | № Заходу | Назва заходу | Дата початку | Дата завершення | Головний виконавець | Співвиконавці | Джерела фінансування | Обсяги фінансування, тис.грн. | Показник (індикатор) виконання | Стан виконання | Статус виконання | Оцінка досягнення ОСР
2.1 | Fair courts, prosecutorial and law enforcement authorities | 2.1.7 The need to improve the process of independent evaluation of the performance of anticorruption agencies and develop mechanisms for holding them liable | 2.1.7.2 | The issue of the grounds for dismissal of heads of law enforcement agencies who have been brought to administrative liability for a corruption-related administrative offense has been regulated | 2.1.7.2.1 | Drafting and submitting to the Cabinet of Ministers of Ukraine a draft law under which law enforcement officers can be dismissed following a binding court decision to hold them administratively or criminally liable for committing corruption or a corruption-related offense, which imposed a penalty or punishment on the officer in the form of a prohibition from filling positions or engaging in activities involving the performance of the functions of state or local self-government | 01.07.2025 | 31.12.2025 | National Agency on Corruption Prevention |  | state budget | within the established budget allocations for the relevant year | The draft law has been submitted to the Parliament of Ukraine. | Здійснюється підготовка зазначеного законопроекту. З огляду на те, що настала дата завершення строку виконання відповідного заходу, а законопроект станом на момент звітування не розроблено та не забезпечувалось його подання Кабінетові Міністрів України, такий захід вважається не виконаним. | Not implemented | 0.0
2.1 | Fair courts, prosecutorial and law enforcement authorities | 2.1.7 The need to improve the process of independent evaluation of the performance of anticorruption agencies and develop mechanisms for holding them liable | 2.1.7.3 | An effective mechanism for conducting an independent evaluation (audit) of the performance of the National Anticorruption Bureau of Ukraine and the Specialized Anticorruption Prosecutor’s Office has been introduced | 2.1.7.3.1 | Drafting and submitting to the Cabinet of Ministers of Ukraine a draft law proposing to institute a periodic external independent assessment (audit) of the performance of the Specialized Anticorruption Prosecutor’s Office, which will be carried out by reputed international experts proposed by international and foreign organizations that have provided international technical assistance to Ukraine in matters of preventing and combating corruption | 01.01.2024 | 30.11.2024 | National Agency on Corruption Prevention | Ministry of Justice of Ukraine, National Anti-Corruption Bureau of Ukraine | state budget | within the established budget allocations for the relevant year | The draft law has been submitted to the Parliament of Ukraine. | On September 15, 2023, the Draft Law No. 10060 On Amendments to the Criminal Procedure Code of Ukraine and Other Legislative Acts of Ukraine on Strengthening the Independence of the Specialized Anti-Corruption Prosecutor's Office was registered in the Verkhovna Rada of Ukraine. On December 08, 2023, the Verkhovna Rada of Ukraine adopted the Law of Ukraine No. 3509-IX On Amendments to the Criminal Procedure Code of Ukraine and Other Legislative Acts of Ukraine on Strengthening the Independence of the Specialized Anti-Corruption Prosecutor's Office. Part ten of Article 8-1 of the Law of Ukraine On the Prosecutor's Office fully reproduces the provisions of the measure provided for in sub-clause 2.1.7.3.1 of Appendix 2 to the State Anti-Corruption Program for 2023-2025. In particular, part ten of Article 8-1 of the Law of Ukraine On the Prosecutor's Office provides that every two years, but not more than twice during the term of office of the Deputy Prosecutor General - Head of the Specialized Anti-Corruption Prosecutor's Office, an external independent assessment (audit) of the effectiveness of the Specialized Anti-Corruption Prosecutor's Office is conducted. It is also established that the assessment (audit) of the effectiveness of the Specialized Anti-Corruption Prosecutor's Office is carried out by the Commission for External Independent Assessment (Audit) of the Effectiveness of the Specialized Anti-Corruption Prosecutor's Office consisting of three persons appointed by the Prosecutor General based on proposals of international and foreign organizations that provide international technical assistance to Ukraine in the area of preventing and combating corruption in accordance with international or intergovernmental agreements. | Implemented | 0.0
2.1 | Fair courts, prosecutorial and law enforcement authorities | 2.1.7 The need to improve the process of independent evaluation of the performance of anticorruption agencies and develop mechanisms for holding them liable | 2.1.7.3 | An effective mechanism for conducting an independent evaluation (audit) of the performance of the National Anticorruption Bureau of Ukraine and the Specialized Anticorruption Prosecutor’s Office has been introduced | 2.1.7.3.2 | Arranging an external independent assessment (audit) of the performance of the National Anticorruption Bureau and publicizing a report on its findings at intervals prescribed by the law | 07.03.2024 | 01.01.1970 | Ministry of Foreign Affairs of Ukraine |  | state budget | within the established budget allocations for the relevant year | The assessment has been conducted at intervals prescribed by the law, and the report on the findings of each assessment has been publicized. | Міністерство закордонних справ листом від 11.07.2025 вих. №110/15-628/1-82469 повідомило, що відповідно до отриманого МЗС листа НАБУ від 09.05.2025 р. № 01-016/13522, незалежна оцінка (аудит) ефективності діяльності Агентства завершена 02.05.2025 та звіт за її результатами опубліковано на сайті «Урядовий портал», який доступний за наступним посиланням: https://www.kmu.gov.ua/storage/app/sites/1/otsinka_nabu/finalnyi-zvit-ukr.pdf Відповідно до п. 6 Прикінцевих та перехідних положень ЗУ «Про внесення змін до деяких законів України щодо приведення статусу Національного антикорупційного бюро України у відповідність з вимогами Конституції України» перша зовнішня незалежна оцінка (аудит) ефективності діяльності НАБУ проводиться через один рік з дня призначення Директора НАБУ (тобто після 6 березня 2023 року). Крім того, згідно з п.7 ст. 26 ЗУ «Про Національне антикорупційне бюро України» зовнішня незалежна оцінка (аудит) ефективності діяльності Національного бюро.проводиться щороку. Для виконання цього завдання Уряд 06.02.2024 ухвалив рішення про початок формування Комісії з проведення зовнішньої незалежної оцінки. Склад Комісії було затверджено Розпорядженням Кабінету Міністрів України від 03 вересня 2024 р. № 832-р на основі пропозицій міжнародних та іноземних організацій, які протягом останніх трьох років надавали Україні міжнародну технічну допомогу у сфері запобігання та протидії корупції відповідно до міжнародних або міждержавних угод. До складу Комісії увійшли: юрист, екс-заступник генерального директора Служби внутрішньої безпеки Естонії, екс-радник голови Ради Werol Tehased AS Мартін Арпо; екс-кримінальний слідчий, юрист, менеджер програм Офісу генерального інспектора Поштової служби США та Міністерства транспорту США Роберт Вестбрукс; екс-антикорупційний фахівець Глобальної операційної мережі органів боротьби з корупцією (GlobE Network) Тереза Герміона Кроньє. 18 листопада 2024 року Комісія з проведення зовнішньої незалежної оцінки (аудиту) ефективності діяльності НАБУ затвердила Критерії та методику проведення оцінювання. Зовнішній незалежний аудит діяльності Національного антикорупційного бюро України розпочався 03.10.2024 і охоплював період з березня 2023 до листопада 2024 року, як визначено п. 3.1 Критеріїв та методики. За результатами роботи Комісія 02.05.2025 затвердила звіт, який було опубліковано у спеціальному розділі на сайті Кабінету Міністрів України. З огляду на вищевикладене та враховуючи дату початку виконання заходу, можна зробити висновок, що захід 2.1.7.3.2. Додатку 2 до ДАП є виконаним повністю. | Implemented | 0.0