## Заходи
№ Напрямку | Напрямок | Проблема | № ОСР | Назва ОСР | № Заходу | Назва заходу | Дата початку | Дата завершення | Головний виконавець | Співвиконавці | Джерела фінансування | Обсяги фінансування, тис.грн. | Показник (індикатор) виконання | Стан виконання | Статус виконання | Оцінка досягнення ОСР
1.1 | Shaping and implementing the state anticorruption policy | 1.1.4 The institution of authorized anticorruption units (officers) does not fully realize its potential due to insufficient guarantees of autonomy | 1.1.4.1 | The institution of authorized anticorruption units (officers) is operating with integrity as an independent network of leaders drawing on best international and domestic practices and receives comprehensive coordination support from the National Agency | 1.1.4.1.1 | Drafting and submitting to the Cabinet of Ministers of Ukraine a draft law that: 1) defines the leadership role of the head of the institution in shaping and implementing the sectoral anticorruption policy in the Law of Ukraine On the Central Executive Authorities and remove the provision to the effect that the minister has a deputy minister tasked with the issues of combating corruption; 3) unifies the principles of organization of the activities of authorized officers of government agencies, local self-government bodies, legal entities under public law, as well as legal entities under private law; 4) includes heads of authorized units of regional state administrations, executive offices of regional councils in the list of heads of authorized units tasked with prevention and detection of corruption, whose dismissal at the initiative of the institution manager would require the consent of the National Agency; 5) expands the list of reasons for which the National Agency grants consent to the dismissal of the head of the authorized unit (authorized officer); 6) defines the powers of the National Agency to establish the recommended requirements for the minimum staff headcount of the authorized unit at local self-government bodies; 7) obligates the head of the government agency to adhere to the requirements with respect to the minimum staff headcount of the authorized unit tasked with prevention and detection of corruption at government agencies; 8) sets forth the obligation to coordinate with the National Agency any changes in the structure and staff of the agencies indicated in Part 1 of Article 19 of the Law, where such changes result in the reorganization of the authorized unit, the relocation or dismissal of its head or employees, as well as to obtain the approval of the National Agency for this structure and staff list where the authorized unit gets formed (authorized officer gets appointed) for the first time; 9) obligates the heads of agencies, enterprises, institutions, and organizations to sign a declaration of independence with the head of the authorized unit (authorized officer) using the model form approved by the National Agency and ensure adherence to this declaration, which would make it possible to specify more concretely the guarantees of independence of the authorized unit (authorized officer) from undue influence or interference with its activities; 10) provides for the approval of the appointment and dismissal of heads of authorized units (authorized officers) at regional offices of government agencies whose jurisdiction covers the entire territory of Ukraine, at enterprises, institutions, and organizations managed by government agencies by the heads of authorized units (authorized officers) of the relevant government agencies, and for the approval of the appointment and dismissal of heads of authorized units (authorized officers) of municipal enterprises by heads of authorized units (authorized officers) at the relevant local self-government bodies. | 01.08.2023 | 30.06.2024 | National Agency on Corruption Prevention |  | state budget | within the established budget allocations for the relevant year | The draft law has been submitted to the Parliament of Ukraine. | Національне агентство за результатами проведеного аналізу наявних проблем функціонування інституту уповноважених осіб з питань запобігання та виявлення корупції, практики реалізації відповідних повноважень, відповідного міжнародного досвіду та низки консультацій фіналізувало потенційні шляхи законодавчого врегулювання існуючих проблем у відповідній сфері та доопрацювало відповідний законопроект. Зазначений законопроект направлений 19.03.2025 на погодження до заінтересованих органів. Здійснюється опрацювання отриманих зауважень та з огляду на висловлені заінтересованими органами зауваження, триває підготовка до узгоджувальних процедур. Одним із зауважень, отриманих до законопроекту, є зауваження Мінфіну щодо необхідності погодження цього проекту зі всеукраїнськими асоціаціями органів місцевого самоврядування. З метою врахування цього зауваження Національне агентство надіслало листом від 14.05.2025 № 10-03/42288-25 проект на погодження до діючих в Україні всеукраїнських асоціацій органів місцевого самоврядування. Всі з цих асоціацій підтримали проект без зауважень. Станом на 31.03.2026 здійснюється опрацювання зауважень заінтересованих органів. | Not implemented | 0.0
1.1 | Shaping and implementing the state anticorruption policy | 1.1.4 The institution of authorized anticorruption units (officers) does not fully realize its potential due to insufficient guarantees of autonomy | 1.1.4.1 | The institution of authorized anticorruption units (officers) is operating with integrity as an independent network of leaders drawing on best international and domestic practices and receives comprehensive coordination support from the National Agency | 1.1.4.1.11 | Drafting and submitting to the Cabinet of Ministers of Ukraine the draft resolution of the Cabinet of Ministers of Ukraine on amendments to the recommended lists of organizational units of regional state administrations, Kyiv and Sevastopol city state administrations, district state administrations, district state administrations in the cities of Kyiv and Sevastopol, approved by the resolution of the Cabinet of Ministers of Ukraine dated April 18, 2021, No. 606, which would include the authorized unit tasked with prevention of corruption in the recommended lists of organizational units of regional state administrations, Kyiv and Sevastopol city state administrations, district state administrations, district state administrations in the cities of Kyiv and Sevastopol | 01.03.2023 | 31.07.2023 | Ministry for Communities and Territories Development of Ukraine |  | state budget | within the established budget allocations for the relevant year | The resolution of the Cabinet of Ministers of Ukraine has been adopted. | 09.06.2023 Кабінетом Міністрів України прийнято постанову № 579 "Про внесення змін до постанови Кабінету Міністрів України від 18 квітня 2012 р. № 606", якою затверджено зміни щодо включення уповноваженого підрозділу з питань запобігання корупції до рекомендаційних переліків структурних підрозділів обласної, Київської та Севастопольської міської, районної, районної в мм. Києві та Севастополі державних адміністрацій | Implemented | 0.0
1.1 | Shaping and implementing the state anticorruption policy | 1.1.4 The institution of authorized anticorruption units (officers) does not fully realize its potential due to insufficient guarantees of autonomy | 1.1.4.1 | The institution of authorized anticorruption units (officers) is operating with integrity as an independent network of leaders drawing on best international and domestic practices and receives comprehensive coordination support from the National Agency | 1.1.4.1.12 | Drafting and submitting to the Cabinet of Ministers of Ukraine the draft resolution of the Cabinet of Ministers of Ukraine on amendments to the Model Form of the Contract with the head of a state-owned enterprise, approved by the resolution of the Cabinet of Ministers of Ukraine dated August 2, 1995, No. 597, which would supplement the Model Form with the obligation of the enterprise manager to implement anticorruption standards in the operations of the enterprise and ensure the guarantees of independence of the anticorruption officer | 01.03.2023 | 31.10.2024 | Ministry of Economy, Environment and Agriculture of Ukraine |  | state budget | within the established budget allocations for the relevant year | The resolution of the Cabinet of Ministers of Ukraine has been adopted. | На виконання заходу 1.1.4.1.12. Мінекономіки розроблено проект постанови Кабінету Міністрів України “Про внесення змін до постанови Кабінету Міністрів України від 2 серпня 1995 р. № 597” (далі – проект постанови), яким передбачається внести зміни до Типової форми контракту (шляхом викладення його у новій редакції) з керівником підприємства, що є у державній власності, передбачивши в контракті, у тому числі, обов’язок керівника підприємства впроваджувати стандарти запобігання корупції у діяльності підприємства та забезпечувати гарантії незалежності антикорупційного уповноваженого. За результатами розгляду проекту постанови на засіданні Урядового комітету з питань економічної, фінансової і правової політики, паливно-енергетичного комплексу, стратегічних галузей промисловості та правоохоронної діяльності 28.03.2024 прийнято рішення про необхідність доопрацювання проекту постанови. При цьому доручено Мінекономіки разом із заінтересованими органами опрацювати питання законодавчого врегулювання повноважень щодо затвердження типової форми контракту з керівником державного унітарного підприємства та за результатами подати Кабінетові Міністрів відповідні пропозиції. На виконання зазначеного рішення Мінекономіки розробило проект Закону України “Про внесення зміни до статті 5 Закону України “Про управління об’єктами державної власності” (далі – проект Закону), яким пропонується шляхом доповнення частини другої статті 5 Закону України “Про управління об’єктами державної власності” встановити, що здійснюючи управління об’єктами державної власності, Кабінет Міністрів України затверджує типову форму контракту з керівником державного унітарного підприємства та головою виконавчого органу господарського товариства, у статутному капіталі якого 100 відсотків акцій (часток) належать державі. Проект Закону схвалено Кабінетом Міністрів України та подано до Верховної Ради України (зареєстровано у Верховній Раді України 19.08.2024, реєстр. № 11494). Натомість, Мінекономіки повідомляє, що 28.08.2025 введено в дію Закон України «Про особливості регулювання діяльності юридичних осіб окремих організаційно-правових форм у перехідний період та об’єднань юридичних осіб», яким передбачено припинення всіх державних підприємств шляхом ліквідації або перетворення у господарські товариства. З урахуванням цього Закону та в рамках підготовки пропозицій щодо внесення змін до Політики державної власності, затвердженої постановою КМУ від 29.11.2024 № 1369, передбачається визнати такою, що втратила чинність, постанову КМУ від 2 серпня 1995 р. № 597. Водночас, з огляду на викладене, показник виконання заходу не досягнуто: постанову Кабінету Міністрів України не прийнято, у зв’язку з чим захід не може вважатися виконаним. | Not implemented | 0.0
1.1 | Shaping and implementing the state anticorruption policy | 1.1.4 The institution of authorized anticorruption units (officers) does not fully realize its potential due to insufficient guarantees of autonomy | 1.1.4.1 | The institution of authorized anticorruption units (officers) is operating with integrity as an independent network of leaders drawing on best international and domestic practices and receives comprehensive coordination support from the National Agency | 1.1.4.1.13 | Drafting and submitting to the Cabinet of Ministers of Ukraine the draft resolution of the Cabinet of Ministers of Ukraine on amendments to the Model Requirements for Individuals Applying for Category “A” Civil Service Positions, approved by the resolution of the Cabinet of Ministers of Ukraine dated July 22, 2016, No. 448, and defining the following as one of the components of the “Leadership” requirement: fostering a culture of openness, accountability, and zero tolerance of corruption | 01.03.2023 | 31.07.2023 | National Agency of Ukraine on Civil Service |  | state budget | within the established budget allocations for the relevant year | The resolution of the Cabinet of Ministers of Ukraine has been adopted. | Кабінетом Міністрів України прийнято постанову від 02.06.2023 № 562 "Про внесення зміни до Типових вимог до осіб, які претендують на зайняття посад державної служби категорії “А”, якою одним із компонентів вимоги “Лідерство” до осіб, які претендують на зайняття посад державної служби категорії “А” визначено створення культури нульової толерантності до корупції, відкритості та відповідальності | Implemented | 0.0
1.1 | Shaping and implementing the state anticorruption policy | 1.1.4 The institution of authorized anticorruption units (officers) does not fully realize its potential due to insufficient guarantees of autonomy | 1.1.4.1 | The institution of authorized anticorruption units (officers) is operating with integrity as an independent network of leaders drawing on best international and domestic practices and receives comprehensive coordination support from the National Agency | 1.1.4.1.14 | Developing and launching an online course on the role of the leader in developing an environment of integrity in an organization. At least 300 heads of ministries, other central executive authorities, local state administrations, city, town, and village mayors, regional council heads, managers of enterprises, institutions, and organizations of all forms of ownership have completed the training and successfully past the final test. | 01.11.2023 | 31.12.2025 | National Agency on Corruption Prevention |  | funds of international technical assistance | within international technical assistance funds | An online course for the leader of an organization has been developed and launched. At least 300 heads of ministries, other central executive authorities, local state administrations, city, town, and village mayors, regional council heads, managers of enterprises, institutions, and organizations of all forms of ownership have completed the training and successfully past the final test. | У межах IV кварталу 2023 року Національним агентством розроблено онлайн-курс для керівників "Розбудова доброчесних організацій" та розміщено його на навчальній платформі Study.NAZK. Станом на 31.12.2025 року всього на курс було зареєстровано 20 509 осіб, з яких 17 954 осіб отримали сертифікат про завершення курсу, а отже, успішно склали вихідне тестування. Відповідно до змісту заходу та визначеного показника його виконання передбачено розроблення та впровадження онлайн-курс для керівника організації навчання пройшли та успішно склали вихідне тестування щонайменше 300 керівників міністерств, інших центральних органів виконавчої влади, місцевих державних адміністрацій, міських, селищних, сільських голів, голів обласних рад, керівників підприємств, установ, організацій всіх форм власності. Таким чином, частина показника, яка стосується розроблення та впровадження онлайн-курсу, виконана у повному обсязі. Водночас наразі відсутня технічна можливість достовірно ідентифікувати належність слухачів до визначених категорій осіб, оскільки під час реєстрації на платформі не передбачено обов’язкового зазначення посади та місця роботи, а також відсутній функціонал коригування таких даних у профілі користувача. У зв’язку з цим на даний момент неможливо визначити кількість керівників визначених категорій серед усіх осіб, які пройшли вихідне тестування. З огляду на викладене, відповідний захід не може вважатись виконаним повністю. | Partially implemented | 0.0
1.1 | Shaping and implementing the state anticorruption policy | 1.1.4 The institution of authorized anticorruption units (officers) does not fully realize its potential due to insufficient guarantees of autonomy | 1.1.4.1 | The institution of authorized anticorruption units (officers) is operating with integrity as an independent network of leaders drawing on best international and domestic practices and receives comprehensive coordination support from the National Agency | 1.1.4.1.15 | Developing a general short-term professional development program for Category “A” civil servants on the role of the leader in fostering an environment of integrity in an organization | 01.03.2023 | 31.05.2023 | National Agency of Ukraine on Civil Service | National Agency on Corruption Prevention | state budget and/or international technical assistance funds | within the established budget allocations for the relevant year and/or international technical assistance funds | The professional development program has been developed. | Загальну короткострокову програму підвищення кваліфікації державних службовців категорії “А” щодо ролі керівника у побудові доброчесного середовища організації розроблено Вищою школою публічного управління спільно з Національним агентством з питань запобігання корупції. Наказом Вищої школи публічного управління від 13.07.2023 № 89-09 затверджено загальну короткострокову програму підвищення кваліфікації «Роль керівника у побудові доброчесного середовища організації» | Implemented | 0.0
1.1 | Shaping and implementing the state anticorruption policy | 1.1.4 The institution of authorized anticorruption units (officers) does not fully realize its potential due to insufficient guarantees of autonomy | 1.1.4.1 | The institution of authorized anticorruption units (officers) is operating with integrity as an independent network of leaders drawing on best international and domestic practices and receives comprehensive coordination support from the National Agency | 1.1.4.1.16 | Ensuring the training of Category “A” civil servants as part of the general short-term professional development program on the role of the leader in fostering an environment of integrity in an organization | 01.12.2024 | 31.12.2025 | National Agency of Ukraine on Civil Service | National Agency on Corruption Prevention | state budget and/or international technical assistance funds | within the established budget allocations for the relevant year and/or international technical assistance funds | At least 33 heads of agencies receive training each year. | Під час інформування за ІІ квартал 2025 року Національне агентство України з питань державної служби повідомило, що за період з 21–22 травня 2025 року забезпечено підвищення кваліфікації 33 державних службовців категорії «А» за загальною короткостроковою програмою «Роль керівника у побудові доброчесного середовища організації». Під час інформування за ІV квартал 2024 року Національне агентство України з питань державної служби повідомило, що у 2024 році забезпечено підвищення кваліфікації за загальною короткостроковою програмою підвищення кваліфікації державних службовців категорії «А» «Роль керівника у побудові доброчесного середовища організації» у кількості 34 осіб. Під час інформування за ІV квартал 2025 року Національне агентство України з питань державної служби повідомило, що Вищою школою публічного управління спільно з НАДС та НАЗК протягом 2023-2025 років забезпечено проведення навчання 100 державних службовців категорії “А” за загальною короткостроковою програмою підвищення кваліфікації «Роль керівника у побудові доброчесного середовища організації». Плани-графіки підвищення кваліфікації державних службовців, голів місцевих державних адміністрацій, їх перших заступників та заступників, посадових осіб місцевого самоврядування у Вищій школі публічного управління на 2024 та 2025 роки наведено у джерелах. З урахуванням викладеного вище можна констатувати досягнення показника виконання заходу, що свідчить про повне виконання заходу. | Implemented | 0.0
1.1 | Shaping and implementing the state anticorruption policy | 1.1.4 The institution of authorized anticorruption units (officers) does not fully realize its potential due to insufficient guarantees of autonomy | 1.1.4.2 | Anticorruption officers have, share, and implement understandable and effective standards of work developed by the National Agency jointly with other stakeholders based on substantiated qualification requirements, quality recruitment for the relevant positions, a sufficient supply of resources, and protection against interference | 1.1.4.2.1 | Developing and launching master’s degree educational programs (particularly cross-disciplinary ones) with a focus on anticorruption efforts as part of existing specialties and branches of knowledge jointly with partner institutions of higher education | 01.05.2023 | 31.12.2025 | Ministry of Education and Science of Ukraine | National Agency for Higher Education Quality Assurance, National Agency on Corruption Prevention | state budget | within the established budget allocations for the relevant year | A master’s degree program for anticorruption officers has been launched. Enrollment for the program has begun at the institution of higher education. The first group of students have been enrolled for the master’s degree program. | Протягом 2023-2025 років Міністерством освіти і науки України було розроблено та запроваджено разом з партнерськими закладами вищої освіти освітніх програм освітнього рівня магістр (зокрема міждисциплінарних) антикорупційного спрямування у межах діючих спеціальностей та галузей знань. 10.05.2023 на базі Київського національного економічного університету імені Вадима Гетьмана запущено освітньо-професійну програму «Комплаєнс-менеджмент організацій», яка стала першою в Україні комплексною освітньою програмою з підготовки менеджерів у сфері комплаєнсу та управління ризиками організації. На 30.10.2025 кількість здобувачів вищої освіти за програмою «Комплаєнс-менеджмент організацій» - 35 осіб. Спільно з фахівцями Київського національного університету ім. Тараса Шевченка у квітні 2024 року внесено зміни до освітньо-професійної програми «Місцеве самоврядування» та розроблено вибірковий блок дисциплін «Антикорупційний комплаєнс в системі місцевого самоврядування». Набрано групу студентів магістерської програми за спеціальністю «Публічне управління та адміністрування», які обрали навчання за зазначеним блоком дисциплін. У 2025 році розроблено тематичний план для вибіркового блоку дисциплін «Антикорупційний комплаєнс в системі місцевого самоврядування» та проведено навчання за цим вибірковим блоком дисциплін для студентів, які розпочали навчання на магістерській програмі «Публічне управління та адміністрування» у 2024 році. Також у 2023 році Національним університетом "Києво-Могилянська академія" запроваджено освітню програму "Антикорупційні студії" зі спеціальності 052 Політологія. У 2023 році на зазначену програму вступило 10 осіб, у 2024 - 8 осіб, а у 2025 - 23 особи. | Implemented | 0.0
1.1 | Shaping and implementing the state anticorruption policy | 1.1.4 The institution of authorized anticorruption units (officers) does not fully realize its potential due to insufficient guarantees of autonomy | 1.1.4.2 | Anticorruption officers have, share, and implement understandable and effective standards of work developed by the National Agency jointly with other stakeholders based on substantiated qualification requirements, quality recruitment for the relevant positions, a sufficient supply of resources, and protection against interference | 1.1.4.2.2 | Conducting the annual National Anticorruption Forum where anticorruption officers will unveil the best practices, discuss international and domestic practices and challenges in matters of prevention and detection of corruption | 01.06.2023 | 31.12.2025 | National Agency on Corruption Prevention |  | state budget and/or international technical assistance funds | within international technical assistance funds | Three National Anticorruption Forums have been held. The forums were attended by managers of domestic and international agencies and organizations and compliance officers of foreign companies. | 09.12.2025 відбувся Національний антикорупційний форум «Integrity2030: антикорупційна стратегія майбутнього»., в рамках якого було представлено й відзначено вдалі практики запобігання корупції й розбудови доброчесності, впроваджені різними органами та установами. 09.12.2024 відбувся Форум "Міжнародний день боротьби з корупцією: від Євромайдану до Євроінтеграції", в рамках якого було відзначено вдалі практики запобігання корупції й розбудови доброчесності, впроваджені різними органами та установами. 05.12.2023 в рамках Всеукраїнського антикорупційного форуму проведено захід «Доброчесність – спільна справа: від керівника до антикорупційного уповноваженого», в рамках якого антикорупційні уповноважені з різних регіонів держави, а також комплаєнс-офіцери іноземних компаній представили кращі практики розбудови ефективних систем запобігання та виявлення корупції. | Implemented | 0.0
1.1 | Shaping and implementing the state anticorruption policy | 1.1.4 The institution of authorized anticorruption units (officers) does not fully realize its potential due to insufficient guarantees of autonomy | 1.1.4.2 | Anticorruption officers have, share, and implement understandable and effective standards of work developed by the National Agency jointly with other stakeholders based on substantiated qualification requirements, quality recruitment for the relevant positions, a sufficient supply of resources, and protection against interference | 1.1.4.2.3 | Developing specialized online courses for professional development of anticorruption officers, covering the following topics: 1) vetting of draft acts of an agency or organization by the anticorruption officer; 2) management of corruption risks in operations of an agency or organization; 3) exercising powers relating to the protection of whistleblowers and reviewing reports about violations of anticorruption legislation; 4) preventing conflicts of interest and violations of other anticorruption restrictions; 5) conducting an anticorruption background check of contracting parties; 6) disseminating information and raising awareness in matters of compliance with anticorruption legislation; | 01.03.2023 | 31.12.2025 | National Agency on Corruption Prevention |  | state budget and/or international technical assistance funds | within the established budget allocations for the relevant year and/or international technical assistance funds | At least three online courses for anticorruption officers have been developed and launched. | Розроблено та впроваджено 6 спеціалізованих онлайн-курсів для уповноважених з питань запобігання та виявлення корупції: 1) візування антикорупційним уповноваженим проектів актів органу/організації - розроблено онлайн-курс для антикорупційних уповноважених "Візуй професійно!" 2) управління корупційними ризиками у діяльності органу/організації - спільно з партнерами розроблено онлайн-курс "Корпоративне управління та антикорупційний комплаєнс на підприємствах комунальної власності" 3) здійснення повноважень у сфері захисту викривачів та розгляд повідомлень про порушення вимог антикорупції - розроблено онлайн-курси для антикорупційних уповноважених: - "На захисті прав викривачів" - “Робота з Єдиним порталом повідомлень викривачів” 4) запобігання конфлікту інтересів та порушенню інших антикорупційних обмежень - розроблено онлайн-курс для антикорупційних уповноважених "Конфлікт інтересів: від виявлення до врегулювання" 5) проведення антикорупційної перевірки контрагентів - розроблено онлайн-курс для антикорупційних уповноважених “Знай, хто твій контрагент” З урахуванням викладеного вище можна констатувати досягнення показника виконання заходу, що свідчить про повне його виконання. | Implemented | 0.0
1.1 | Shaping and implementing the state anticorruption policy | 1.1.4 The institution of authorized anticorruption units (officers) does not fully realize its potential due to insufficient guarantees of autonomy | 1.1.4.2 | Anticorruption officers have, share, and implement understandable and effective standards of work developed by the National Agency jointly with other stakeholders based on substantiated qualification requirements, quality recruitment for the relevant positions, a sufficient supply of resources, and protection against interference | 1.1.4.2.4 | Ensuring the development of a general short-term professional development program for anticorruption officers based on the key functions of the professional standard titled “Anticorruption Officer”, followed by training | 01.03.2023 | 31.12.2025 | National Agency of Ukraine on Civil Service | National Agency on Corruption Prevention | state budget and/or international technical assistance funds | within the established budget allocations for the relevant year and/or international technical assistance funds | The general short-term professional development program for anticorruption officers has been developed and launched. | У межах ІІІ кварталу 2023 року розроблено такі програми: - загальна короткострокова програма підвищення кваліфікації «Ключові функції професійного стандарту Уповноважений з антикорупційної діяльності»» (затверджено наказом Вищої школи публічного управління від 15.09.2023 №99-ОД/23 та погоджено наказом НАДС від 28.09.2023 № 157-23); - загальна короткострокова програма підвищення кваліфікації уповноважених осіб з питань запобігання та виявлення корупції «Організація роботи з декларування у державному органі» (затверджено наказом Вищої школи від 08 травня 2023 р. № 60-ОД/23 та погоджено наказом НАДС від 13.06.2023 р. № 86-23); - загальна короткострокова програма підвищення кваліфікації уповноважених осіб з питань запобігання та виявлення корупції «Впровадження професійного стандарту антикорупційної роботи в діяльності органів влади та органів місцевого самоврядування» (затверджено наказом Вищої школи від 17.08.2023 р. № 95-ОД/23 та погоджено наказом НАДС від 08.09.2023 року № 143-23); - загальна короткострокова програма підвищення кваліфікації уповноважених осіб з питань запобігання та виявлення корупції «Управління корупційними ризиками» (затверджено наказом Вищої школи від 17.08.2023 р. № 95-ОД/23 та погоджено наказом НАДС від 08.09.2023 р. № 143-23). Вищою школою публічного управління спільно з НАЗК розроблено загальну короткострокову програму підвищення кваліфікації «Електронне декларування як один із механізмів фінансового контролю» (затверджено наказом Вищої школи від 30.06.2025 року № 96-ОД/25 та погоджено наказом НАДС від 09.10.2025 року №139-25). Протягом 2023-2025 років Вищою школою публічного управління спільно з партнерами забезпечено підвищення кваліфікації: 1. За загальною короткостроковою програмою підвищення кваліфікації уповноважених осіб з питань запобігання та виявлення корупції «Організація роботи з декларування у державному органі» у кількості 307 осіб. 2. За загальною короткостроковою програмою підвищення кваліфікації уповноважених осіб з питань запобігання та виявлення корупції «Впровадження професійного стандарту антикорупційної роботи в діяльності органів влади та органів місцевого самоврядування» у кількості 251 особи. 3. За загальною короткостроковою програмою підвищення кваліфікації уповноважених осіб з питань запобігання та виявлення корупції «Управління корупційними ризиками» у кількості 313 осіб. 4. За загальною короткостроковою програмою підвищення кваліфікації «Ключові функції професійного стандарту Уповноважений з антикорупційної діяльності» у кількості 102 осіб. 5. За загальною короткостроковою програмою підвищення кваліфікації «Електронне декларування як один із механізмів фінансового контролю» у кількості 98 осіб. З урахуванням викладеного вище можна констатувати досягнення показника виконання заходу, що свідчить про повне виконання заходу. | Implemented | 0.0
1.1 | Shaping and implementing the state anticorruption policy | 1.1.4 The institution of authorized anticorruption units (officers) does not fully realize its potential due to insufficient guarantees of autonomy | 1.1.4.2 | Anticorruption officers have, share, and implement understandable and effective standards of work developed by the National Agency jointly with other stakeholders based on substantiated qualification requirements, quality recruitment for the relevant positions, a sufficient supply of resources, and protection against interference | 1.1.4.2.5 | Updating the methodology of evaluation of the performance of anticorruption officers with a focus on evaluating their effectiveness in the priority areas of their work | 01.03.2023 | 31.07.2023 | National Agency on Corruption Prevention |  | state budget and/or international technical assistance funds | within the established budget allocations for the relevant year | The methodology has been updated and approved by an order of the National Agency. | The Methodology of Evaluation of the Performance of Anticorruption Units (Anticorruption Officers) was approved by the order of the National Agency on Corruption Prevention dated August 1, 2023 No. 164/23 | Implemented | 0.0
1.1 | Shaping and implementing the state anticorruption policy | 1.1.4 The institution of authorized anticorruption units (officers) does not fully realize its potential due to insufficient guarantees of autonomy | 1.1.4.3 | The following efforts of anticorruption officers have been prioritized: preventing the spread of corrupt practices, getting the public involved in the analysis and eradication of the risks of corruption in normative legal acts of government agencies and local self-government bodies | 1.1.4.3.2 | Drafting an order of the National Agency to amend the Model Regulation on the authorized unit (authorized officer) in matters of prevention and detection of corruption regarding specification of case of appointing an authorized persons on prevention and detection of corruption by assigning such functions to them | 01.01.2025 | 31.03.2025 | National Agency on Corruption Prevention |  | state budget | within the established budget allocations for the relevant year | The draft order has been drafted and publicized for a public discussion. | Станом на 31.03.2026 здійснюються підготовчі дії з метою організації розроблення проекту наказу, передбаченого заходом 1.1.4.3.2. | Not implemented | 0.0
1.1 | Shaping and implementing the state anticorruption policy | 1.1.4 The institution of authorized anticorruption units (officers) does not fully realize its potential due to insufficient guarantees of autonomy | 1.1.4.3 | The following efforts of anticorruption officers have been prioritized: preventing the spread of corrupt practices, getting the public involved in the analysis and eradication of the risks of corruption in normative legal acts of government agencies and local self-government bodies | 1.1.4.3.3 | Holding a public discussion of the draft order indicated in subclause 1.1.4.3.2, and ensuring its revision (if needed), issuance, and submission for state registration | 01.04.2025 | 31.05.2025 | National Agency on Corruption Prevention |  | state budget | within the established budget allocations for the relevant year | The public discussion has been conducted and its results have been made public. | Виконання заходу 1.1.4.3.3. не розпочато, оскільки потребує розроблення проекту наказу, визначеного заходом 1.1.4.3.2. Станом на 31.03.2026 відповідний проект наказу не розроблений. | Not implemented | 0.0
1.1 | Shaping and implementing the state anticorruption policy | 1.1.4 The institution of authorized anticorruption units (officers) does not fully realize its potential due to insufficient guarantees of autonomy | 1.1.4.3 | The following efforts of anticorruption officers have been prioritized: preventing the spread of corrupt practices, getting the public involved in the analysis and eradication of the risks of corruption in normative legal acts of government agencies and local self-government bodies | 1.1.4.3.4 | Supporting the state registration of the order indicated in subclause 1.1.4.3.2 and its official publication | 01.06.2025 | 31.07.2025 | National Agency on Corruption Prevention | Ministry of Justice of Ukraine | state budget | within the established budget allocations for the relevant year | The order has taken effect. | Виконання заходу 1.1.4.3.4. не розпочато, оскільки потребує розроблення проекту наказу, визначеного заходом 1.1.4.3.2. Станом на 31.03.2026 відповідний проект наказу не розроблений. | Not implemented | 0.0
1.1 | Shaping and implementing the state anticorruption policy | 1.1.4 The institution of authorized anticorruption units (officers) does not fully realize its potential due to insufficient guarantees of autonomy | 1.1.4.3 | The following efforts of anticorruption officers have been prioritized: preventing the spread of corrupt practices, getting the public involved in the analysis and eradication of the risks of corruption in normative legal acts of government agencies and local self-government bodies | 1.1.4.3.6 | Ensuring the training of anticorruption officers as part of the general short-term professional development program in corruption risk management | 01.06.2023 | 31.12.2025 | National Agency on Corruption Prevention | National Agency of Ukraine on Civil Service | state budget and/or international technical assistance funds | within the established budget allocations for the relevant year and/or international technical assistance funds | At least 300 anticorruption officers have completed training as part of the general short-term professional development program. | Національним агентством з питань запобігання корупції спільно з Вищою школою публічного управління розроблено та погоджено загальну короткострокову програму підвищення кваліфікації «Управління корупційними ризиками» (ЗК/2023/099), яку затверджено наказом Національного агентства України з питань державної служби від 08.09.2023 № 143-23. Протягом 2023-2025 років проведено 7 наборів навчання уповноважених осіб з питань запобігання та виявлення корупції за загальною короткостроковою програмою підвищення кваліфікації з питань управління корупційними ризиками: - 10-12.10.2023 (30 осіб) - 24-26.10.2023 (33 особи) - 31.10-02.11.2023 (40 осіб) - 16.07-18.07.2024 (50 осіб) - 28.10-30.10.2024 (75 осіб) - 15.04-17.04.2025 (47 осіб) - 29.07-31.07.2025 (53 особи) Загальна кількість учасників - 328 осіб. Також у 2024 році було реалізовано навчальний проєкт "Марафон практичних навичок уповноваженого: Управління корупційними ризиками". Навчання відбувалося на платформі Google Classroom. Протягом місяця учасники вдосконалювали свої навички, виконуючи реальні завдання з ідентифікації корупційних ризиків і визначення заходів впливу на них, а також отримуючи зворотний зв’язок від провідних експертів. З 445 зареєстрованих представників публічної служби та приватного сектору успішно завершило марафон понад 150 учасників. | Implemented | 0.0