## Заходи
№ Напрямку | Напрямок | Проблема | № ОСР | Назва ОСР | № Заходу | Назва заходу | Дата початку | Дата завершення | Головний виконавець | Співвиконавці | Джерела фінансування | Обсяги фінансування, тис.грн. | Показник (індикатор) виконання | Стан виконання | Статус виконання | Оцінка досягнення ОСР
2.7 | Healthcare, education, science, and social security | 2.7.1 Patients and doctors do not receive medications and medical devices in a timely manner and in full, in particular due to the incomplete transition to the new system of organization and control of medical procurement, and the incomplete regulation of the processes of identifying the needs for and accounting of medications | 2.7.1.1 | Procurement of medications and medical devices at the expense of the state and local budgets is carried out on a professional basis by centralized procurement organizations under transparent and detailed procedures in accordance with objective needs based on the quality and evidence of effectiveness of such products and devices. If necessary, specialized international organizations are also involved in centralized procurement | 2.7.1.1.1 | Development and submission to Cabinet of Ministers of Ukraine a draft regulation of Cabinet of Ministers of Ukraine ‘On implementation and operation of medical supplies and products electronic management system’ to ensure the following: 1) planning of procurement needs, including monitoring the delivery of goods in all stages; 2) performance of distribution and re-distribution of goods; 3) accounting and inventory of goods with indication of parameters; 4) goods monitoring (automation of operational reporting on goods availability in storages), inventory management with consideration of due distribution practice; 5) development of reporting documentation on goods availability and turnover in the storages and medical facilities, Pes with licenses to perform medical economic activities; 6) managing the goods stock with consideration of requirements, established by laws; 7) performance of electronic documentation turnover on goods accounting and distribution; 8) electronic accounting of targeted disposal of goods; 9) automated publication of the system data in the open data format. | 01.01.2024 | 31.08.2024 | Ministry of Health of Ukraine |  | state budget | within the established budget allocations for the relevant year | The resolution of the Cabinet of Ministers of Ukraine has been adopted. | На виконання заходу передбаченого п. 2.7.1.1.1. Державної антикорупційної програми на 2023-2025 роки, Міністерством охорони здоров'я України повідомлено, що: "на підставі успішної реалізації експериментального проекту з впровадження та функціонування електронної системи управління запасами лікарських засобів та медичних виробів “e-Stock” було прийнято постанову Кабінету Міністрів України від 07.03.2025 № 262 "Про затвердження Порядку функціонування електронної системи управління запасами лікарських засобів та медичних виробів “е-Stock”". З аналізу змісту вказаної постанови ідентифіковано, що останній корелюється із вимогами Державної антикорупційної програми на 2023-2025 роки. Разом із тим, з огляду на порушення строків виконання вказаного заходу, можемо констатувати, що останній виконаний повністю та невчасно. | Implemented | 0.0
2.7 | Healthcare, education, science, and social security | 2.7.1 Patients and doctors do not receive medications and medical devices in a timely manner and in full, in particular due to the incomplete transition to the new system of organization and control of medical procurement, and the incomplete regulation of the processes of identifying the needs for and accounting of medications | 2.7.1.1 | Procurement of medications and medical devices at the expense of the state and local budgets is carried out on a professional basis by centralized procurement organizations under transparent and detailed procedures in accordance with objective needs based on the quality and evidence of effectiveness of such products and devices. If necessary, specialized international organizations are also involved in centralized procurement | 2.7.1.1.2 | Development and approval of a technical task for functions of medical supplies and products electronic management system to ensure the following: 1) planning of needs, procurement and monitoring the delivery of goods in all stages; 2) performance of distribution and re-distribution of goods; 3) accounting and inventory of goods with indication of parameters; 4) goods monitoring (automation of operational reporting on goods availability in storages), inventory management with consideration of due distribution practice; 5) development of reporting documentation on goods availability and turnover in the storages and medical facilities, Pes with licenses to perform medical economic activities; 6) managing the goods stock with consideration of requirements, established by laws; 7) performance of electronic documentation turnover on goods accounting and distribution; 8) electronic accounting of targeted disposal of goods; 9) automated publication of the system data in the open data format. | 13.03.2025 | 13.06.2025 | Ministry of Health of Ukraine |  | state budget and/or international technical assistance funds | within the established budget allocations for the relevant year or amount of international technical assistance | The statement of work has been approved. | На виконання заходу передбаченого п. 2.7.1.1.2 Державної антикорупційної програми на 2023-2025 роки, Міністерством охорони здоров'я повідомлено, про розробку технічного завдання для функціоналу електронної системи обліку та управління запасами лікарських засобів і медичних виробів. Таким чином, можемо констатувати, що вказаний захід є виконаним вчасно та повністю. | Implemented | 0.0
2.7 | Healthcare, education, science, and social security | 2.7.1 Patients and doctors do not receive medications and medical devices in a timely manner and in full, in particular due to the incomplete transition to the new system of organization and control of medical procurement, and the incomplete regulation of the processes of identifying the needs for and accounting of medications | 2.7.1.1 | Procurement of medications and medical devices at the expense of the state and local budgets is carried out on a professional basis by centralized procurement organizations under transparent and detailed procedures in accordance with objective needs based on the quality and evidence of effectiveness of such products and devices. If necessary, specialized international organizations are also involved in centralized procurement | 2.7.1.1.3 | Designing software for expanding the functionality of the electronic system for registering and managing stocks of medications and medical devices in accordance with subclauses 2.7.1.1.2, 2.7.1.2.2 | 13.07.2025 | 31.12.2025 | Ministry of Health of Ukraine | Ministry of Digital Transformation of Ukraine, State Enterprise "Medical Procurement of Ukraine" | state budget and/or international technical assistance funds | within the established budget allocations for the relevant year and/or international technical assistance funds | The software design has been developed. | На виконання заходу передбаченого п. 2.7.1.1.3. Державної антикорупційної програми на 2023-2025 роки, Міністерством охорони здоров'я повідомлено, що: " 1. Потреба - Модуль розроблений та введений в експлуатацію. Функціонал включає збір, агрегування і затвердження потреб, зокрема: відкриття збору потреби по напрямках за різними методологіями згідно з переліком номенклатури; формування заявки ЗОЗ; узгодження заявок ДОЗ; формування зведеної потреби МОЗ. https://www.prostir.ua/?grants=stvorennya-avtomatyzovanoji-informatsijnoji-systemy-e-stock 2. Закупівля - Модуль розроблений та запущено пілот. Функціонал включає консолідацію закупівель відповідно до напрямів та відстеження закупівель за рахунок інтеграції з SAP Ariba та Prozorro, функціонал включатиме: операції з приймання лікарських засобів, медичних виробів та допоміжних засобів; операції з списання лікарських засобів, медичних виробів та допоміжних засобів на пацієнта та відділення та повернення медичних товарів; операції з переміщення товарів в межах закладу та передача між закладами (перерозподіл); операції з переміщення товарів в карантин, зняття з карантину, утилізація товарів; операції по інвентаризації товару. https://www.prostir.ua/?grants=tender-na-rozrobku-natsionalnoji-avtomatyzovanoji-informatsijnoji-systemy-e-stock-etap-2-modul-zakupivel 3. Облік - Розроблено. https://www.prostir.ua/?grants=tender-na-rozrobku-modulyu-e-stock-oblik 4. Логістика - Розроблено. https://www.prostir.ua/?grants=tender-na-rozrobku-modulyu-e-stock-lohistyka". З доданих виконавцем заходу скріншотів можливо констатувати, що відповідне програмне забезпечення функціоналу електронної системи обліку та управління запасами лікарських засобів та медичних виробів є розробленим. Відтак, наявне програмне забезпечення, що матиме можливість: 1) проводити збір потреб у лікарських виробах та медичних засобах від лікарень по всіх Україні; 2) агрегувати інформацію про проведенні закупівлі; 3) здійснювати моніторинг постачання медичних товарів і керування їх розподілом між лікарнями; 4) проводити облік наявних лікарських засобів та медичних виробів, їх рух та перерозподіл. З огляду на зазначене, захід передбачений п. 2.7.1.1.3 є виконаним вчасно та повністю. | Implemented | 0.0
2.7 | Healthcare, education, science, and social security | 2.7.1 Patients and doctors do not receive medications and medical devices in a timely manner and in full, in particular due to the incomplete transition to the new system of organization and control of medical procurement, and the incomplete regulation of the processes of identifying the needs for and accounting of medications | 2.7.1.1 | Procurement of medications and medical devices at the expense of the state and local budgets is carried out on a professional basis by centralized procurement organizations under transparent and detailed procedures in accordance with objective needs based on the quality and evidence of effectiveness of such products and devices. If necessary, specialized international organizations are also involved in centralized procurement | 2.7.1.1.4 | Implementing the functionality of the electronic system for registering and managing stocks of medications and medical devices in accordance with subclauses 2.7.1.1.2, 2.7.1.2.2 | 13.08.2026 | 31.12.2025 | Ministry of Health of Ukraine | Ministry of Digital Transformation of Ukraine, State Enterprise "Medical Procurement of Ukraine" | state budget and/or international technical assistance funds | within the established budget allocations for the relevant year or the amount of international technical assistance | The unified web portal is operating on an ongoing basis. | На виконання заходу передбаченого п. 2.7.1.1.4 Державної антикорупційної програми на 20234-2025 роки, Міністерством охорони здоров'я України, повідомлено, що: "наказом МОЗ від 31.12.2025 № 1994 було введено в дослідну експлуатацію модулі «Визначення потреби за номенклатурою», «Управління організаціями та користувачами», «Закупівлі», «Логістика», «Облік» Електронної системи управління запасами лікарських засобів та медичних виробів «e-Stock». Посилання на наказ: https://moz.gov.ua/uk/decrees/nakaz-moz-ukrayini-vid-31-12-2025-1994-pro-vvedennya-v-doslidnu-ekspluataciyu-elektronnoyi-sistemi-upravlinnya-zapasami-likarskih-zasobiv-ta-medichnih-virobiv-e-stock". Відповідно до вказаного наказу в дослідну експлуатацію введено Електронну систему управління запасами лікарських засобів та медичних виробів «e-Stock», зокрема модулі «Визначення потреби за номенклатурою», «Управління організаціями та користувачами», «Закупівлі», «Логістика», «Облік». З огляду на підтверджуючу інформацію, що надана від МОЗ, зокрема скріншоти, що відображають функціонування вказаних модулів, а також прийняте нормативно-правове регулювання вказаний захід може вважатися виконаним вчасно та повністю. | Implemented | 0.0
2.7 | Healthcare, education, science, and social security | 2.7.1 Patients and doctors do not receive medications and medical devices in a timely manner and in full, in particular due to the incomplete transition to the new system of organization and control of medical procurement, and the incomplete regulation of the processes of identifying the needs for and accounting of medications | 2.7.1.1 | Procurement of medications and medical devices at the expense of the state and local budgets is carried out on a professional basis by centralized procurement organizations under transparent and detailed procedures in accordance with objective needs based on the quality and evidence of effectiveness of such products and devices. If necessary, specialized international organizations are also involved in centralized procurement | 2.7.1.1.5 | Drafting and submitting to the Cabinet of Ministers of Ukraine a draft resolution of the Cabinet of Ministers of Ukraine, according to which local healthcare buyers (healthcare institutions, organizational units in charge of healthcare at regional state administrations and the Kyiv City State Administration) shall conduct procurement of the specified list of medications and medical devices with the use of an e-catalog | 01.03.2023 | 31.10.2023 | Ministry of Health of Ukraine | Ministry of Economy, Environment and Agriculture of Ukraine, State Enterprise "Medical Procurement of Ukraine" | state budget | within the established budget allocations for the relevant year or the amount of international technical assistance | The resolution of the Cabinet of Ministers of Ukraine has been adopted. | In order to implement the measure provided for in subclause 2.7.1.1.5 of the State Anti-Corruption Program for 2023-2025, the Ministry of Health of Ukraine has developed the Draft Resolution of the Cabinet of Ministers of Ukraine On Amendments to the Specifics of Public Procurement of Goods and Services for Customers Provided for by the Law of Ukraine On Public Procurement while Martial Law is in Effect in Ukraine and within 90 Days from the Day of Its Termination or Cancellation. On July 7, 2023, the Cabinet of Ministers of Ukraine adopted Resolution No. 686 On Amendments to the Specifics of Public Procurement of Goods and Services for Customers Provided for by the Law of Ukraine On Public Procurement while Martial Law is in Effect in Ukraine and within 90 Days from the Day of Its Termination or Cancellation. | Implemented | 0.0
2.7 | Healthcare, education, science, and social security | 2.7.1 Patients and doctors do not receive medications and medical devices in a timely manner and in full, in particular due to the incomplete transition to the new system of organization and control of medical procurement, and the incomplete regulation of the processes of identifying the needs for and accounting of medications | 2.7.1.3 | The specific considerations of procurement of medications and medical devices necessitated by the pandemic or carried out during the pandemic are established in such a way as to prevent corruption risks | 2.7.1.3.1 | Arranging an analytical study on the assessment of corruption risks in the procurement of medications and medical devices necessitated by the pandemic or conducted during the pandemic, with the presentation of statistical, economic, and other data, as well as the relevant proposals on how to prevent the identified corruption risks and to enhance the transparency and effectiveness of the procurement procedures in question | 01.03.2023 | 31.05.2023 | Ministry of Health of Ukraine | National Agency on Corruption Prevention | state budget | within the established budget allocations for the relevant year | The analytical study has been conducted and a report on its findings has been published. | In order to implement the measure provided for in subclause 2.7.1.3.1 of the State Anti-Corruption Program for 2023-2025 the Ministry of Health of Ukraine has prepared an analytical report on the assessment of corruption risks in the procurement of medications and medical devices necessitated by the pandemic or conducted during the pandemic. | Implemented | 0.0
2.7 | Healthcare, education, science, and social security | 2.7.1 Patients and doctors do not receive medications and medical devices in a timely manner and in full, in particular due to the incomplete transition to the new system of organization and control of medical procurement, and the incomplete regulation of the processes of identifying the needs for and accounting of medications | 2.7.1.3 | The specific considerations of procurement of medications and medical devices necessitated by the pandemic or carried out during the pandemic are established in such a way as to prevent corruption risks | 2.7.1.3.2 | Holding a presentation of the report on the findings of the analytical study indicated in subclause 2.7.1.3.1, followed by its discussion with stakeholders | 01.05.2023 | 30.06.2023 | Ministry of Health of Ukraine | National Agency on Corruption Prevention | state budget | within the established budget allocations for the relevant year | The discussion has been conducted and its results have been publicized. | На виконання заходу передбаченого п. 2.7.1.3.2 Державної антикорупційної програми на 2023-2025 роки, Міністерством охорони здоров'я України повідомлено, що: "аналітичний звіт опубліковано на офіційному вебсайті МОЗ в розділі Аналітичні звіти за посиланням -https://moz.gov.ua/analitichni-zviti та в розділі Запобігання корупції, за посиланням - https://moz.gov.ua/analitichnij-zvit-schodo-ocinki-korupcijnih-rizikiv-pid-chas-zakupivel-likarskih-zasobiv-ta-medichnih-virobiv-scho-zumovleni-pandemieju-abo-zdijsnjujutsja-pid-chas-pand. Також, на офіційному вебсайті МОЗ в розділі "Оголошення та анонси", за посиланням - (https://moz.gov.ua/article/announcements/zaproshennja-priednatisja-do-obgovorennja-analitichnogo-zvitu) опубліковано запрошення приєднатися до обговорення аналітичного звіту представників органів державної влади, неурядових організацій, міжнародних організацій, проектів міжнародної технічної допомоги, наукової спільноти.За результатами громадського обговорення зауважень та пропозицій до аналітичного звіту щодо оцінки корупційних ризиків під час закупівель лікарських засобів та медичних виробів, що зумовлені пандемією або здійснюються під час пандемії, не надходили. Звіт за результатами громадського обговорення опубліковано на офіційному вебсайті МОЗ в розділі "Громадське обговорення".Разом із тим, з огляду на те, що громадське обговорення не було проведено у формі публічних консультацій констатувати повне виконання вказаного заходу неможливо. Для виконання заходу необхідно провести обговорення аналітичного звіту у форматі публічної дискусії із запрошенням до участі у ньому заінтересованих органів влади, неурядових організацій та міжнародних організацій, які працюють над питанням запобігання корупції та мінімізації ризиків у діяльності Міністерства. Таким чином, можемо констатувати, що захід виконаний частково. | Partially implemented | 0.0
2.7 | Healthcare, education, science, and social security | 2.7.1 Patients and doctors do not receive medications and medical devices in a timely manner and in full, in particular due to the incomplete transition to the new system of organization and control of medical procurement, and the incomplete regulation of the processes of identifying the needs for and accounting of medications | 2.7.1.3 | The specific considerations of procurement of medications and medical devices necessitated by the pandemic or carried out during the pandemic are established in such a way as to prevent corruption risks | 2.7.1.3.3 | Drafting normative legal acts on amendments to normative legal acts, taking into account the findings of the analytical study indicated in subclause 2.7.1.3.1 (if needed) | 01.06.2023 | 31.07.2023 | Ministry of Health of Ukraine |  | state budget | within the established budget allocations for the relevant year | The draft normative legal acts have been publicized for a public discussion. | In order to implement the measure provided for in subclause 2.7.1.3.3. of the State Anti-Corruption Program for 2023-2025, based on the findings of the analytical study on the assessment of corruption risks in the procurement of medications and medical devices caused by the pandemic or carried out during the pandemic, the Ministry of Health of Ukraine stated that there was no need to develop draft normative legal acts on amendments to normative legal acts. | Implemented | 0.0
2.7 | Healthcare, education, science, and social security | 2.7.1 Patients and doctors do not receive medications and medical devices in a timely manner and in full, in particular due to the incomplete transition to the new system of organization and control of medical procurement, and the incomplete regulation of the processes of identifying the needs for and accounting of medications | 2.7.1.3 | The specific considerations of procurement of medications and medical devices necessitated by the pandemic or carried out during the pandemic are established in such a way as to prevent corruption risks | 2.7.1.3.4 | Holding a public discussion of the draft normative legal acts indicated in subclause 2.7.1.3.3 (if needed) | 01.08.2023 | 30.09.2023 | Ministry of Health of Ukraine |  | state budget | within the established budget allocations for the relevant year | The public discussion has been conducted and its results have been made public. | In order to implement the measure provided for in subclause 2.7.1.3.4 of the State Anti-Corruption Program for 2023-2025 the Ministry of Health of Ukraine reported that according to the findings of analytical study specified in subclause 2.7.1.3.1 the development of drafts of normative legal acts on amendments to normative legal acts is not provided for, therefore no public discussion was held. | Implemented | 0.0
2.7 | Healthcare, education, science, and social security | 2.7.1 Patients and doctors do not receive medications and medical devices in a timely manner and in full, in particular due to the incomplete transition to the new system of organization and control of medical procurement, and the incomplete regulation of the processes of identifying the needs for and accounting of medications | 2.7.1.3 | The specific considerations of procurement of medications and medical devices necessitated by the pandemic or carried out during the pandemic are established in such a way as to prevent corruption risks | 2.7.1.3.5 | Final revision (if needed) and approval of the draft normative legal acts indicated in subclause 2.7.1.3.3 (if needed) | 01.10.2023 | 31.10.2023 | Ministry of Health of Ukraine |  | state budget | within the established budget allocations for the relevant year | The amendments to the normative legal acts have been approved. | In order to implement the measure provided for in subclause 2.7.1.3.5 of the State Anti-Corruption Program for 2023-2025 the Ministry of Health of Ukraine established that according to the findings of analytical study specified in subclause 2.7.1.3.1 the development of drafts of normative legal acts on amendments to normative legal acts is not provided for, therefore amendments to normative legal acts were not approved. | Implemented | 0.0
2.7 | Healthcare, education, science, and social security | 2.7.1 Patients and doctors do not receive medications and medical devices in a timely manner and in full, in particular due to the incomplete transition to the new system of organization and control of medical procurement, and the incomplete regulation of the processes of identifying the needs for and accounting of medications | 2.7.1.4 | Ukrainian procurement organizations engaged in the procurement of medications and medical devices have independent supervisory boards | 2.7.1.4.1 | Forming a supervisory board at the state enterprise Medical Procurement of Ukraine using an impartial and transparent procedure | 01.01.2024 | 31.12.2024 | Ministry of Health of Ukraine |  | funds of international technical assistance | within the limits of the scope of international technical assistance | The supervisory board has been formed using an impartial and transparent procedure. | На виконання заходу передбаченого п. 2.7.1.4.1. Державної антикорупційної програми на 2023-2025 роки, Міністерством охорони здоров'я України, повідомлено, що: "розпорядженням КМУ від 24 грудня 2024 р. № 1316-р "Питання наглядової ради державного підприємства “Медичні закупівлі України” погоджено кандидатури на посади членів наглядової ради державного підприємства “Медичні закупівлі України”. Наказом МОЗ від 01.01.2025 року № 4 утворено Наглядову раду ДП "Медичні закупівлі України" та затверджено її склад". З офіційного веб-сайту МОЗ, стало відомо, що за результатами прозорого конкурсу до складу наглядової ради увійшли три незалежні члени: Ільзе Вінькеле (Латвія) — експертка зі стратегічного менеджменту та регуляторної діяльності, колишня міністерка соціальної політики та охорони здоров’я Латвії. Янне Харьюнпяя (Фінляндія) — фахівець з фінансового планування, операційного менеджменту та управління ризиками. Діна Немирович (Україна) — досвідчена аудиторка і фахівчиня зі стратегічного планування. Державу в наглядовій раді представлятимуть Юрій Джигир та Едем Адаманов. Окрім того, відкритий відбір незалежних членів наглядової ради відбувся за участю міжнародних партнерів — членів комісії з правом дорадчого голосу, серед яких: Дін Кернс, представник Бюро Всесвітньої організації охорони здоров’я в Україні, Рене Штайнер з Представництва ЄС в Україні, Робін Марц від Офісу охорони здоров'я USAID в Україні та Якуб Какєтек, представник Світового банку в Україні. Таким чином, можемо констатувати, що захід передбачений п. 2.7.1.4.1 Державної антикорупційної програми на 2023-2025 роки є виконаним вчасно та повністю. | Implemented | 0.0
2.7 | Healthcare, education, science, and social security | 2.7.1 Patients and doctors do not receive medications and medical devices in a timely manner and in full, in particular due to the incomplete transition to the new system of organization and control of medical procurement, and the incomplete regulation of the processes of identifying the needs for and accounting of medications | 2.7.1.5 | Standard catalogs and requirements for products procured in the healthcare sector are used in the procurement process | 2.7.1.5.1 | Drafting and submitting to the Cabinet of Ministers of Ukraine a draft law proposing amendments to the Law of Ukraine On Public Procurement with a view to preventing discrimination against bidders at the stage of qualification for the e-catalog (including in the list of qualified suppliers) | 01.09.2023 | 31.01.2024 | Ministry of Economy, Environment and Agriculture of Ukraine | State Enterprise "Prozorro", State Enterprise "Medical Procurement of Ukraine", State Institution "Professional Procurement" | state budget | within the established budget allocations for the relevant year | The draft law has been submitted to the Parliament of Ukraine. | На виконання заходу передбаченого п. 2.7.1.5.1. Державної антикорупційної програми на 2023-2025 роки, Міністерством економіки України, повідомлено, що: "проект Закону України “Про публічні закупівлі”, який розроблений Мінекономіки та поданий Кабінетом Міністрів України до Верховної Ради України (реєстр. № 11520 від 23.08.2024), 17.09.2024 прийнято за основу (у першому читанні)". З аналізу вказаного проекту Закону, можемо встановити, що ч. 18 ст. 14 значною мірою удосконалює порядок кваліфікації до електронного каталогу, унеможливлюючи дискримінацію учасників публічних закупівель на вказаному етапі. Відтак, з огляду на зміну законодавчого підходу щодо проведення кваліфікації до електронного каталогу, констатуємо, що законопроект № 11520 від 23.08.2024 р. корелюється з вимогами Державної антикорупційної програми. Таким чином, можемо констатувати, що захід передбачений п. 2.7.1.5.1 виконаний повністю, однак з урахуванням порушення строків зазначених Державною антикорупційною програмою, відтак невчасно. | Implemented | 0.0
2.7 | Healthcare, education, science, and social security | 2.7.1 Patients and doctors do not receive medications and medical devices in a timely manner and in full, in particular due to the incomplete transition to the new system of organization and control of medical procurement, and the incomplete regulation of the processes of identifying the needs for and accounting of medications | 2.7.1.5 | Standard catalogs and requirements for products procured in the healthcare sector are used in the procurement process | 2.7.1.5.2 | Drafting and submitting to the Cabinet of Ministers of Ukraine the draft resolution of the Cabinet of Ministers of Ukraine on amendments to the resolution of the Cabinet of Ministers of Ukraine dated September 14, 2020, No. 822 On Approval of the Procedure for Forming and Using the e-Catalog with a view to preventing discrimination against bidders at the stage of qualification for the e-catalog (including in the list of qualified suppliers) | з дня набрання чинності законом, зазначеним у підпункті 2.7.1.5.1 | три місяці з дня набрання чинності законом, зазначеним у підпункті 2.7.1.5.1 | Ministry of Economy, Environment and Agriculture of Ukraine | State Enterprise "Prozorro", State Enterprise "Medical Procurement of Ukraine", State Institution "Professional Procurement" | state budget | within the established budget allocations for the relevant year | The resolution of the Cabinet of Ministers of Ukraine has been adopted. | На виконання пункту 2.7.1.5.2 Державної антикорупційної програми на 2023–2025 роки Міністерство економіки, довкілля та сільського господарства України повідомило, що: "Мінекономіки розроблено і подано на КМУ проєкт постанови Кабінету Міністрів України “Про внесення змін до Порядку формування та використання електронного каталогу” (лист від 10.11.2025 № 3312-05/76305-01). Проєкт акта доопрацьовано на виконання рішення Урядового комітету, прийнятого на засіданні 05.12.2025 (пункт 5 Витягу з протоколу № 23), та надіслано до КМУ (лист від 04.01.2026 № 3312-03/522-0)". З огляду на надану звітну інформацію можна зробити висновок, що у межах звітного періоду здійснюється змістовне виконання вказаного заходу. Крім того, станом на дату проведення моніторингу констатовано, що Кабінетом Міністрів України прийнято постанову «Про внесення змін до Порядку формування та використання електронного каталогу» від 14 січня 2026 р. № 33, у межах якої, зокрема, передбачаються положення щодо недопущення дискримінації учасників на етапі кваліфікації до електронного каталогу (включення до переліку кваліфікованих постачальників), що корелюються з тими, що викладені у проєкті Закону України «Про публічні закупівлі» (реєстр. № 11520 від 23.08.2024). Водночас, з огляду на те, що вказаний законопроєкт не є прийнятим, а також потенційні зміни, яких може зазнати його редакція, що можуть вплинути на відповідне підзаконне нормативно-правове регулювання, у межах звітного періоду можемо констатувати, що захід, передбачений п. 2.7.1.5.2, виконано частково. | Partially implemented | 0.0
2.7 | Healthcare, education, science, and social security | 2.7.1 Patients and doctors do not receive medications and medical devices in a timely manner and in full, in particular due to the incomplete transition to the new system of organization and control of medical procurement, and the incomplete regulation of the processes of identifying the needs for and accounting of medications | 2.7.1.6 | Clear rules and procedures have been established for identifying and resolving conflicts of interest of members of working and expert groups (primarily those that support the procurement of medical products at the expense of the state budget and determine the lists of products to be procured), and their strict observance in practice is ensured | 2.7.1.6.1 | Arranging an analytical study of the cases of conflict of interest involving members of consultative, auxiliary, and other advisory bodies at the Ministry of Health (including those supporting the procurement of medical products at the expense of the state budget and determine the list of products to be procured), which will include proposals on ways to improve the current legislation pertaining to these issues | 01.03.2023 | 31.05.2023 | Ministry of Health of Ukraine | National Agency on Corruption Prevention | state budget | within the established budget allocations for the relevant year | The analytical report has been prepared and made public. | In order to implement the measure provided for in subclause 2.7.1.6.1 of the State Anti-Corruption Program for 2023-2025 the Ministry of Health of Ukraine conducted an analytical study of the cases of conflict of interest involving members of consultative, auxiliary, and other advisory bodies at the Ministry of Health of Ukraine. The findings of the analytical study are published on the official website of the Ministry of Health of Ukraine in the "Analytical reports" section. | Implemented | 0.0
2.7 | Healthcare, education, science, and social security | 2.7.1 Patients and doctors do not receive medications and medical devices in a timely manner and in full, in particular due to the incomplete transition to the new system of organization and control of medical procurement, and the incomplete regulation of the processes of identifying the needs for and accounting of medications | 2.7.1.6 | Clear rules and procedures have been established for identifying and resolving conflicts of interest of members of working and expert groups (primarily those that support the procurement of medical products at the expense of the state budget and determine the lists of products to be procured), and their strict observance in practice is ensured | 2.7.1.6.2 | Holding a presentation of the report on the findings of the analytical study indicated in subclause 2.7.1.6.1, followed by its expert discussion | 01.05.2023 | 30.06.2023 | Ministry of Health of Ukraine | National Agency on Corruption Prevention | state budget | within the established budget allocations for the relevant year | The conclusions and recommendations outlined in the analytical report have been discussed with the participation of representatives of government agencies, NGOs, international organizations, international technical assistance projects, and the academic community. | На виконання заходу передбаченого п. 2.7.1.6.2. Державної антикорупційної програми на 2023-2025 роки, Міністерством охорони здоров'я України повідомлено, що: " аналітичний звіт опубліковано на офіційному вебсайті МОЗ в розділі Аналітичні звіти за посиланням - https://moz.gov.ua/analitichni-zviti) та в розділі Запобігання корупції за посиланням - https://moz.gov.ua/analitichnij-zvit-schodo-vipadkiv-konfliktu-interesiv-chleniv-konsultativnih-dopomizhnih-ta-inshih-doradchih-organiv-pri-moz. Також, на офіційному вебсайті МОЗ в розділі "Оголошення та анонси" за посиланням - https://moz.gov.ua/article/announcements/zaproshennja-priednatisja-do-obgovorennja-analitichnogo-zvit опубліковано запрошення приєднатися до обговорення аналітичного звіту представників органів державної влади, неурядових організацій, міжнародних організацій, проектів міжнародної технічної допомоги, наукової спільноти.За результатами громадського обговорення зауважень та пропозицій до аналітичного звіту щодо випадків конфлікту інтересів членів консультативних, допоміжних та інших дорадчих органів при МОЗ, не надходило. Звіт за результатами громадського обговорення опубліковано на офіційному вебсайті МОЗ в розділі "Громадське обговорення". Разом із тим, констатувати повне виконання вказаного заходу не видається за можливе, адже не було проведено публічного громадського обговорення аналітичного звіту. Для виконання заходу необхідно провести обговорення аналітичного звіту у форматі публічної дискусії із запрошенням до участі у ньому заінтересованих органів влади, неурядових організацій та міжнародних організацій, які працюють над питанням запобігання корупції та мінімізації ризиків у діяльності Міністерства. Відтак, захід є таким, що виконаний частково. | Partially implemented | 0.0
2.7 | Healthcare, education, science, and social security | 2.7.1 Patients and doctors do not receive medications and medical devices in a timely manner and in full, in particular due to the incomplete transition to the new system of organization and control of medical procurement, and the incomplete regulation of the processes of identifying the needs for and accounting of medications | 2.7.1.6 | Clear rules and procedures have been established for identifying and resolving conflicts of interest of members of working and expert groups (primarily those that support the procurement of medical products at the expense of the state budget and determine the lists of products to be procured), and their strict observance in practice is ensured | 2.7.1.6.3 | Drafting and submitting to the Cabinet of Ministers of Ukraine the draft law that incorporates the findings of the analytical report indicated in subclause 2.7.1.6.1, which: 1) makes improvements to normative legal regulation of instances of discovery and resolution of conflicts of interest involving members of consultative, auxiliary, and other advisory bodies at the Ministry of Health (including those supporting the procurement of medical products at the expense of the state budget and determine the list of products to be procured); 2) provides for the grounds and procedure for holding individuals liable under law for violating the requirements with respect to the prevention and resolution of conflicts of interest; 3) provides for the procedure for reviewing reports by individuals or legal entities about signs of conflicts of interest involving members of consultative, auxiliary, and other advisory bodies. | 01.06.2023 | 31.12.2023 | Ministry of Health of Ukraine | National Agency on Corruption Prevention | state budget | within the established budget allocations for the relevant year | The draft law has been submitted to the Parliament of Ukraine. | На виконання заходу передбаченого п. 2.7.1.6.3. Державної антикорупційної програми на 2023-2025 роки, Міністерством охорони здоров'я повідомлено, що: "протягом звітного періоду розроблено проєкт наказу МОЗ "Про внесення змін в Примірне положення про утворення та діяльність консультативних, дорадчих та інших допоміжних органів при Міністерстві охорони здоров’я України" в частині доповнення розділу "Запобігання та врегулювання конфлікту інтересів" в якому, зокрема, передбачено: особливості врегулювання конфлікту інтересів у членів Дорадчих органів; підстави та порядок притягнення членів Дорадчих органів до відповідальності за порушення вимог щодо запобігання та врегулювання конфлікту інтересів; порядок розгляду повідомлень фізичних та юридичних осіб про ознаки конфлікту інтересів членів Дорадчих органів, та який затверджено 15.04.2025 № 646". З аналізу наказу МОЗ "Про внесення змін в Примірне положення про утворення та діяльність консультативних, дорадчих та інших допоміжних органів при Міністерстві охорони здоров’я України" констатовано визначення порядку запобігання та врегулювання конфлікту інтересів членів Дорадчих органів при МОЗ. Разом із тим, з огляду на те, що відповідне правове регулювання встановлено на рівні підзаконного нормативно-правового акту, а також з порушенням строків визначених Державною антикорупційною програмою на 2023-2025 роки, можемо констатувати, що вказаний захід виконаний частково та невчасно. | Partially implemented | 0.0
2.7 | Healthcare, education, science, and social security | 2.7.1 Patients and doctors do not receive medications and medical devices in a timely manner and in full, in particular due to the incomplete transition to the new system of organization and control of medical procurement, and the incomplete regulation of the processes of identifying the needs for and accounting of medications | 2.7.1.6 | Clear rules and procedures have been established for identifying and resolving conflicts of interest of members of working and expert groups (primarily those that support the procurement of medical products at the expense of the state budget and determine the lists of products to be procured), and their strict observance in practice is ensured | 2.7.1.6.4 | Creating a section on the official website of the Ministry of Health with complete information about consultative, auxiliary, and other advisory bodies that have been formed and are operating at the Ministry, with a focus on the following aspects: 1) individual members of such bodies and their positions; 2) the agenda of meetings attended by them; 3) the decisions made. | 01.03.2023 | 31.07.2023 | Ministry of Health of Ukraine |  | state budget | within the established budget allocations for the relevant year | The relevant information has been published on the official website of the Ministry of Health. | In order to implement the measure provided for in subclause 2.7.1.6.4 of the State Anti-Corruption Program for 2023-2025 the Ministry of Health of Ukraine has created the section of its official website named "Consultative, Auxiliary, and Other Advisory Bodies at the Ministry of Health of Ukraine", which contains information about the Advisory bodies that have been formed and are operating at the Ministry of Health of Ukraine, with following aspects: individual members of such bodies and their positions, the agenda of meetings attended by them, the decisions made. | Implemented | 0.0
2.7 | Healthcare, education, science, and social security | 2.7.1 Patients and doctors do not receive medications and medical devices in a timely manner and in full, in particular due to the incomplete transition to the new system of organization and control of medical procurement, and the incomplete regulation of the processes of identifying the needs for and accounting of medications | 2.7.1.6 | Clear rules and procedures have been established for identifying and resolving conflicts of interest of members of working and expert groups (primarily those that support the procurement of medical products at the expense of the state budget and determine the lists of products to be procured), and their strict observance in practice is ensured | 2.7.1.6.5 | Creating a channel for reporting conflicts of interest involving members of the consultative, auxiliary, and other advisory bodies at the Ministry of Health by the public and business community | 01.03.2023 | 30.09.2023 | Ministry of Health of Ukraine |  | state budget | within the established budget allocations for the relevant year | The channel for reports is functioning. | In order to implement the measure provided for in subclause 2.7.1.6.4 of the State Anti-Corruption Program for 2023-2025 the Ministry of Health of Ukraine has created a message channel for reporting conflicts of interest involving members of the consultative, auxiliary, and other advisory bodies at the Ministry of Health of Ukraine in the section of its official website named "Consultative, Auxiliary, and Other Advisory Bodies at the Ministry of Health of Ukraine". The message channel is functioning. | Implemented | 0.0
2.7 | Healthcare, education, science, and social security | 2.7.1 Patients and doctors do not receive medications and medical devices in a timely manner and in full, in particular due to the incomplete transition to the new system of organization and control of medical procurement, and the incomplete regulation of the processes of identifying the needs for and accounting of medications | 2.7.1.7 | Clear ethical rules of interaction between pharmaceutical companies and healthcare professionals have been defined, which make it impossible to abuse the prescription of medicines to patients; legal liability for violations of these rules has been established | 2.7.1.7.1 | Drafting and submitting to the Cabinet of Ministers of Ukraine a draft law proposing to amend the Fundamentals of Ukrainian Healthcare Legislation, which defines: 1) the list of prohibited forms of interaction of medical workers and healthcare institutions with business entities that manufacture and/or distribute medications and medical devices (medical products) and auxiliary means of rehabilitation and with their representatives (in particular: medical workers and healthcare institutions are prohibited from accepting samples of medications, medical devices, souvenirs, and branded products of pharmaceutical companies for purposes of promotion; pharmaceutical companies are prohibited from launching loyalty programs for doctors); 2) the ethical principles to be upheld by medical workers when prescribing medications and medical devices to patients; 3) disciplinary and administrative liability (under Article 442 of the Code of Ukraine on Administrative Offenses) for violations of restrictions applicable to the forms of interaction of medical workers with business entities manufacturing and/or distributing medications, medical devices (medical products), and auxiliary means of rehabilitation. | 01.03.2023 | 30.11.2023 | Ministry of Health of Ukraine |  | state budget | within the established budget allocations for the relevant year | The draft law has been submitted to the Parliament of Ukraine. | На виконання заходу передбаченого п. 2.7.1.7.1 Державної антикорупційної програми на 2023-2025 роки, Міністерством охорони здоров'я України повідомлено, що: "21.08.2024 року Верховною Радою України прийнято Закон України № 3911-IX "Про внесення змін до деяких законів України щодо врегулювання окремих питань у сферах охорони здоров’я, реабілітації, соціального захисту та державної реєстрації окремих об’єктів санітарних заходів", яким внесено зміни до статей 78 та 78 - 1 Основ законодавства України про охорону здоров’я та передбачено перелік заборонених форм взаємодії медичних працівників з суб’єктами господарювання, які здійснюють виробництво та/або реалізацію лікарських засобів, медичних виробів (виробів медичного призначення), допоміжних засобів реабілітації, їх представників (зокрема: заборона отримання медичними працівниками та закладами охорони здоров’я з метою просування зразків лікарських засобів, медичних виробів, сувенірної та брендованої продукції фармацевтичних компаній; заборона запровадження програм лояльності для лікарів з боку фармацевтичних компаній) та встановлені етичні засади, яких необхідно дотримуватися медичним працівникам під час призначення пацієнтам лікарських засобів, медичних виробів. Закон № 3911-IX набрав чинності 18.12.2024. В той же час статтею 44-2 Кодексу України про адміністративні правопорушення встановлено, що порушення обмежень, встановлених для медичних і фармацевтичних працівників під час здійснення ними професійної діяльності: - тягне за собою накладення штрафу у розмірі трьохсот неоподатковуваних мінімумів доходів громадян. Ті самі дії, вчинені повторно протягом року після накладення адміністративного стягнення за порушення, передбачені частиною першою цієї статті: - тягнуть за собою накладення штрафу у розмірі однієї тисячі двохсот неоподатковуваних мінімумів доходів громадян".З аналізу вказаного Закону, можемо встановити, що: ст. 78, визначає, зокрема такі ключові етичні засади, взаємодії медичних, фармацевтичних працівників із пацієнтами, як: -бути чесними та неупередженими у всіх професійних взаємодіях, у тому числі прямо або опосередковано пов’язаних із проведенням рекламних або промоційних заходів суб’єктами господарювання, які здійснюють виробництво та/або реалізацію лікарських засобів, медичних виробів, допоміжних засобів реабілітації, а також їх представниками; -не використовувати свої повноваження або своє становище та пов’язані з цим можливості в особистих інтересах, інтересах близьких їм осіб і не отримувати від них особисту вигоду або вигоду для близьких їм осіб; - призначати та відпускати лікарські засоби, медичні вироби, допоміжні засоби реабілітації без впливу приватних інтересів; -усвідомлювати відповідальність перед пацієнтом під час надання йому медичної, фармацевтичної та/або реабілітаційної допомоги. У свою чергу відповідно до ст. 78-1 визначаються ключові обмеження, встановлені для медичних, фармацевтичних працівників та фахівців з реабілітації під час здійснення ними професійної діяльності. Разом із тим, незважаючи на те, що Закон № 3911-IX відповідає Державній антикорупційній програмі на 2023-2025 роки, у контексті встановлення ключових засад взаємодії медичних, фармацевтичних працівників, а також переліку заборонених форм взаємодії, можемо констатувати, що проект акту не містить окремих положень, що визначені Державною антикорупційною програмою на 2023-2025 роки, зокрема законопроектом не встановлюється що за порушення обмежень щодо форм взаємодії медичних працівників з суб’єктами господарювання, які здійснюють виробництво та/або реалізацію лікарських засобів, медичних виробів (виробів медичного призначення), допоміжних засобів реабілітації, медичні працівники несуть дисциплінарну та адміністративну відповідальність (за статтею 44-2 Кодексу України про адміністративні правопорушення). Положення ст. 80 Закону України "Про Основи законодавства України про охорону здоров'я" визначає виключно загальну, а не спеціальну норму про види відповідальності, що можуть бути застосованими до осіб, які порушують законодавство про охорону здоров'я. Відтак, такий підхід до виконання заходу 2.7.1.7.1 видається частковим та не спрямованим на те, щоб нормативно закріпити можливість притягувати медичних та фармацевтичних працівників до адміністративної та дисциплінарної відповідальності за порушення обмежень щодо взаємодії з суб’єктами господарювання, які здійснюють виробництво та/або реалізацію лікарських засобів, медичних виробів (виробів медичного призначення), допоміжних засобів реабілітації, а також чітко регламентувати правила дозволеної взаємодії медичних та фармацевтичних працівників. З огляду на це, можемо констатувати, що захід виконаний вчасно, але частково. | Partially implemented | 0.0
2.7 | Healthcare, education, science, and social security | 2.7.1 Patients and doctors do not receive medications and medical devices in a timely manner and in full, in particular due to the incomplete transition to the new system of organization and control of medical procurement, and the incomplete regulation of the processes of identifying the needs for and accounting of medications | 2.7.1.7 | Clear ethical rules of interaction between pharmaceutical companies and healthcare professionals have been defined, which make it impossible to abuse the prescription of medicines to patients; legal liability for violations of these rules has been established | 2.7.1.7.2 | Development of instruction on promotion rules, specifying the requirements to interaction between entities conducting medical and/or pharmaceutical activities, and pharmaceutical companies | 19.09.2024 | 19.03.2025 | Ministry of Health of Ukraine |  | state budget and/or international technical assistance funds | within the established budget allocations for the relevant year or funds of international technical assistance | Ministry of Health of Ukraine draft order has been developed | На виконання заходу передбаченого п. 2.7.1.7.2. Державної антикорупційної програми на 2023-2025 роки, Міністерством охорони здоров'я України повідомлено, що: "затверджено та оприлюднено на офіційному вебсайті МОЗ наказ Міністерства охорони здоров'я України від 12.06.2025 № 962 "Про затвердження Настанови «Належна практика з промоції лікарських засобів", який набрав чинності від моменту оприлюднення на сайті МОЗ". З аналізу відповідного наказу МОЗ «Про затвердження настанови «Належна практика з промоції лікарських засобів» можемо встановити, що останній встановлює вимоги до взаємодії між особами, які провадять медичну чи фармацевтичну діяльність, і фармацевтичними компаніями. Відтак, встановлюються правила щодо промоції лікарських засобів, вимоги до промоційних матеріалів та правила їх поширення, а також правила організації, проведення, спонсорства спеціалізованих заходів з медичної, фармацевтичної та/ або реабілітаційної тематики. Таким чином, можемо констатувати, що захід виконаний повністю, однак з порушенням строків визначених Державною антикорупційною програмою. | Implemented | 0.0
2.7 | Healthcare, education, science, and social security | 2.7.1 Patients and doctors do not receive medications and medical devices in a timely manner and in full, in particular due to the incomplete transition to the new system of organization and control of medical procurement, and the incomplete regulation of the processes of identifying the needs for and accounting of medications | 2.7.1.7 | Clear ethical rules of interaction between pharmaceutical companies and healthcare professionals have been defined, which make it impossible to abuse the prescription of medicines to patients; legal liability for violations of these rules has been established | 2.7.1.7.3 | Development and performance of online training course for entities conducting medical and/or pharmaceutical activities, regarding interaction between the pharmaceutical companies and medical workers in accordance with the approved instruction on promotion rules, indicated in subclause 2.7.1.7.2 | 12.06.2025 | 12.09.2025 | Ministry of Health of Ukraine |  | state budget and/or international technical assistance funds | within the established budget allocations for the relevant year or funds of international technical assistance | Registration for the online course has been made available | На виконання заходу передбаченого п. 2.7.1.7.3. Державної антикорупційної програми на 2023-2025 роки, Міністерством охорони здоров'я України повідомлено, що: "наразі МОЗ розробляється онлайн-тренінг для лікарів, фармацевтів та представників фармацевтичного бізнесу, який допоможе практично застосовувати вимоги Настанови (наказ Міністерства охорони здоров'я України від 12.06.2025 № 962 "Про затвердження Настанови «Належна практика з промоції лікарських засобів") та формувати культуру належної промоції". Таким чином, можемо констатувати, що у межах звітного періоду розпочато змістовне виконання вказаного заходу Державної антикорупційної програми. | Implemented | 0.0