## Заходи
№ Напрямку | Напрямок | Проблема | № ОСР | Назва ОСР | № Заходу | Назва заходу | Дата початку | Дата завершення | Головний виконавець | Співвиконавці | Джерела фінансування | Обсяги фінансування, тис.грн. | Показник (індикатор) виконання | Стан виконання | Статус виконання | Оцінка досягнення ОСР
1.2 | Instilling a negative attitude towards corruption | 1.2.1 Everyday corrupt practices are an established norm of conduct and are not perceived as violations of moral or legal norms. There is no consistent demand from the population for public officials to uphold the prescribed rules of ethical conduct and integrity | 1.2.1.1 | The overall level of tolerance of corruption in Ukraine has decreased owing to the integration of anticorruption topics into educational curricula at all levels, which includes instilling in society a stable perception of corruption as a phenomenon that significantly slows down the socioeconomic development of the country, of corrupt officials as persons who make public administration ineffective, and the realization that dishonest practices, even when they look like a convenient opportunity to solve their issues in the short term, are always disadvantageous for individuals and society in the medium and long term | 1.2.1.1.1 | Supplementing the State Standard of Vocational Secondary Education: a) with a list of value orientations aimed at instilling intolerance of corruption and manifestations of dishonesty; b) with a list of tasks essential to acquiring civic and social competencies as part of instilling intolerance of corruption in all of its manifestations, an understanding of the inadmissibility of tolerating inequality and dishonesty, as well as the readiness to abandon unscrupulous practices when solving problems | 01.03.2023 | 31.12.2023 | Ministry of Education and Science of Ukraine |  | state budget | within the established budget allocations for the relevant year | The state standard has been supplemented with value orientations aimed at instilling intolerance of corruption and manifestations of dishonesty, as well as tasks essential to acquiring civic and social competencies as part of instilling intolerance of corruption in all of its manifestations. | За повідомленням Міністерства освіти і науки України, станом на 30.09.2024 р. Державний стандарт профільної середньої освіти затверджено постановою КМУ від 25 липня 2024 р. № 851 "Про затвердження Державного стандарту профільної середньої освіти" https://www.kmu.gov.ua/npas/pro-zatverdzhennia-derzhavnoho-standartu-profilnoi-serednoi-osvity-851-250724 | Implemented | 0.0
1.2 | Instilling a negative attitude towards corruption | 1.2.1 Everyday corrupt practices are an established norm of conduct and are not perceived as violations of moral or legal norms. There is no consistent demand from the population for public officials to uphold the prescribed rules of ethical conduct and integrity | 1.2.1.1 | The overall level of tolerance of corruption in Ukraine has decreased owing to the integration of anticorruption topics into educational curricula at all levels, which includes instilling in society a stable perception of corruption as a phenomenon that significantly slows down the socioeconomic development of the country, of corrupt officials as persons who make public administration ineffective, and the realization that dishonest practices, even when they look like a convenient opportunity to solve their issues in the short term, are always disadvantageous for individuals and society in the medium and long term | 1.2.1.1.2 | Supplementing the objective of the “Civic Accountability” cross-cutting content thread with concepts essential to instilling intolerance of corruption and adherence to integrity strategies | 01.03.2023 | 31.12.2023 | Ministry of Education and Science of Ukraine | State Scientific Institution “Institute of Education Content Modernization” | state budget | within the established budget allocations for the relevant year | Amendments have been introduced into the Model Curriculum of General Secondary Education Institutions of the 2nd Degree, approved by the order of the Ministry of Education and Science dated April 20, 2018, No. 405 | The order of the Ministry of Education and Science of Ukraine On Amendments to Certain Orders of the Ministry of Education and Science of Ukraine dated February 07, 2024 No. 142 amended the Model Educational Program of General Secondary Education Institutions of the Secondary Level approved by the order of the Ministry of Education and Science of Ukraine dated April 20, 2018 No. 405 (as amended) regarding the content line "Civic Accountability", which includes provisions on the instilling intolerance of corruption and adherence to integrity strategies, the establishment of a culture of integrity and respect for the rule of law, prevention of corruption and corruption-related offences. | Implemented | 0.0
1.2 | Instilling a negative attitude towards corruption | 1.2.1 Everyday corrupt practices are an established norm of conduct and are not perceived as violations of moral or legal norms. There is no consistent demand from the population for public officials to uphold the prescribed rules of ethical conduct and integrity | 1.2.1.1 | The overall level of tolerance of corruption in Ukraine has decreased owing to the integration of anticorruption topics into educational curricula at all levels, which includes instilling in society a stable perception of corruption as a phenomenon that significantly slows down the socioeconomic development of the country, of corrupt officials as persons who make public administration ineffective, and the realization that dishonest practices, even when they look like a convenient opportunity to solve their issues in the short term, are always disadvantageous for individuals and society in the medium and long term | 1.2.1.1.3 | Developing educational and methodological materials to be used to accomplish the objective of the “Civic Accountability” cross-cutting content thread in terms of instilling in the context of corruption and adherence to integrity strategies (with the possible involvement of NGOs and international technical assistance projects in this activity) | 01.03.2023 | 31.01.2024 | National Agency on Corruption Prevention |  | state budget and/or international technical assistance funds | within the established budget allocations for the relevant year | The teaching methods materials have been developed. | According to the National Agency on Corruption Prevention, as of March 31, 2024, "a complex of exercises that teachers can use in the educational process has been prepared. Comprehensive work was carried out to disseminate the developed materials". | Implemented | 0.0
1.2 | Instilling a negative attitude towards corruption | 1.2.1 Everyday corrupt practices are an established norm of conduct and are not perceived as violations of moral or legal norms. There is no consistent demand from the population for public officials to uphold the prescribed rules of ethical conduct and integrity | 1.2.1.1 | The overall level of tolerance of corruption in Ukraine has decreased owing to the integration of anticorruption topics into educational curricula at all levels, which includes instilling in society a stable perception of corruption as a phenomenon that significantly slows down the socioeconomic development of the country, of corrupt officials as persons who make public administration ineffective, and the realization that dishonest practices, even when they look like a convenient opportunity to solve their issues in the short term, are always disadvantageous for individuals and society in the medium and long term | 1.2.1.1.4 | Submitting documents to obtain the stamp of approval for use in the educational process for the educational and methodological handbook on instilling intolerance of corruption and adherence to integrity strategies | 01.02.2024 | 30.06.2024 | National Agency on Corruption Prevention | Ministry of Education and Science of Ukraine | state budget and/or international technical assistance funds | within the established budget allocations for the relevant year and/or international technical assistance funds | The educational and methodological handbook have passed expert examination. The expert committee has reviewed the expert opinions on the feasibility of using the handbook in the educational process. | Навчально-методичний посібник «PRO доброчесність» із рекомендаціями щодо досягнення мети наскрізної змістової лінії «Громадянська відповідальність» в частині формування нетерпимості до корупції та слідуванням доброчесних стратегій поведінки пройшов експертизу та отримав гриф «Схвалено до використання в освітньому процесі» (рішення експертної комісії з громадянської та історичної освітньої галузі від 08.07.2025 (протокол № 9), зареєстрований в Каталозі надання грифів навчальній літературі та навчальним програмам за № БО-0226-25). | Implemented | 0.0
1.2 | Instilling a negative attitude towards corruption | 1.2.1 Everyday corrupt practices are an established norm of conduct and are not perceived as violations of moral or legal norms. There is no consistent demand from the population for public officials to uphold the prescribed rules of ethical conduct and integrity | 1.2.1.1 | The overall level of tolerance of corruption in Ukraine has decreased owing to the integration of anticorruption topics into educational curricula at all levels, which includes instilling in society a stable perception of corruption as a phenomenon that significantly slows down the socioeconomic development of the country, of corrupt officials as persons who make public administration ineffective, and the realization that dishonest practices, even when they look like a convenient opportunity to solve their issues in the short term, are always disadvantageous for individuals and society in the medium and long term | 1.2.1.1.5 | Developing recommendations on the implementation of the “Civic Accountability” cross-cutting content thread in the educational process to the extent of instilling intolerance of corruption and adherence to integrity strategies | 01.07.2024 | 30.09.2024 | Ministry of Education and Science of Ukraine | National Agency on Corruption Prevention | state budget | within the established budget allocations for the relevant year | The recommendation has been communicated to institutions of general secondary education and vocational secondary education. | За повідомленням Міністерства освіти і науки України, станом на 30.09.2024 р. "в інструктивно-методичних рекомендаціях щодо викладання навчальних предметів / інтегрованих курсів у закладах загальної середньої освіти у 2024/2025 навчальному році до розділу «Громадянська та історична освітня галузь» включено необхідність висвітлення в освітньому процесі питань з формування нетерпимості до корупції та слідування доброчесним стратегіям поведінки, які надіслано листом МОН від 30.08.2024 № 1.1/15776-24 до департаментів (управлінь) освіти і науки обласних, Київської міської (військових) державних адміністрацій, закладів післядипломної педагогічної та загальної середньої освіти". | Implemented | 0.0
1.2 | Instilling a negative attitude towards corruption | 1.2.1 Everyday corrupt practices are an established norm of conduct and are not perceived as violations of moral or legal norms. There is no consistent demand from the population for public officials to uphold the prescribed rules of ethical conduct and integrity | 1.2.1.1 | The overall level of tolerance of corruption in Ukraine has decreased owing to the integration of anticorruption topics into educational curricula at all levels, which includes instilling in society a stable perception of corruption as a phenomenon that significantly slows down the socioeconomic development of the country, of corrupt officials as persons who make public administration ineffective, and the realization that dishonest practices, even when they look like a convenient opportunity to solve their issues in the short term, are always disadvantageous for individuals and society in the medium and long term | 1.2.1.1.6 | Developing the curriculum and the educational and methodological handbook of the optional course on the prevention of corruption and social integrity for the 9th grade (with the possible involvement of NGOs and international technical assistance projects in this activity) | 01.03.2023 | 30.06.2023 | National Agency on Corruption Prevention |  | state budget | within the established budget allocations for the relevant year | The curriculum and the educational and methodological handbook have been developed. | Навчально-методичний посібник курсу за вибором про запобігання корупції та суспільну доброчесність для 9 класів підготовлено, пропілотовано та поширено серед закладів загальної середньої освіти. Зовнішнім експертом розроблено навчальну програму для курсу за вибором «Протидія корупції», якій відповідає посібник «Антикорупційний курс для 9 класу» | Implemented | 0.0
1.2 | Instilling a negative attitude towards corruption | 1.2.1 Everyday corrupt practices are an established norm of conduct and are not perceived as violations of moral or legal norms. There is no consistent demand from the population for public officials to uphold the prescribed rules of ethical conduct and integrity | 1.2.1.1 | The overall level of tolerance of corruption in Ukraine has decreased owing to the integration of anticorruption topics into educational curricula at all levels, which includes instilling in society a stable perception of corruption as a phenomenon that significantly slows down the socioeconomic development of the country, of corrupt officials as persons who make public administration ineffective, and the realization that dishonest practices, even when they look like a convenient opportunity to solve their issues in the short term, are always disadvantageous for individuals and society in the medium and long term | 1.2.1.1.7 | Submitting documents to obtain the stamp of approval for use in the educational process for the curriculum and the educational and methodological handbook of the optional course on the prevention of corruption and social integrity for the 9th grade | 01.07.2023 | 30.09.2023 | National Agency on Corruption Prevention | Ministry of Education and Science of Ukraine | state budget and/or international technical assistance funds | within the established budget allocations for the relevant year and/or international technical assistance funds | The curriculum and the educational and methodological handbook have passed expert examination. The expert committee has reviewed the expert opinions on the feasibility of using it in the educational process. | Навчальна програма і навчально-методичний посібник пройшли експертизу. Рішенням експертної комісії з громадянської освіти та правознавства від 26.04.2024 (протокол № 3) навчально-методичному посібнику «Антикорупційний курс» для 9 класу закладів загальної середньої освіти (авт. колектив Офісу доброчесності НАЗК та ГО «ЕдКемп Україна» в межах проекту «Прозора школа») надано гриф «Схвалено для використання в освітньому процесі», який зареєстрований у Каталозі надання грифів навчальній літературі та навчальним програмам за № 3.0272-2024. Рішенням експертної комісії з громадянської та історичної освітньої галузі від 13.08.2025 (протокол № 10) навчальній програмі «Навчальна програма «Антикорупційний курс для 9 класу» надано гриф «Схвалено для використання в освітньому процесі», який зареєстрований у Каталозі надання грифів навчальній літературі та навчальним програмам за № БО - 0311-25. | Implemented | 0.0
1.2 | Instilling a negative attitude towards corruption | 1.2.1 Everyday corrupt practices are an established norm of conduct and are not perceived as violations of moral or legal norms. There is no consistent demand from the population for public officials to uphold the prescribed rules of ethical conduct and integrity | 1.2.1.1 | The overall level of tolerance of corruption in Ukraine has decreased owing to the integration of anticorruption topics into educational curricula at all levels, which includes instilling in society a stable perception of corruption as a phenomenon that significantly slows down the socioeconomic development of the country, of corrupt officials as persons who make public administration ineffective, and the realization that dishonest practices, even when they look like a convenient opportunity to solve their issues in the short term, are always disadvantageous for individuals and society in the medium and long term | 1.2.1.1.12 | Developing educational and methodological materials on anticorruption topics (anticorruption and integrity) for students pursuing professional (vocational) education, focusing on the development of cross-cutting civic and social competencies (with the possible involvement of NGOs and international technical assistance projects in this activity). | 01.01.2025 | 30.06.2025 | National Agency on Corruption Prevention |  | state budget | within the established budget allocations for the relevant year | The educational and methodological materials have been developed. | За інформацією наданою за попередні звітні періоди Управлінням просвітницької роботи та навчальних програм апарату Національного агентства з питань запобігання корупції, наказом Національного агентства з питань запобігання корупції (далі - Національне агентство) від 02.06.2025 №152/25 утворено робочу групу з розроблення навчально-методичних матеріалів з антикорупційної тематики (запобігання корупції та доброчесність) для здобувачів професійної (професійно-технічної) освіти в частині розвитку наскрізних громадянських та соціальних компетентностей. Підготовлено проект навчально-методичних матеріалів та передано на ознайомлення Голові Національного агентства (службова записка №120-06/5970-25 від 30.06.2025). За інформацією, наданою виконавцем у IV кварталі 2025 року, навчально-методичні матеріали фіналізовані та готові до апробації пілотними закладами професійної освіти та подальшого використання. Упродовж січня-лютого буде завершено верстку та дизайн посібника. Разом з тим, надані для ознайомлення матеріали містять окремі редакційні та технічні коментарі, що свідчить про перебування документа на стадії редакційного доопрацювання. Таким чином, зважаючи на ступінь відповідності фактично вжитих дій вимогам ДАП щодо змісту та способу виконання заходу, вважаємо за можливе констатувати, що захід є виконаним частково. | Partially implemented | 0.0
1.2 | Instilling a negative attitude towards corruption | 1.2.1 Everyday corrupt practices are an established norm of conduct and are not perceived as violations of moral or legal norms. There is no consistent demand from the population for public officials to uphold the prescribed rules of ethical conduct and integrity | 1.2.1.1 | The overall level of tolerance of corruption in Ukraine has decreased owing to the integration of anticorruption topics into educational curricula at all levels, which includes instilling in society a stable perception of corruption as a phenomenon that significantly slows down the socioeconomic development of the country, of corrupt officials as persons who make public administration ineffective, and the realization that dishonest practices, even when they look like a convenient opportunity to solve their issues in the short term, are always disadvantageous for individuals and society in the medium and long term | 1.2.1.1.13 | Designation by the Ministry of Education and Science of anticorruption topics (anticorruption and integrity) as a mandatory component of state standards of professional (vocation) education (as a separate educational component or a cross-cutting component within other components) | 01.04.2025 | 31.07.2025 | National Agency on Corruption Prevention | Ministry of Education and Science of Ukraine, State Scientific Institution “Institute of Education Content Modernization” | state budget and/or international technical assistance funds | within the established budget allocations for the relevant year and/or international technical assistance funds | The Ministry of Education and Science has designated anticorruption topics (anticorruption and integrity) as a mandatory component of state standards of professional (vocation) education (as a separate educational component or a cross-cutting component within other components). | За інформацією наданою за попередні звітні періоди Управлінням просвітницької роботи та навчальних програм апарату Національного агентства з питань запобігання корупції, з прийняттям Закону України «Про професійну освіту» (№ 4574-IX від 21.08.2025), який набрав чинності 12.09.2025 року, розпочалась робота по розробці нового Державного стандарту професійної освіти, у якому тематика запобігання корупції та доброчесності отримає системне закріплення як окремий освітній компонент або наскрізна лінія. Листом від 15.10.2025 № 137103003-25 Міністерство освіти і науки України повідомило НАЗК, що прийняття нового Закону України «Про професійну освіту» № 4574-IX започаткувало системне оновлення змісту професійної освіти. Одним із ключових нововведень є запровадження єдиного державного стандарту професійної освіти, який визначає спільні підходи до структури, змісту, результатів навчання та формування наскрізних компетентностей для всіх професійних кваліфікацій. Разом з тим, станом на кінець звітного періоду єдиний державний стандарт професійної освіти не затверджено, а отже відсутній нормативний акт, яким антикорупційну тематику визначено МОН як обов’язкову складову державних стандартів професійної (професійно-технічної) освіти. Також у державних стандартах професійної (професійно-технічної) освіти, затверджених до вересня 2025 року для окремих професій можна простежити антикорупційну тематику як обов’язкову складову освітнього процесу. Проте, це не свідчить про її системне визначення як обов’язкової складової державних стандартів у розумінні показника виконання заходу. Разом з тим, антикорупційна тематика інтегрується до: • освітніх програм, що реалізуються у закладах П(ПТ)О, з урахуванням можливості їх адаптації відповідно до типових та авторських навчальних планів; • навчальних предметів та модулів, зокрема: «Громадянська освіта», «Правознавство», «Основи трудового законодавства», «Охорона праці», «Етика ділових відносин» тощо. Також антикорупційна тематика реалізується в рамках виховної роботи, тренінгів, інтерактивних заходів у співпраці з представниками громадських організацій, проектів міжнародної технічної допомоги, НАЗК. Таким чином, зважаючи на ступінь відповідності фактично вжитих дій вимогам ДАП щодо змісту та способу виконання заходу, вважаємо, що захід є виконаним частково, оскільки станом на кінець звітного періоду єдиний державний стандарт професійної освіти не затверджено. | Partially implemented | 0.0
1.2 | Instilling a negative attitude towards corruption | 1.2.1 Everyday corrupt practices are an established norm of conduct and are not perceived as violations of moral or legal norms. There is no consistent demand from the population for public officials to uphold the prescribed rules of ethical conduct and integrity | 1.2.1.1 | The overall level of tolerance of corruption in Ukraine has decreased owing to the integration of anticorruption topics into educational curricula at all levels, which includes instilling in society a stable perception of corruption as a phenomenon that significantly slows down the socioeconomic development of the country, of corrupt officials as persons who make public administration ineffective, and the realization that dishonest practices, even when they look like a convenient opportunity to solve their issues in the short term, are always disadvantageous for individuals and society in the medium and long term | 1.2.1.1.14 | Updating the curricula of professional (vocational) education to incorporate the anticorruption topics (anticorruption and integrity) as a mandatory component (as a separate educational component or a cross-cutting component within other components). | 01.08.2025 | 31.10.2025 | Ministry of Education and Science of Ukraine | National Agency on Corruption Prevention | state budget | within the established budget allocations for the relevant year | Anticorruption topics have been incorporated into a separate educational component. | У зв’язку з набранням чинності 12.09.2025 Закону України «Про професійну освіту» від 21.08.2025 № 4574-IX розробляється єдиний стандарт професійної освіти. Єдиний стандарт професійної освіти визначить базові та наскрізні компетентності які інтегруються в освітніх програмах, та мають формуватися у кожного здобувача освіти. Новий єдиний стандарт професійної освіти створить можливість системно інтегрувати антикорупційну тематику в освітній процес та освітні програми. Після затвердження єдиного державного стандарту професійної освіти будуть розробляться та затверджуватись освітні прогами. Отже, виконання заходу буде можливе після остаточного виконання заходу 1.2.1.1.13. Враховуючи зазначене вище, а також зважаючи на те, що дата завершення строку виконання заходу вже настала, констатуємо, що захід не є виконаним. | Not implemented | 0.0
1.2 | Instilling a negative attitude towards corruption | 1.2.1 Everyday corrupt practices are an established norm of conduct and are not perceived as violations of moral or legal norms. There is no consistent demand from the population for public officials to uphold the prescribed rules of ethical conduct and integrity | 1.2.1.1 | The overall level of tolerance of corruption in Ukraine has decreased owing to the integration of anticorruption topics into educational curricula at all levels, which includes instilling in society a stable perception of corruption as a phenomenon that significantly slows down the socioeconomic development of the country, of corrupt officials as persons who make public administration ineffective, and the realization that dishonest practices, even when they look like a convenient opportunity to solve their issues in the short term, are always disadvantageous for individuals and society in the medium and long term | 1.2.1.1.15 | Developing educational and methodological materials on anticorruption topics (anticorruption, social and academic integrity) for first-year students pursuing a higher education (with the possible involvement of NGOs and international technical assistance projects in this activity) | 01.03.2023 | 31.10.2024 | National Agency on Corruption Prevention |  | state budget and/or international technical assistance funds | within the established budget allocations for the relevant year | The educational and methodological materials have been developed. | According to the National Agency on Corruption Prevention, as of March 31, 2024, teaching materials have been developed, and “piloting of the discipline in 10 Ukrainian higher education institutions has been completed. The discipline is already being extended to other Ukrainian higher education institutions.” | Implemented | 0.0
1.2 | Instilling a negative attitude towards corruption | 1.2.1 Everyday corrupt practices are an established norm of conduct and are not perceived as violations of moral or legal norms. There is no consistent demand from the population for public officials to uphold the prescribed rules of ethical conduct and integrity | 1.2.1.1 | The overall level of tolerance of corruption in Ukraine has decreased owing to the integration of anticorruption topics into educational curricula at all levels, which includes instilling in society a stable perception of corruption as a phenomenon that significantly slows down the socioeconomic development of the country, of corrupt officials as persons who make public administration ineffective, and the realization that dishonest practices, even when they look like a convenient opportunity to solve their issues in the short term, are always disadvantageous for individuals and society in the medium and long term | 1.2.1.1.16 | Developing amendments to the Procedural Recommendations on the Development of Standards of Higher Education, approved by the order of the Ministry of Education and Science dated June 1, 2016, No. 600, which would supplement the list of mandatory general competencies for the academic degree of a bachelor with the competency defined as intolerance of corruption in all of its manifestations, an understanding of the inadmissibility of tolerating inequality and dishonesty | 01.02.2024 | 30.04.2024 | Ministry of Education and Science of Ukraine | National Agency on Corruption Prevention | state budget | within the established budget allocations for the relevant year | The draft order amending the order of the Ministry of Education and Science has been developed. | Amendments to the Methodological Recommendations for the Development of Higher Education Standards, approved by the order of the Ministry of Education and Science of Ukraine dated June 1, 2016, No. 600, were developed and approved. The amendments include in the list of mandatory general competencies for the bachelor's degree the competence related to intolerance to corruption in all its manifestations, understanding the inadmissibility of tolerating inequality and dishonesty (Order of the Ministry of Education and Science of Ukraine dated April 3, 2024, No. 441). | Implemented | 0.0
1.2 | Instilling a negative attitude towards corruption | 1.2.1 Everyday corrupt practices are an established norm of conduct and are not perceived as violations of moral or legal norms. There is no consistent demand from the population for public officials to uphold the prescribed rules of ethical conduct and integrity | 1.2.1.1 | The overall level of tolerance of corruption in Ukraine has decreased owing to the integration of anticorruption topics into educational curricula at all levels, which includes instilling in society a stable perception of corruption as a phenomenon that significantly slows down the socioeconomic development of the country, of corrupt officials as persons who make public administration ineffective, and the realization that dishonest practices, even when they look like a convenient opportunity to solve their issues in the short term, are always disadvantageous for individuals and society in the medium and long term | 1.2.1.1.17 | Conducting a public discussion of the draft order indicated in subclause 1.2.1.1.16 | 01.05.2024 | 31.05.2024 | Ministry of Education and Science of Ukraine |  | state budget | within the established budget allocations for the relevant year | The public discussion has been conducted. | Міністерство освіти і науки України провело громадське обговорення проєкт наказу "Про внесення змін до Методичних рекомендацій щодо розроблення стандартів вищої освіти". МОН затверджено звіт з громадського обговорення проєкту акта | Implemented | 0.0
1.2 | Instilling a negative attitude towards corruption | 1.2.1 Everyday corrupt practices are an established norm of conduct and are not perceived as violations of moral or legal norms. There is no consistent demand from the population for public officials to uphold the prescribed rules of ethical conduct and integrity | 1.2.1.1 | The overall level of tolerance of corruption in Ukraine has decreased owing to the integration of anticorruption topics into educational curricula at all levels, which includes instilling in society a stable perception of corruption as a phenomenon that significantly slows down the socioeconomic development of the country, of corrupt officials as persons who make public administration ineffective, and the realization that dishonest practices, even when they look like a convenient opportunity to solve their issues in the short term, are always disadvantageous for individuals and society in the medium and long term | 1.2.1.1.18 | Revising (if needed) and issuing the order indicated in subclause 1.2.1.1.16 | 01.06.2024 | 31.07.2024 | Ministry of Education and Science of Ukraine |  | state budget | within the established budget allocations for the relevant year | The order has been issued. | Amendments to the Guidelines for the Development of Higher Education Standards, approved by the Order of the Ministry of Education and Science (MES) No. 600 of June 1, 2016, were developed and approved. These amendments include in the list of mandatory general competencies for the Bachelor’s degree the competence related to intolerance to corruption in all its manifestations and understanding the inadmissibility of tolerating inequality and dishonesty (MES Order No. 441 of April 3, 2024). | Implemented | 0.0
1.2 | Instilling a negative attitude towards corruption | 1.2.1 Everyday corrupt practices are an established norm of conduct and are not perceived as violations of moral or legal norms. There is no consistent demand from the population for public officials to uphold the prescribed rules of ethical conduct and integrity | 1.2.1.1 | The overall level of tolerance of corruption in Ukraine has decreased owing to the integration of anticorruption topics into educational curricula at all levels, which includes instilling in society a stable perception of corruption as a phenomenon that significantly slows down the socioeconomic development of the country, of corrupt officials as persons who make public administration ineffective, and the realization that dishonest practices, even when they look like a convenient opportunity to solve their issues in the short term, are always disadvantageous for individuals and society in the medium and long term | 1.2.1.1.19 | Developing amendments to standards of higher education, approved by orders of the Ministry of Education and Science, taking into account the amendments to the Procedural Recommendations indicated in subclause 1.2.1.1.16 | 04.05.2024 | 04.07.2024 | Ministry of Education and Science of Ukraine | National Agency on Corruption Prevention | state budget | within the established budget allocations for the relevant year | The draft order amending the normative legal acts has been developed. | The Order of the Ministry of Education and Science No. 842 of June 13, 2024, “On Amending Certain Higher Education Standards,” was developed and approved, providing for certain specialties to include in the list of mandatory general competencies for the Bachelor’s degree the competence related to intolerance to corruption in all its manifestations, understanding the inadmissibility of tolerating inequality and dishonesty. | Implemented | 0.0
1.2 | Instilling a negative attitude towards corruption | 1.2.1 Everyday corrupt practices are an established norm of conduct and are not perceived as violations of moral or legal norms. There is no consistent demand from the population for public officials to uphold the prescribed rules of ethical conduct and integrity | 1.2.1.1 | The overall level of tolerance of corruption in Ukraine has decreased owing to the integration of anticorruption topics into educational curricula at all levels, which includes instilling in society a stable perception of corruption as a phenomenon that significantly slows down the socioeconomic development of the country, of corrupt officials as persons who make public administration ineffective, and the realization that dishonest practices, even when they look like a convenient opportunity to solve their issues in the short term, are always disadvantageous for individuals and society in the medium and long term | 1.2.1.1.20 | Conducting a public discussion of the draft order indicated in subclause 1.2.1.1.19 | 04.08.2024 | 04.09.2024 | Ministry of Education and Science of Ukraine |  | state budget | within the established budget allocations for the relevant year | The public discussion has been conducted. | Міністерство освіти і науки України провело громадського обговорення проєкт наказу "Про всесення змін до деяких стандартів вищої освіти". | Implemented | 0.0
1.2 | Instilling a negative attitude towards corruption | 1.2.1 Everyday corrupt practices are an established norm of conduct and are not perceived as violations of moral or legal norms. There is no consistent demand from the population for public officials to uphold the prescribed rules of ethical conduct and integrity | 1.2.1.1 | The overall level of tolerance of corruption in Ukraine has decreased owing to the integration of anticorruption topics into educational curricula at all levels, which includes instilling in society a stable perception of corruption as a phenomenon that significantly slows down the socioeconomic development of the country, of corrupt officials as persons who make public administration ineffective, and the realization that dishonest practices, even when they look like a convenient opportunity to solve their issues in the short term, are always disadvantageous for individuals and society in the medium and long term | 1.2.1.1.21 | Revising (if needed) and issuing the order indicated in subclause 1.2.1.1.19 | 04.10.2024 | 04.11.2024 | Ministry of Education and Science of Ukraine |  | state budget | within the established budget allocations for the relevant year | The order has been issued. | “The Order of the Ministry of Education and Science No. 842 of June 13, 2024, “On Amending Certain Higher Education Standards,” was approved, stipulating certain specialties to include in the list of mandatory general competencies for the Bachelor’s degree the competence related to intolerance to corruption in all its manifestations, understanding the inadmissibility of tolerating inequality and dishonesty.” | Implemented | 0.0
1.2 | Instilling a negative attitude towards corruption | 1.2.1 Everyday corrupt practices are an established norm of conduct and are not perceived as violations of moral or legal norms. There is no consistent demand from the population for public officials to uphold the prescribed rules of ethical conduct and integrity | 1.2.1.2 | The overall level of tolerance of corruption in Ukraine has decreased owing to the creation of favorable conditions for professional development of educators and people working with the public, in particular in matters of academic integrity and instilling an attitude of intolerance of corruption in all its manifestations among students | 1.2.1.2.1 | Adapting courses devoted to anticorruption topics (anticorruption, social and academic integrity) and incorporating them into available professional development programs for educators (with the possible involvement of NGOs and international technical assistance projects in this activity) | 01.03.2023 | 31.08.2023 | Ministry of Education and Science of Ukraine | National Agency on Corruption Prevention | state budget | within the established budget allocations for the relevant year | Thematic courses have been incorporated into programs administered by institutions of postgraduate education for educators. | Course on anti-corruption topic "Compliance with Anti-Corruption Legislation and Academic Integrity in the Activities of Employees of Educational Institutions" has been developed. Anti-corruption topics are integrated into professional development courses for pedagogical, academic and research staff, conducted by the State Institution "Scientific and Methodological Center of Higher and Professional Pre-Higher Education". The training program has been developed. The online course is in the final stage of development. The letter from the Ministry of Education and Science of Ukraine recommending the online course for teachers "Learn: what to say about integrity in class" to be used as material for professional development classes for teachers was sent to the rectors (directors) of postgraduate pedagogical education institutions (letter dated August 11, 2023 No. 1/11946-23). | Implemented | 0.0
1.2 | Instilling a negative attitude towards corruption | 1.2.1 Everyday corrupt practices are an established norm of conduct and are not perceived as violations of moral or legal norms. There is no consistent demand from the population for public officials to uphold the prescribed rules of ethical conduct and integrity | 1.2.1.2 | The overall level of tolerance of corruption in Ukraine has decreased owing to the creation of favorable conditions for professional development of educators and people working with the public, in particular in matters of academic integrity and instilling an attitude of intolerance of corruption in all its manifestations among students | 1.2.1.2.2 | Issuing a recommendation for educators to regularly complete professional development training in anticorruption topics (anticorruption, social and academic integrity) | 01.03.2023 | 31.07.2023 | Ministry of Education and Science of Ukraine | National Agency on Corruption Prevention | state budget | within the established budget allocations for the relevant year | The recommendation has been disseminated among educators through educational institutions. | "The Ministry of Education and Science of Ukraine has provided recommendations to pedagogical staff on regular professional development on anti-corruption topics (corruption prevention, public and academic integrity) - a letter to the heads of higher education institutions. According to the information received through the Information System for Monitoring the Implementation of the State Anti-Corruption Policy, 2000 people have taken anti-corruption courses". | Implemented | 0.0
1.2 | Instilling a negative attitude towards corruption | 1.2.1 Everyday corrupt practices are an established norm of conduct and are not perceived as violations of moral or legal norms. There is no consistent demand from the population for public officials to uphold the prescribed rules of ethical conduct and integrity | 1.2.1.2 | The overall level of tolerance of corruption in Ukraine has decreased owing to the creation of favorable conditions for professional development of educators and people working with the public, in particular in matters of academic integrity and instilling an attitude of intolerance of corruption in all its manifestations among students | 1.2.1.2.3 | Developing the study discipline “Integrity and Anticorruption for Educators” designed for all students pursuing specialties in the academic branch 01 “Education” (with the possible involvement of NGOs and international technical assistance projects in this activity) | 01.12.2023 | 31.12.2024 | National Agency on Corruption Prevention | Ministry of Education and Science of Ukraine | state budget and/or international technical assistance funds | within the established budget allocations for the relevant year and/or international technical assistance funds | The study discipline has been developed. | За інформацією наданою за попередні звітні періоди Управлінням просвітницької роботи та навчальних програм апарату Національного агентства з питань запобігання корупції, у ІІ кварталі 2025 року було сформовано робочу групу, напрацьовано тематичний план дисципліни із зазначенням основних модулів та тем. Також сформовано міжвідомчу робочу групу для проведення експертизи та фахового рецензування розроблених матеріалів. Експертами було здійснено рецензування та надано рекомендації. Станом на кінець 31.12.2025 розроблено змістовне наповнення дисципліни "Доброчесність та антикорупція для педагогічних працівників" та фіналізовано змістовне наповнення модулів, супровідних навчально-методичних матеріалів з дисципліни, складових й механізму оцінювання знань. Матеріали готові до апробації. Таким чином, зважаючи на ступінь відповідності фактично вжитих дій вимогам ДАП щодо змісту та способу виконання заходу, а також беручи до уваги, що матеріали дисципліни станом на 31.12.2025 були готові до апробації, за результатом якої можливе змістовне доопрацювання, розроблення дисципліни не можна вважати завершеним у повному обсязі. Таким чином, зважаючи на ступінь відповідності фактично вжитих дій вимогам ДАП щодо змісту та способу виконання заходу, вважаємо за можливе констатувати, що захід є виконаним частково. | Partially implemented | 0.0
1.2 | Instilling a negative attitude towards corruption | 1.2.1 Everyday corrupt practices are an established norm of conduct and are not perceived as violations of moral or legal norms. There is no consistent demand from the population for public officials to uphold the prescribed rules of ethical conduct and integrity | 1.2.1.2 | The overall level of tolerance of corruption in Ukraine has decreased owing to the creation of favorable conditions for professional development of educators and people working with the public, in particular in matters of academic integrity and instilling an attitude of intolerance of corruption in all its manifestations among students | 1.2.1.2.4 | Amending the standards of higher education for all specialties in the academic branch 01 “Education/Pedagogics” for the higher education academic degree of a bachelor in terms of the normative substance of training for students pursuing a higher education: “Know the fundamentals of anticorruption, social and academic integrity at a level necessary to instill intolerance of corruption and manifestations of dishonest conduct among students pursuing education, and be able to apply them in professional work” | 01.01.2025 | 31.03.2025 | Ministry of Education and Science of Ukraine | National Agency on Corruption Prevention | state budget | within the established budget allocations for the relevant year | Amendments have been introduced. | Наказом МОН від 13.06.2024 № 842 "Про внесення змін до деяких стандартів вищої освіти", передбачено для певних спеціальностей серед переліку обов’язкових загальних компетентностей для освітнього рівня бакалавр компетентність, пов’язану із нетерпимістю до корупції в усіх її проявах, розумінням неприпустимості толерування нерівності та недоброчесності. | Implemented | 0.0
1.2 | Instilling a negative attitude towards corruption | 1.2.1 Everyday corrupt practices are an established norm of conduct and are not perceived as violations of moral or legal norms. There is no consistent demand from the population for public officials to uphold the prescribed rules of ethical conduct and integrity | 1.2.1.2 | The overall level of tolerance of corruption in Ukraine has decreased owing to the creation of favorable conditions for professional development of educators and people working with the public, in particular in matters of academic integrity and instilling an attitude of intolerance of corruption in all its manifestations among students | 1.2.1.2.5 | Developing recommendations on how to ensure transparency and integrity in the work of institutions of general secondary education (with the possible involvement of NGOs and international technical assistance projects in this activity) | 01.03.2023 | 31.01.2024 | National Agency on Corruption Prevention |  | state budget and/or international technical assistance funds | within the established budget allocations for the relevant year | The recommendations have been developed. | Національне агентство з питань запобігання корупції у співпраці з експертною робочою групою завершило розроблення рекомендацій у форматі «Освітній навігатор». Перша редакція рекомендацій була апробована у 5 пілотних закладах загальної середньої освіти протягом 2023–2024 років. За результатами апробації документ було доопрацьовано та вдосконалено. Станом на кінець IV кварталу 2024 року завершено візуальне оформлення та верстку остаточної редакції рекомендацій. Передача матеріалів до МОН для схвалення запланована на І квартал 2025 року. Показник заходу "рекомендації розроблено" вважається досягнутим | Implemented | 0.0
1.2 | Instilling a negative attitude towards corruption | 1.2.1 Everyday corrupt practices are an established norm of conduct and are not perceived as violations of moral or legal norms. There is no consistent demand from the population for public officials to uphold the prescribed rules of ethical conduct and integrity | 1.2.1.2 | The overall level of tolerance of corruption in Ukraine has decreased owing to the creation of favorable conditions for professional development of educators and people working with the public, in particular in matters of academic integrity and instilling an attitude of intolerance of corruption in all its manifestations among students | 1.2.1.2.6 | Approving recommendations for institutions of general secondary education via a directive of the Ministry of Education and Science, specifying the deadline for their integration into the processes of institutions of general secondary education | 01.02.2024 | 31.05.2024 | Ministry of Education and Science of Ukraine | National Agency on Corruption Prevention | state budget | within the established budget allocations for the relevant year | The recommendations have been approved via a directive of the Ministry of Education and Science, with the deadlines for their implementation specified. | На виконання пп. 1.2.1.2.5 додатку 2 до ДАП Національне агентство з питань запобігання корупції спільно з робочою групою експертів у сфері освіти розробило рекомендації щодо забезпечення прозорості та доброчесності в діяльності закладів загальної середньої освіти (Освітній навігатор). Перша редакція рекомендацій була апробована в 5-ти пілотних закладах освіти протягом 2023-2024 рр. За результатами апробації рекомендації були доопрацьовані та вдосконалені. Станом на кінець I кварталу 2025 року завершено візуальне оформлення та верстку доопрацьованої редакції Освітнього навігатора. Відповідні матеріали направлено до МОН листом №121-01/4129-25 від 16.01.2025 для подальшого схвалення. Міністерство освіти і науки України ініціювало громадське обговорення рекомендацій щодо забезпечення прозорості та доброчесності в діяльності закладів загальної середньої освіти – посібник «Освітній навігатор». Зауваження та пропозиції до зазначеного проєкту приймалися в електронній формі до 10 квітня 2025 року. Затверджено наказ від 15.05.2025 № 734 "Про затвердження рекомендацій для забезпечення прозорості та доброчесності у діяльності закладів загальної середньої освіти - посібника "Освітній навігатор", розроблених Національним агентством з питань запобігання корупції". | Implemented | 0.0
1.2 | Instilling a negative attitude towards corruption | 1.2.1 Everyday corrupt practices are an established norm of conduct and are not perceived as violations of moral or legal norms. There is no consistent demand from the population for public officials to uphold the prescribed rules of ethical conduct and integrity | 1.2.1.2 | The overall level of tolerance of corruption in Ukraine has decreased owing to the creation of favorable conditions for professional development of educators and people working with the public, in particular in matters of academic integrity and instilling an attitude of intolerance of corruption in all its manifestations among students | 1.2.1.2.7 | Submitting an information message with recommendations, indicated in subclause 1.2.1.2.5, to local government bodies responsible for education area, other central executive bodies managing educational establishments | 01.06.2024 | 30.11.2024 | Ministry of Education and Science of Ukraine |  | state budget | within the established budget allocations for the relevant year | The recommendations indicated in subclause 1.2.1.2.5 have been integrated into normative documents, charters, guidelines, and orders. | За інформацією від Міністерства освіти і науки України, листом від 14.06.2025 № 1/12502-25 місцевим органам управління у сфері освіти надіслано розроблені Національним агентством з питань запобігання корупції Рекомендації щодо забезпечення прозорості та доброчесності в діяльності закладів загальної середньої освіти – посібник «Освітній навігатор». Щодо показника (індикатора) виконання відповідного заходу, звертаємо увагу на наступне. У первинній редакції найменування та змісту заходу, передбаченого п. п. 1.2.1.2.7 додатка 2 до Державної антикорупційної програми на 2023 – 2025 роки, затвердженої постановою Кабінету Міністрів України від 04.03.2023 року № 220 (далі – ДАП), закріплювалось :«Закріплення у нормативних документах, статутах, інструкціях, наказах рекомендацій, зазначених у підпункті 1.2.1.2.5». Постановою Кабінету Міністрів України від 18.10.2024 року № 1194 «Про внесення змін до Державної антикорупційної програми на 2023 – 2025 роки» було внесено зміни до ДАП. Відповідними змінами передбачалося викладення найменування та змісту заходу, передбаченого п. п. 1.2.1.2.7 додатка 2 до ДАП, у новій редакції, а саме: «Надсилання інформаційного повідомлення з рекомендаціями, зазначеними у підпункті 1.2.1.2.5, місцевим органам управління у сфері освіти, іншим центральним органам виконавчої влади, у сфері управління яких перебувають заклади освіти» (див. п. п. 57 змін до додатку 2 до ДАП). Разом з тим, показник (індикатор) виконання відповідного заходу не було змінено, який і залишився як: «рекомендації, зазначені у підпункті 1.2.1.2.5, закріплено у нормативних документах, статутах, інструкціях, наказах». У результаті виникла неузгодженість між найменуванням та змістом заходу і показником (індикатором) його виконання. Враховуючи найменування та зміст цього заходу, релевантним показником (індикатором) його виконання могло б бути: «Інформаційне повідомлення з рекомендаціями, зазначеними у підпункті 1.2.1.2.5, місцевим органам управління у сфері освіти, іншим центральним органам виконавчої влади, у сфері управління яких перебувають заклади освіти надіслано». Враховуючи зазначене вище, а також зважаючи на ступінь відповідності фактично вжитих дій вимогам ДАП щодо змісту та способу виконання заходу, вважаємо за можливе констатувати, що захід є виконаним повністю. | Implemented | 0.0
1.2 | Instilling a negative attitude towards corruption | 1.2.1 Everyday corrupt practices are an established norm of conduct and are not perceived as violations of moral or legal norms. There is no consistent demand from the population for public officials to uphold the prescribed rules of ethical conduct and integrity | 1.2.1.2 | The overall level of tolerance of corruption in Ukraine has decreased owing to the creation of favorable conditions for professional development of educators and people working with the public, in particular in matters of academic integrity and instilling an attitude of intolerance of corruption in all its manifestations among students | 1.2.1.2.8 | Gathering and consolidating data on the implementation of recommendations by institutions of general secondary education, once every six months | 01.11.2024 | 31.12.2025 | State Education Quality Service of Ukraine |  | state budget | within the established budget allocations for the relevant year | Data has been gathered, consolidated, and submitted to the National Agency. | За інформацією, наданою Державною службою якості освіти України (далі - Служба), Службою спільно з її територіальними органами у період з 03 до 15 грудня 2025 року проведено моніторингове дослідження рівня обізнаності керівників закладів і впровадження методичних рекомендацій для забезпечення прозорості та доброчесності у діяльності закладів загальної середньої освіти «Освітній навігатор», розроблених Національним агентством з питань запобігання корупції (далі – НАЗК), затверджених наказом Міністерства освіти і науки України від 15.05.2025 № 734. У моніторинговому дослідженні загалом взяли участь 6 065 керівників закладів загальної середньої освіти з усіх областей України та міста Києва (окрім Автономної Республіки Крим). Дослідження стосувалося питань: - обізнаності про «Освітній навігатор»; - джерел інформації, з яких керівники закладів освіти отримують нові матеріали, рекомендації тощо для організації управлінської та педагогічної діяльності, зокрема про «Освітній навігатор»; - ознайомлення керівників закладів освіти з основними розділами методичних рекомендацій; - обговорення методичних рекомендацій НАЗК «Освітній навігатор» у педагогічних колективах ЗЗСО; - розроблення в закладі освіти плану заходів із впровадження зазначених рекомендацій; - форм впровадження методичних рекомендацій НАЗК «Освітній навігатор» в ЗЗСО; - та ін. Разом з тим, сам захід передбачає збір та узагальнення даних щодо застосування рекомендацій закладами загальної середньої освіти раз на півріччя. Тобто збирання, узагальнення та надсилання відповідних даних мало бути здійснено двічі. Проте, виконання заходу 1.2.1.2.8 перебувало у системно зв’язку із заходом 1.2.1.2.7, щодо статусу якого було узгоджено остаточну позицію у III кварталі 2025 року. Зазначені вище обставини унеможливили збір даних, передбачених заходом 1.2.1.2.8 двічі. За інформацією від Державної служби якості освіти в Україні, черговий збір даних заплановано до кінця I півріччя 2026 року. Таким чином, зважаючи на ступінь відповідності фактично вжитих дій вимогам ДАП щодо змісту та способу виконання заходу, вважаємо за можливе констатувати, що захід є виконаним частково. | Partially implemented | 0.0
1.2 | Instilling a negative attitude towards corruption | 1.2.1 Everyday corrupt practices are an established norm of conduct and are not perceived as violations of moral or legal norms. There is no consistent demand from the population for public officials to uphold the prescribed rules of ethical conduct and integrity | 1.2.1.2 | The overall level of tolerance of corruption in Ukraine has decreased owing to the creation of favorable conditions for professional development of educators and people working with the public, in particular in matters of academic integrity and instilling an attitude of intolerance of corruption in all its manifestations among students | 1.2.1.2.9 | Developing recommendations on how to increase the level of transparency and integrity in the work of institutions of professional (vocational) education (with the possible involvement of NGOs and international technical assistance projects in this activity) | 01.06.2024 | 31.05.2025 | National Agency on Corruption Prevention |  | state budget and/or international technical assistance funds | within the established budget allocations for the relevant year and/or international technical assistance funds | The recommendations have been developed. | За інформацією, наданою за попередні звітні періоди, у ІІ кварталі 2025 року було сформовано робочу групу, напрацьовано тематику розділів та забезпечено напрацювання проекту змістовного наповнення рекомендацій. У ІІІ кварталі 2025 року сформовано узгоджену структуру документа, доопрацьовано змістовні положення та підготовлений текст передано на рецензування профільним експертам. У IV кварталі 2025 року рекомендації щодо підвищення рівня прозорості та доброчесності у діяльності закладів професійної (професійно-технічної) освіти були розроблені та готові до апробації. У I кварталі 2026 року рекомендації були остаточно розробленими та затвердженими. Так 05.03.2026 було видано наказ Міністерства освіти і науки України № 408 «Про затвердження рекомендацій щодо підвищення рівня прозорості та доброчесності у діяльності закладів професійної освіти, розроблених Національним агентством з питань запобігання корупції». Таким чином, зважаючи на ступінь відповідності фактично вжитих дій вимогам ДАП щодо змісту та способу виконання, вважаємо за можливе констатувати, що захід є виконаним. | Implemented | 0.0
1.2 | Instilling a negative attitude towards corruption | 1.2.1 Everyday corrupt practices are an established norm of conduct and are not perceived as violations of moral or legal norms. There is no consistent demand from the population for public officials to uphold the prescribed rules of ethical conduct and integrity | 1.2.1.2 | The overall level of tolerance of corruption in Ukraine has decreased owing to the creation of favorable conditions for professional development of educators and people working with the public, in particular in matters of academic integrity and instilling an attitude of intolerance of corruption in all its manifestations among students | 1.2.1.2.10 | Approving recommendations for institutions of professional (vocational) education via a directive of the Ministry of Education and Science, specifying the deadline for their integration into the processes of institutions of professional (vocational) education | 01.06.2025 | 31.08.2025 | Ministry of Education and Science of Ukraine | National Agency on Corruption Prevention | state budget | within the established budget allocations for the relevant year | The recommendations have been approved via a directive of the Ministry of Education and Science, with the deadlines for their implementation specified. | Працівниками Національного агентства з питань запобігання корупції (далі - НАЗК), Міністерства освіти і науки України (далі - МОН), закладів професійної освіти було розроблено проект рекомендацій щодо підвищення рівня прозорості та доброчесності у діяльності закладів професійної освіти. 02.10.2025 було проведено нараду за участю НАЗК, МОН, працівників закладів професійної та фахової передвищої освіти. Загальна кількість учасників наради становила 339 осіб. 05.03.2026 було видано наказ МОН № 408 «Про затвердження рекомендацій щодо підвищення рівня прозорості та доброчесності у діяльності закладів професійної освіти, розроблених Національним агентством з питань запобігання корупції». Зазначеним наказом передбачено: - визначення граничного строку впровадження Рекомендацій в діяльність закладів професійної освіти до 31 грудня 2026 року; - керівникам закладів професійної освіти забезпечити закріплення у нормативних документах, статутах, інструкціях, наказах Рекомендацій; - Державній службі якості освіти протягом 2026 року забезпечити збір та узагальнення даних щодо виконання Рекомендацій. Таким чином, зважаючи на ступінь відповідності фактично вжитих дій вимогам ДАП щодо змісту та способу виконання, а також, що Рекомендації схвалено наказом МОН, яким, зокрема, визначено граничні строки їх впровадження, що відповідає показнику виконання, вважаємо за можливе констатувати, що захід є виконаним повністю, але невчасно. | Implemented | 0.0
1.2 | Instilling a negative attitude towards corruption | 1.2.1 Everyday corrupt practices are an established norm of conduct and are not perceived as violations of moral or legal norms. There is no consistent demand from the population for public officials to uphold the prescribed rules of ethical conduct and integrity | 1.2.1.2 | The overall level of tolerance of corruption in Ukraine has decreased owing to the creation of favorable conditions for professional development of educators and people working with the public, in particular in matters of academic integrity and instilling an attitude of intolerance of corruption in all its manifestations among students | 1.2.1.2.11 | Integrating the recommendations indicated in subclause 1.2.1.2.9 in normative documents, charters, guidelines, and orders | 01.09.2025 | 30.11.2025 | Ministry of Education and Science of Ukraine |  | state budget | within the established budget allocations for the relevant year | The recommendations indicated in subclause 1.2.1.2.9 have been integrated into normative documents, charters, guidelines, and orders. | За інформацією, наданою Міністерством освіти і науки України, листом ДПО МОН від 16.03.2026 № 5/805-26 директорат професійної освіти просив Департаменти (управління) освіти і науки обласних, Київської міської державних адміністрацій довести наказ МОН від 05.03.2026 № 408 «Про затвердження рекомендацій щодо підвищення рівня прозорості та доброчесності у діяльності закладів професійної освіти, розроблених Національним агентством з питань запобігання корупції» до відома керівників закладів професійної та фахової передвищої освіти. Разом з тим, не надано інформацію, яка підтверджувала закріплення у нормативних документах, статутах, інструкціях, наказах рекомендацій, зазначених у підпункті 1.2.1.2.9. Враховуючи зазначене вище, вважаємо, що захід не є виконаним. | Not implemented | 0.0
1.2 | Instilling a negative attitude towards corruption | 1.2.1 Everyday corrupt practices are an established norm of conduct and are not perceived as violations of moral or legal norms. There is no consistent demand from the population for public officials to uphold the prescribed rules of ethical conduct and integrity | 1.2.1.2 | The overall level of tolerance of corruption in Ukraine has decreased owing to the creation of favorable conditions for professional development of educators and people working with the public, in particular in matters of academic integrity and instilling an attitude of intolerance of corruption in all its manifestations among students | 1.2.1.2.12 | Gathering and consolidating data on the implementation of recommendations by institutions of professional (vocational) education, once every six months | 01.12.2025 | 31.12.2025 | State Education Quality Service of Ukraine | Ministry of Education and Science of Ukraine | state budget | within the established budget allocations for the relevant year | Data has been gathered, consolidated, and submitted to the National Agency. | 05.03.2026 було видано наказ МОН № 408 «Про затвердження рекомендацій щодо підвищення рівня прозорості та доброчесності у діяльності закладів професійної освіти, розроблених Національним агентством з питань запобігання корупції». Зазначеним наказом передбачено, зокрема: - Державній службі якості освіти протягом 2026 року забезпечити збір та узагальнення даних щодо виконання Рекомендацій. У зв'язку з цим ДСЯО не мало можливості здійснити відповідний збір та узагальнення даних протягом відповідного звітного періоду. Разом з тим, захід перебуває на стадії виконання. Але, оскільки показник виконання протягом звітного періоду не досягнуто, вважаємо, що захід не є виконаним. | Not implemented | 0.0
1.2 | Instilling a negative attitude towards corruption | 1.2.1 Everyday corrupt practices are an established norm of conduct and are not perceived as violations of moral or legal norms. There is no consistent demand from the population for public officials to uphold the prescribed rules of ethical conduct and integrity | 1.2.1.2 | The overall level of tolerance of corruption in Ukraine has decreased owing to the creation of favorable conditions for professional development of educators and people working with the public, in particular in matters of academic integrity and instilling an attitude of intolerance of corruption in all its manifestations among students | 1.2.1.2.13 | Developing recommendations on how to increase the level of transparency and integrity in the work of institutions of higher education (with the possible involvement of NGOs and international technical assistance projects in this activity) | 01.03.2023 | 29.02.2024 | National Agency on Corruption Prevention |  | state budget and/or international technical assistance funds | within the established budget allocations for the relevant year | The recommendations have been developed. | Завершено розробку рекомендацій щодо забезпечення прозорості та доброчесності у діяльності закладів вищої освіти. Методичні рекомендації погоджені робочою групою. Методичні рекомендації передані для схвалення Міністерством освіти та науки України (лист № 121-02/71586-24 від 26.09.2024). | Implemented | 0.0
1.2 | Instilling a negative attitude towards corruption | 1.2.1 Everyday corrupt practices are an established norm of conduct and are not perceived as violations of moral or legal norms. There is no consistent demand from the population for public officials to uphold the prescribed rules of ethical conduct and integrity | 1.2.1.2 | The overall level of tolerance of corruption in Ukraine has decreased owing to the creation of favorable conditions for professional development of educators and people working with the public, in particular in matters of academic integrity and instilling an attitude of intolerance of corruption in all its manifestations among students | 1.2.1.2.14 | Approving recommendations for institutions of higher education via a directive of the Ministry of Education and Science, specifying the deadline for their integration into the processes of institutions of higher education | 01.03.2024 | 31.05.2024 | Ministry of Education and Science of Ukraine | National Agency on Corruption Prevention | state budget | within the established budget allocations for the relevant year | The recommendations have been approved via a directive of the Ministry of Education and Science, with the deadlines for their implementation specified. | Наказом МОН від 17 квітня 2025 року № 576 затверджено Методичні рекомендації щодо застосування інструментів та механізмів для трансформації різних сфер функціонування закладів вищої освіти на засадах прозорості та доброчесності. Надіслано інструктивний лист МОН на ЗВО (від 24.04.2025 №1/8061-25), яким зазначається необхідність закріплення в своїх нормативних документах, зокрема статутах, інструкціях, наказах тощо норм щодо підвищення рівня прозорості та доброчесності у діяльності ЗВО, передбачених Методичними рекомендаціями, до 01 вересня 2025 року | Implemented | 0.0
1.2 | Instilling a negative attitude towards corruption | 1.2.1 Everyday corrupt practices are an established norm of conduct and are not perceived as violations of moral or legal norms. There is no consistent demand from the population for public officials to uphold the prescribed rules of ethical conduct and integrity | 1.2.1.2 | The overall level of tolerance of corruption in Ukraine has decreased owing to the creation of favorable conditions for professional development of educators and people working with the public, in particular in matters of academic integrity and instilling an attitude of intolerance of corruption in all its manifestations among students | 1.2.1.2.15 | Integrating the recommendations indicated in subclause 1.2.1.2.13 in normative documents, charters, guidelines, and orders | 01.06.2024 | 31.12.2024 | Ministry of Education and Science of Ukraine |  | state budget | within the established budget allocations for the relevant year | The recommendations indicated in subclause 1.2.1.2.13 have been integrated into normative documents, charters, guidelines, and orders. | За повідомленням Міністерства освіти і науки України (далі - МОН), надіслано інструктивний лист МОН на заклади вищої освіти (далі - ЗВО) (від 24.04.2025 № 1/8061-25), яким зазначається необхідність закріплення у своїх нормативних документах, зокрема статутах, інструкціях, наказах тощо норм щодо підвищення рівня прозорості та доброчесності у діяльності ЗВО, передбачених Методичними рекомендаціями, до 01.10.2025 року. Станом на 09.10.2025 було розроблено опитувальник та надіслано лист ЗВО щодо моніторингу впровадження Методичних рекомендацій у діяльність ЗВО (закріплення в своїх нормативних документах (статутах, інструкціях, наказах тощо) норми щодо підвищення рівня прозорості та доброчесності у діяльності ЗВО, передбачені Методичними рекомендаціями. За результатами проведення моніторингу підготовлено Звіт про стан виконання заходу, надісланий до НАЗК листом МОН від 05.12.2025 № 1/25596-25. Відповідно до Звіту, протягом 08 жовтня 2025 року по 08 листопада 2025 року була проведена оцінка рівня впровадження ЗВО інструментів та механізмів, спрямованих на підвищення прозорості та забезпечення академічної доброчесності. Кількість учасників становила 131 заклад вищої освіти. Було здійснено аналіз нормативно-правового забезпечення прозорості та доброчесності, а саме щодо: - наявності профільних нормативних документів (крім Статутів); - виконання вимог Закону України «Про запобігання корупції»; - стану впровадження антикорупційних та доброчесних механізмів. Таким чином, зважаючи на ступінь відповідності фактично вжитих дій вимогам ДАП щодо змісту та способу виконання заходу, з урахуванням інформації, зазначеної у Звіті, можна простежити врахування ЗВО рекомендацій та їх закріплення. Тому вважаємо за можливе констатувати, що захід є виконаним, але невчасно. | Implemented | 0.0
1.2 | Instilling a negative attitude towards corruption | 1.2.1 Everyday corrupt practices are an established norm of conduct and are not perceived as violations of moral or legal norms. There is no consistent demand from the population for public officials to uphold the prescribed rules of ethical conduct and integrity | 1.2.1.2 | The overall level of tolerance of corruption in Ukraine has decreased owing to the creation of favorable conditions for professional development of educators and people working with the public, in particular in matters of academic integrity and instilling an attitude of intolerance of corruption in all its manifestations among students | 1.2.1.2.16 | Gathering and consolidating data on the implementation of recommendations by institutions of higher education, once every six months | 01.01.2025 | 31.12.2025 | State Education Quality Service of Ukraine | Ministry of Education and Science of Ukraine | state budget | within the established budget allocations for the relevant year | Data has been gathered, consolidated, and submitted to the National Agency. | За інформацією від Державної служби якості освіти в Україні на виконання цього заходу проводилось опитування керівників закладів вищої освіти з метою збору та узагальнення даних з виконання Методичних рекомендацій щодо застосування інструментів та механізмів для трансформації різних сфер функціонування закладів вищої освіти на засадах прозорості та доброчесності, затверджених наказом МОН від 17.04.2025 № 576. Опитування тривало 3-12 грудня 2025 року й охопило 155 закладів вищої освіти України. За результатом такого опитування було зібрано необхідні дані та узагальнено у Звіті про результати опитування щодо застосування інструментів та механізмів для трансформації різних сфер функціонування закладів вищої освіти на засадах прозорості та доброчесності. Разом з тим, сам захід передбачає збір та узагальнення даних щодо виконання рекомендацій закладами вищої освіти раз на півріччя. Тобто збирання та узагальнення відповідних даних мало бути здійснено двічі протягом року. За інформацією від Державної служби якості освіти в Україні, черговий збір даних заплановано до кінця I півріччя 2026 року. Таким чином, зважаючи на ступінь відповідності фактично вжитих дій вимогам ДАП щодо змісту та способу виконання заходу, але враховуючи недотримання встановленої періодичності виконання, вважаємо за можливе констатувати, що захід є виконаним частково. | Partially implemented | 0.0
1.2 | Instilling a negative attitude towards corruption | 1.2.1 Everyday corrupt practices are an established norm of conduct and are not perceived as violations of moral or legal norms. There is no consistent demand from the population for public officials to uphold the prescribed rules of ethical conduct and integrity | 1.2.1.3 | The overall level of tolerance of corruption in Ukraine has decreased owing to the dissemination of information to the public about the negative consequences of corruption and corruption-related offenses (for society and the state, as well as for the perpetrators of such offenses), as well as about the importance of ensuring public control over the activities of executive authorities and local self-government bodies | 1.2.1.3.1 | Developing and disseminating communications and awareness raising materials that shed light on the detrimental effects of corruption and the importance of abiding by integrity strategies (with the possible involvement of NGOs and international technical assistance projects in the implementation of this activity) | 01.03.2023 | 31.12.2025 | National Agency on Corruption Prevention |  | state budget and/or international technical assistance funds | within the established budget allocations for the relevant year | The materials have been developed, published, and disseminated. | Розроблення та розповсюдження інформаційно-просвітницьких матеріалів, які висвітлюють наслідки корупції та важливість дотримання доброчесних стратегій поведінки здійснювалося щоквартально протягом 2023, 2024, 2025 років. У рамках виконання даного заходу у І кварталі 2025 року проведено: 1 Стратегічні сесії з напрацювання Стратегії доброчесності в освіті з понад 120 представниками трьох рівнів освіти. 2. 4 лекції для 541 здобувача вищої освіти з числа студентів, що вивчають дисципліну "Антикорупція та доброчесність". 3. Презентаційно-інформаційні заходи для понад 800 освітян, представників загальної середньої та вищої освіти У II кварталі 2025 року було проведено: 1. Фасилітаційно-презентаційну сесію "Доброчесність в освіті: від рекомендацій до дій" та презентацію Методичних рекомендацій з розбудови доброчесності. 2. Онлайн-лекторій для студентства із залученням НАЗК, НАБУ, САП, ВАКС у межах Тижня Відкритого Уряду. 3. Презентаційно-просвітницький захід "Прозора школа: вперед до доброчесності" для директорів шкіл м.Полтава, Чернігівщини та Сумської області. 4. Вебінар "Школа як простір довіри: безпека та доброчесність" спільно з Національною поліцією та Освітньою службою безпеки. 5. Захід у форматі світового кафе під час Регіонального Саміту учнівського самоврядування Полтавської області "Об’єднані Чесністю: Молодіжна Хартія Прозорості". У III кварталі 2025 року було проведено: 1. Презентаційно-просвітницькі заходи "Прозора школа: розбудова культури доброчесності в освіті" для директорів шкіл: м.Миколаєва, Миколаївщини та Київщини, Одещини. 2. Презентаційний захід «Доброчесність — стала норма в освіті». 3. Презентаційно-просвітницький захід "Прозора професійна освіта" для директорів закладів ПТО та ФПО Одещини. 4. Заходи для студентів Національного університету оборони України; Донецького державного університету внутрішніх справ; учасників "Антикорупційного діалогу: влада громадянське суспільство і молодь"; студентів-учасників проєкту юридичного спрямування «Wave of possibilities. Хвиля 1-2. Категорія: органи державної влади». 5. Зустріч з підлітками в Миколаївському молодіжному просторі Управління молодіжної політики Миколаївської міської ради. У IV кварталі 2025 року було розроблено, опубліковано та поширено серед цільових аудиторій: 1. Рекомендації щодо проведення Тижня доброчесності в організаціях публічного сектору. 2. Методичні рекомендації щодо організації і проведення Тижня доброчесності 2025 в закладах професійної освіти, фахової передвищої освіти. 3. Методичні рекомендації щодо організації і проведення Тижня доброчесності 2025 в закладах загальної середньої освіти. 4. Навчальні матеріали для учнів початкової школи у формі авторських казок антикорупційного спрямування "Таємниця Золотого моста", "Світло над Чесляндією". Таким чином, зважаючи на ступінь відповідності фактично вжитих дій вимогам ДАП щодо змісту та способу виконання заходу, вважаємо за можливе констатувати, що захід є виконаним повністю. | Implemented | 0.0
1.2 | Instilling a negative attitude towards corruption | 1.2.1 Everyday corrupt practices are an established norm of conduct and are not perceived as violations of moral or legal norms. There is no consistent demand from the population for public officials to uphold the prescribed rules of ethical conduct and integrity | 1.2.1.3 | The overall level of tolerance of corruption in Ukraine has decreased owing to the dissemination of information to the public about the negative consequences of corruption and corruption-related offenses (for society and the state, as well as for the perpetrators of such offenses), as well as about the importance of ensuring public control over the activities of executive authorities and local self-government bodies | 1.2.1.3.2 | Developing and disseminating communications and awareness raising materials covering the role of citizens in anticorruption efforts and the opportunities for public oversight over the activities of executive government agencies and local self-government bodies (with the possible involvement of NGOs and international technical assistance projects in this activity) | 01.06.2023 | 31.12.2025 | National Agency on Corruption Prevention |  | state budget | within the established budget allocations for the relevant year | The materials have been developed, published, and disseminated. | Розроблення та розповсюдження інформаційно-просвітницьких матеріалів, які висвітлюють роль громадян у запобіганні та протидії корупції та можливості здійснення громадського контролю за діяльністю органів виконавчої влади та органів місцевого самоврядування здійснювалося протягом звітних періодів у 2024 та 2025 роках. У 2024 році було розміщено та поширено ролики про роль громадського контролю в ефірі центральних каналів, на регіональному телебаченні. Також були борди, розміщені в Київський області. У партнерстві з АТ “Укрзалізниця” було розміщено ролики на екранах центральних залізничних вокзалів Києва, Львова, Дніпра, Луцька: ролики на екранах потягів депо “Коломия” та “Коростень”, а також були ролики в комунальному транспорті та метрополітені. У рамках виконання даного заходу у І кварталі 2025 року в усіх регіонах (за винятком окупованих територій) розміщено борди, сітілайти, плакати у громадському транспорті, органах місцевого самоврядування, центрах надання адміністративних послуг, закладах охорони здоров'я, центрах для внутрішньо переміщених осіб. Ці матеріали висвітлюють роль громадян у запобіганні та протидії корупції та можливості здійснення громадського контролю за діяльністю органів виконавчої влади та органів місцевого самоврядування. Поширено матеріали із порадами для антикорупційної комунікації в громадах. Оприлюднено дані соціологічних досліджень, які демонструють підвищення залученості громадян до контролю за владою та антикорупційної діяльності. У II кварталі 2025 року було завершено поширення матеріалів, присвячених громадському контролю, у громадському транспорті, органах місцевого самоврядування, центрах надання адміністративних послуг, закладах охорони здоров'я, центрах для внутрішньо переміщених осіб тощо у регіонах України. Матеріали в електронному та друкованому вигляді поширено на заходах, які проводило НАЗК, в Києві, Полтаві та Запоріжжі. Поширювалися дописи - пости про реалізацію кампанії про громадський контроль: -Чому цифрові сервіси є важливим елементом запобігання корупції? -Як громадський контроль допомагає мінімізувати корупційні порушення? -Куди потрібно звернутися, щоб повідомити про факти корупції? А також матеріали про типи корупції та корупційних порушень і покарання за недотримання антикорупційного законодавства. У III кварталі 2025 року здійснювалася пряма просвітницька діяльність у регіонах, а саме: проведено зустріч представників НАЗК із молоддю та освітянами в Миколаєві; активне залучення до публічних дискусій через медіа (подкасти та радіоефіри) з метою детального роз’яснення складних питань академічної доброчесності, вимірювання корупції та ефективних механізмів громадського контролю та запобігання корупції. У IV кварталі 2025 року у взаємодії з Київською обласною військовою адміністрацією та Київською міською державною адміністрацією розміщено зовнішню рекламу з інформаційними матеріалами щодо ролі інструментів громадського контролю в запобіганні корупції (5 бордів і 10 сітілайтів у м. Києві, а також 30 бордів та 10 сітілайтів на території Київської області). У співпраці з Міністерством культури України відеоролики, розроблені в межах інформаційної кампанії «Корупція боїться твого контролю» розповсюдили на своїх диджитал-ресурсах обласні військові адміністрації та органи місцевого самоврядування. Представники Національного агентства взяли участь у низці заходів, присвячених питанням взаємодії з медіа, громадськими організаціями та громадському контролю, зокрема у панелях Donbas Media Forum, де інформували про те, як ефективно взаємодіяти НАЗК з громадськістю. Таким чином, зважаючи на ступінь відповідності фактично вжитих дій вимогам ДАП щодо змісту та способу виконання заходу, вважаємо за можливе констатувати, що захід є виконаним повністю. | Implemented | 0.0
1.2 | Instilling a negative attitude towards corruption | 1.2.1 Everyday corrupt practices are an established norm of conduct and are not perceived as violations of moral or legal norms. There is no consistent demand from the population for public officials to uphold the prescribed rules of ethical conduct and integrity | 1.2.1.3 | The overall level of tolerance of corruption in Ukraine has decreased owing to the dissemination of information to the public about the negative consequences of corruption and corruption-related offenses (for society and the state, as well as for the perpetrators of such offenses), as well as about the importance of ensuring public control over the activities of executive authorities and local self-government bodies | 1.2.1.3.3 | Preparing a communications and awareness raising campaign devoted to the importance of public oversight over the activities of executive government agencies and local self-government bodies (with the possible involvement of NGOs and international technical assistance projects in this activity) | 01.07.2023 | 31.10.2023 | National Agency on Corruption Prevention | Ministry of Culture and Strategic Communications of Ukraine | state budget and/or international technical assistance funds | within the established budget allocations for the relevant year and/or international technical assistance funds | The materials have been developed, published, and disseminated. | За повідомленням Національного агентства з питань запобігання корупції, станом на 30.09.2024 р. "підготовлено матеріали інформаційно-просвітницької кампанії, присвяченої важливості здійснення громадського контролю за діяльністю органів державної влади та органів місцевого самоврядування. Слогани кампанії "Корупція - не спадок" та "Корупція боїться твого контролю". В межах кампанії розроблено заходи та матеріали для всіх регіонів України (ролики про роль громадського контролю в ефірі центральних та регіональних каналів, ефіри на регіональному телебаченні, зовнішню соціальну рекламу, домовленості про партнерство з АТ “Укрзалізниця” та ролики в міському громадському транспорті тощо". | Implemented | 0.0
1.2 | Instilling a negative attitude towards corruption | 1.2.1 Everyday corrupt practices are an established norm of conduct and are not perceived as violations of moral or legal norms. There is no consistent demand from the population for public officials to uphold the prescribed rules of ethical conduct and integrity | 1.2.1.3 | The overall level of tolerance of corruption in Ukraine has decreased owing to the dissemination of information to the public about the negative consequences of corruption and corruption-related offenses (for society and the state, as well as for the perpetrators of such offenses), as well as about the importance of ensuring public control over the activities of executive authorities and local self-government bodies | 1.2.1.3.4 | Conducting a communications and awareness raising campaign devoted to the importance of public oversight over the activities of executive government agencies and local self-government bodies (with the possible involvement of NGOs and international technical assistance projects in this activity) | 01.11.2023 | 30.04.2024 | National Agency on Corruption Prevention | Ministry of Culture and Strategic Communications of Ukraine | state budget and/or international technical assistance funds | within the established budget allocations for the relevant year and/or international technical assistance funds | The communications and awareness raising campaign has been completed. The campaign results have been summarized. | У партнерстві НАЗК з органами місцевого самоврядування, обласними військовими адміністраціями та державними підприємствами інформаційні матеріали кампанії, об’єднані лейтмотивом "Корупція боїться твого контролю", транслювалися на загальнонаціональних та місцевих телеканалах і розміщувалися у громадському транспорті, на вокзалах, у ЦНАПах, інших адміністративних будівлях та на вулицях міст і селищ. Відеоролики, білборди, сітілайти та плакати, створені в рамках кампанії, стосуються актуальних питань, таких як використання бюджетних коштів під час війни, фінансування відбудови, цільове використання бюджету громади, містобудування, облаштування цивільних захисних споруд. Вони містять посилання на навчальний відеокурс НАЗК з громадського контролю, де детально роз’яснюються механізми, що дозволяють кожному громадянину долучитися до моніторингу, контролю та участі у прийнятті рішень владою. Ознайомитися з курсом можна просто, відсканувавши QR-код, розміщений на рекламному зображенні, за допомогою смартфона. Захід успішно реалізовано, охоплено широкі цільові аудиторії в регіонах та на національному рівні. Показник "кампанія проведена" виконано, підсумки зафіксовано через публічну комунікацію, фотозвіти та аналітичне узагальнення охоплених тем. | Implemented | 0.0
1.2 | Instilling a negative attitude towards corruption | 1.2.1 Everyday corrupt practices are an established norm of conduct and are not perceived as violations of moral or legal norms. There is no consistent demand from the population for public officials to uphold the prescribed rules of ethical conduct and integrity | 1.2.1.4 | The overall level of tolerance of corruption in Ukraine has decreased owing to the implementation of comprehensive measures aimed at instilling in public servants a perception of themselves as people serving the interests of the Ukrainian nation, as well as public trust in public servants as the key reason of why they hold their office | 1.2.1.4.1 | Developing an online course on the general provisions of anticorruption legislation for civil servants | 01.03.2023 | 30.04.2023 | National Agency on Corruption Prevention |  | state budget | within the established budget allocations for the relevant year | The course has been developed and published on the NAZK.Study learning platform. | According to the National Agency on Corruption Prevention, in pursuance of measure 1.2.1.4.1, “the integrity civil service course was launched with a delayed deadline in accordance with the State Anti-Corruption Program due to the understaffing of the civil servants training department and the training product development department, so the course devising actually started in March 2013, and the course was launched in June.” | Implemented | 0.0
1.2 | Instilling a negative attitude towards corruption | 1.2.1 Everyday corrupt practices are an established norm of conduct and are not perceived as violations of moral or legal norms. There is no consistent demand from the population for public officials to uphold the prescribed rules of ethical conduct and integrity | 1.2.1.4 | The overall level of tolerance of corruption in Ukraine has decreased owing to the implementation of comprehensive measures aimed at instilling in public servants a perception of themselves as people serving the interests of the Ukrainian nation, as well as public trust in public servants as the key reason of why they hold their office | 1.2.1.4.2 | Developing an online course on the particularities of anticorruption legislation for representatives of local self-government bodies (with the possible involvement of NGOs and international technical assistance projects in this activity) | 01.03.2023 | 30.06.2023 | National Agency on Corruption Prevention |  | state budget | within the established budget allocations for the relevant year | The course has been developed and published on the NAZK.Study learning platform. | According to the notification of the National Agency on Corruption Prevention, in order to implement measure 1.2.1.4.2., "the course was developed and published on the Study.NAZK platform. A public presentation of the course was held at the Forum of Virtuous Communities." | Implemented | 0.0
1.2 | Instilling a negative attitude towards corruption | 1.2.1 Everyday corrupt practices are an established norm of conduct and are not perceived as violations of moral or legal norms. There is no consistent demand from the population for public officials to uphold the prescribed rules of ethical conduct and integrity | 1.2.1.4 | The overall level of tolerance of corruption in Ukraine has decreased owing to the implementation of comprehensive measures aimed at instilling in public servants a perception of themselves as people serving the interests of the Ukrainian nation, as well as public trust in public servants as the key reason of why they hold their office | 1.2.1.4.3 | Developing an online course devoted to the particularities of anticorruption legislation for judges | 01.03.2023 | 31.07.2023 | National Agency on Corruption Prevention |  | state budget | within the established budget allocations for the relevant year | The course has been developed and published on the NAZK.Study learning platform. | The course was developed and published on the Study.NAZK platform. As of the end of the third quarter of 2023, more than 400 users completed the course. | Implemented | 0.0
1.2 | Instilling a negative attitude towards corruption | 1.2.1 Everyday corrupt practices are an established norm of conduct and are not perceived as violations of moral or legal norms. There is no consistent demand from the population for public officials to uphold the prescribed rules of ethical conduct and integrity | 1.2.1.4 | The overall level of tolerance of corruption in Ukraine has decreased owing to the implementation of comprehensive measures aimed at instilling in public servants a perception of themselves as people serving the interests of the Ukrainian nation, as well as public trust in public servants as the key reason of why they hold their office | 1.2.1.4.4 | Developing an online course devoted to the particularities of anticorruption legislation for representatives of the law enforcement sector | 01.03.2023 | 31.08.2023 | National Agency on Corruption Prevention |  | state budget | within the established budget allocations for the relevant year | The course has been developed and published on the NAZK.Study learning platform. | The course was developed and published on the Study.NAZK platform. | Implemented | 0.0
1.2 | Instilling a negative attitude towards corruption | 1.2.1 Everyday corrupt practices are an established norm of conduct and are not perceived as violations of moral or legal norms. There is no consistent demand from the population for public officials to uphold the prescribed rules of ethical conduct and integrity | 1.2.1.4 | The overall level of tolerance of corruption in Ukraine has decreased owing to the implementation of comprehensive measures aimed at instilling in public servants a perception of themselves as people serving the interests of the Ukrainian nation, as well as public trust in public servants as the key reason of why they hold their office | 1.2.1.4.5 | Developing an online course devoted to the particularities of anticorruption legislation for parliament members | 01.03.2023 | 31.08.2023 | National Agency on Corruption Prevention |  | state budget | within the established budget allocations for the relevant year | The course has been developed and published on the NAZK.Study learning platform. | The course was developed and published on the Study.NAZK platform. | Implemented | 0.0
1.2 | Instilling a negative attitude towards corruption | 1.2.1 Everyday corrupt practices are an established norm of conduct and are not perceived as violations of moral or legal norms. There is no consistent demand from the population for public officials to uphold the prescribed rules of ethical conduct and integrity | 1.2.1.4 | The overall level of tolerance of corruption in Ukraine has decreased owing to the implementation of comprehensive measures aimed at instilling in public servants a perception of themselves as people serving the interests of the Ukrainian nation, as well as public trust in public servants as the key reason of why they hold their office | 1.2.1.4.6 | Developing an online course devoted to the functioning of government agencies and local self-government bodies and their interaction with various social groups (businesses, the public, etc.) (with the possible involvement of NGOs and international technical assistance projects in this activity) | 01.03.2023 | 31.08.2023 | National Agency on Corruption Prevention |  | state budget | within the established budget allocations for the relevant year | The course has been developed and published on the NAZK.Study learning platform. | The course was developed and published on the Study.NAZK platform. At the time of reporting, 25,746 people were registered for the course, and 23,705 people received certificates of successful completion. | Implemented | 0.0
1.2 | Instilling a negative attitude towards corruption | 1.2.1 Everyday corrupt practices are an established norm of conduct and are not perceived as violations of moral or legal norms. There is no consistent demand from the population for public officials to uphold the prescribed rules of ethical conduct and integrity | 1.2.1.4 | The overall level of tolerance of corruption in Ukraine has decreased owing to the implementation of comprehensive measures aimed at instilling in public servants a perception of themselves as people serving the interests of the Ukrainian nation, as well as public trust in public servants as the key reason of why they hold their office | 1.2.1.4.7 | Conducting systemic training of civil servants and local self-government officials on anticorruption topics (anticorruption, standards of integrity and ethical conduct) in civil service and service at local self-government bodies | 01.03.2023 | 31.12.2025 | National Agency of Ukraine on Civil Service |  | state budget and/or international technical assistance funds | within the established budget allocations for the relevant year | At least 2,000 individuals have completed training in anticorruption and standards of integrity and ethical conduct. | За інформацією, наданою Національним агентством з питань державної служби України (далі - НАДС), за результатами конкурсного відбору було визначено виконавців державного замовлення НАДС на підвищення кваліфікації державних службовців та посадових осіб місцевого самоврядування у 2025 році та затверджено їм обсяги державного замовлення, у тому числі на підвищення кваліфікації з питань антикорупційної тематики (наказ НАДС від 15.08.2025 № 112-25 «Про затвердження обсягів державного замовлення НАДС на підвищення кваліфікації державних службовців та посадових осіб місцевого самоврядування у 2025 році»). Упродовж серпня-вересня 2025 року в закладах освіти, відібраних на конкурсній основі, за державним замовленням НАДС підвищили кваліфікацію 1093 державних службовців, які займають посади державної служби категорій «Б» та «В», посадових осіб місцевого самоврядування з питань антикорупційної тематики (доброчесність, запобігання корупції, стандарти доброчесної та етичної поведінки). Загалом протягом 2025 року навчання з питань антикорупційної тематики (доброчесність, запобігання корупції, стандарти доброчесної та етичної поведінки) пройшли 3 056 державних службовців, які займають посади державної служби категорій «Б» та «В», та посадових осіб місцевого самоврядування. Інформаційно-аналітичний звіт про результати надання освітніх послуг закладами освіти на підвищення кваліфікації державних службовців, голів місцевих державних адміністрацій, їх перших заступників та заступників, посадових осіб місцевого самоврядування у 2025 році буде підготовлено та розміщено на офіційному вебсайті НАДС у лютому 2026 року. Таким чином, зважаючи на ступінь відповідності фактично вжитих дій вимогам ДАП щодо змісту та способу виконання заходу, вважаємо за можливе констатувати, що захід є виконаним повністю. | Implemented | 0.0
1.2 | Instilling a negative attitude towards corruption | 1.2.1 Everyday corrupt practices are an established norm of conduct and are not perceived as violations of moral or legal norms. There is no consistent demand from the population for public officials to uphold the prescribed rules of ethical conduct and integrity | 1.2.1.4 | The overall level of tolerance of corruption in Ukraine has decreased owing to the implementation of comprehensive measures aimed at instilling in public servants a perception of themselves as people serving the interests of the Ukrainian nation, as well as public trust in public servants as the key reason of why they hold their office | 1.2.1.4.8 | Ensuring the development of a model general professional (certification) program of professional development for civil servants and officials of local self-government bodies with a focus on anticorruption topics (anticorruption, standards of integrity and ethical conduct) | 01.04.2023 | 31.12.2025 | National Agency of Ukraine on Civil Service | National Agency on Corruption Prevention | state budget | within the established budget allocations for the relevant year | The model general program has been developed. | According to the National Agency of Ukraine on Civil Service (NAUCS), in pursuance of measure 1.2.1.4.8, “a standard general professional (certificate) advanced training program “Prevention of Corruption and Implementation of Integrity Standards in the Civil Service and Local Government Bodies” was developed, approved by NAUCS Order No. 81-23 of June 09, 2023 and posted on the NAUCS official website at: http://surl.li/hvers.” | Implemented | 0.0
1.2 | Instilling a negative attitude towards corruption | 1.2.1 Everyday corrupt practices are an established norm of conduct and are not perceived as violations of moral or legal norms. There is no consistent demand from the population for public officials to uphold the prescribed rules of ethical conduct and integrity | 1.2.1.4 | The overall level of tolerance of corruption in Ukraine has decreased owing to the implementation of comprehensive measures aimed at instilling in public servants a perception of themselves as people serving the interests of the Ukrainian nation, as well as public trust in public servants as the key reason of why they hold their office | 1.2.1.4.9 | Systemically staging communications and awareness raising events devoted to the issues of integrity in civil service, the role of civil servants, the functioning of the state apparatus, interactions with citizens and businesses, etc. (with the possible involvement of NGOs and international technical assistance projects in this activity) | 01.07.2023 | 31.12.2025 | National Agency on Corruption Prevention | National Agency of Ukraine on Civil Service | state budget and/or international technical assistance funds | within the established budget allocations for the relevant year and/or international technical assistance funds | At least four events are staged each year. | Системне проведення інформаційно-просвітницьких заходів, присвячених питанням доброчесності на публічній службі, ролі публічних службовців, функціонуванню державного апарату, взаємодії з громадянами та бізнесом здійснювалося протягом 2023, 2024, 2025 років. У 2023 році було проведено 4 інформаційно-просвітницькі заходи: Форум доброчесних громад; інформаційно-просвітницький захід з теми доброчесності та презентація курсу для суддів; Доброчесність на практиці: важливі питання від поліцейських; Вирішення ситуацій конфлікту інтересів та моральних дилем для поліцейських. Протягом 2024 року було: • проведено інформаційно-просвітницький захід для слідчих та оперуповноважених НПУ “Необґрунтовані активи та незаконне збагачення”. До навчання долучились понад 900 правоохоронців; • 2 квітня 2024 року НАДС взято участь в Ярмарці вакансій «Career week-2024». Під час заходу висвітлено питання процедури стажування на публічній службі, вступу на публічну службу, а також можливостей щодо проходження публічної служби. Участь у заході взяли більше 200 студентів; • 18 квітня 2024 року в рамках навчання за програмою підвищення кваліфікації «Роль керівника у побудові доброчесного середовища організації», що проходив для публічних службовців вищого корпусу державної служби, Голова НАДС Наталія Алюшина розповіла про важливість формування доброчесного іміджу органів влади та яким чином цього можна досягти; • 26 червня 2024 року відбулась зустріч Голови НАДС Наталії Алюшиної зі студентами Університету «КРОК» та фахового коледжу Університету «КРОК»; • проведено навчально-просвітницький захід “Практичні поради: як запобігти порушенню антикорупційного законодавства та як розслідувати антикорупційні справи” для керівників структурних підрозділів центрального органу управління Національної поліції України; • 19 грудня 2024 року проведено підсумковий у 2024 році координаційний форум фахівців з державних комунікацій, представників медіа, громадських організацій та проектів міжнародної технічної допомоги; • та ін. У рамках виконання даного заходу у І кварталі 2025 року основні зусилля були зосереджені на проведені інформаційно-просвітницьких заходів з питань декларування і дотримання законодавства про запобігання конфлікту інтересів на публічній службі. Також було проведено три регіональні поїздки до Кропивницького, Тернополя, Запоріжжя. У II кварталі 2025 року було проведено та прокомуніковано просвітницькі заходи з питань доброчесності на публічній службі, зокрема під час поїздок до регіонів, навчання для публічних службовців, зустрічей з освітянами та студентами, кампанії декларування тощо. Протягом III кварталу 2025 року системні інформаційно-просвітницькі заходи охопили публічну службу та взаємодію з бізнесом. Важливим кроком стало впровадження нового антикорупційного інструмента – Реєстру прозорості. Зокрема, 01.09.2025 було проведено презентацію його можливостей та функцій, а також опубліковано детальну інструкцію для забезпечення відкритої та прозорої роботи інституту лобіювання. Для підвищення доброчесності в держсекторі НАЗК проводило регіональні поїздки на Миколаївщину та Київщину, де обговорювалися та ідентифікувалися корупційні ризики у важливих сферах для регіонів (відбудова, закупівлі, земельні відносини). Інформаційна кампанія доповнена роз’ясненнями щодо правил отримання подарунків державними службовцями та висвітленням позитивних результатів цифровізації, зокрема економічного та антикорупційного ефекту сервісу «Дія». Також було прокомуніковано запуск нового онлайн-курсу з корпоративного управління та антикорупційного комплаєнсу, що спрямований на підвищення професійної доброчесності комунальних підприємств тощо. У IV кварталі 2025 року для підвищення доброчесності в держсекторі НАЗК провело регіональну поїздку на Сумщину, де обговорювалися та ідентифікувалися корупційні ризики у важливих сферах для регіону (відбудова, закупівлі, земельні відносини). 30 жовтня 2025 року проведено третій Форум доброчесності громад, який є щорічною платформою НАЗК для обміну досвідом і координації дій у розбудові доброчесності на місцевому рівні. Таким чином, зважаючи на ступінь відповідності фактично вжитих дій вимогам ДАП щодо змісту та способу виконання заходу, вважаємо за можливе констатувати, що захід є виконаним повністю. | Implemented | 0.0
1.2 | Instilling a negative attitude towards corruption | 1.2.1 Everyday corrupt practices are an established norm of conduct and are not perceived as violations of moral or legal norms. There is no consistent demand from the population for public officials to uphold the prescribed rules of ethical conduct and integrity | 1.2.1.5 | The overall level of tolerance of corruption in Ukraine has decreased owing to the establishment of the culture of the rule of law, an atmosphere of integrity and intolerance of corruption in society, including through public service advertising. | 1.2.1.5.1 | Developing and disseminating communications and awareness raising materials devoted to the functioning of government agencies and local self-government bodies and the rule of law (with the possible involvement of NGOs and international technical assistance projects in the implementation of this activity) | 01.01.2024 | 31.01.2025 | National Agency on Corruption Prevention |  | state budget and/or international technical assistance funds | within the established budget allocations for the relevant year | The materials have been developed and published on resources of the National Agency. | За інформацією від виконавця - створено та поширено близько 20 публікацій, авторських статей, інфографік та коментарів для медіа на тему запобігання корупції, верховенства права, функціонування держави. В тому числі підготовлено низку інформаційно-просвітницьких матеріалів про ключові функції запобігання корупції, зокрема декларування, дотримання законодавства щодо конфлікту інтересів, виконання заходів Державної антикорупційної програми на 2023 – 2025 роки, підслідність тощо. Захід виконано відповідно до встановленого показника: матеріали розроблено, оприлюднено та забезпечено їхнє публічне поширення. Тематика відповідає завданню популяризації принципів верховенства права та розуміння функцій державних інституцій у контексті запобігання корупції. | Implemented | 0.0
1.2 | Instilling a negative attitude towards corruption | 1.2.1 Everyday corrupt practices are an established norm of conduct and are not perceived as violations of moral or legal norms. There is no consistent demand from the population for public officials to uphold the prescribed rules of ethical conduct and integrity | 1.2.1.5 | The overall level of tolerance of corruption in Ukraine has decreased owing to the establishment of the culture of the rule of law, an atmosphere of integrity and intolerance of corruption in society, including through public service advertising. | 1.2.1.5.2 | Developing and disseminating communications and awareness raising materials that shed light on the detrimental effects of corruption and the importance of abiding by integrity strategies (with the possible involvement of NGOs and international technical assistance projects in the implementation of this activity) | 01.01.2024 | 31.12.2025 | National Agency on Corruption Prevention |  | state budget and/or international technical assistance funds | within the established budget allocations for the relevant year | The materials have been developed and published on resources of the National Agency. | Розроблення та розповсюдження інформаційно-просвітницьких матеріалів, які висвітлюють наслідки корупції та важливість дотримання доброчесних стратегій поведінки здійснювалося протягом 2024 та 2025 років. У 2024 році було опубліковано 18 матеріалів, які висвітлюють важливість доброчесних стратегій поведінки. (Охоплення у соцмережах Агентства – 339 379, з них у Facebook – 171 838, медіа – 300 000). Частину матеріалів розроблено, опубліковано та розповсюджено, зокрема щодо доброчесності медичних працівників. Створено та поширено 22 публікації на ресурсах НАЗК, з них 14 постів про відео про родину Принциповичів щодо протидії побутовій корупції та низка матеріалів від Офісу доброчесності НАЗК. Ролики про родину Принциповичів транслювалися на Суспільному телебаченні та радіо. Ролики про громадський контроль поширено в ефірах трьох національних каналів: ICTV2, СТБ, Новий канал. Охоплення – 2 428 441. У 2025 році розроблено та випущено серію марок "Минуле вчить, як будувати майбутнє", присвячену "артефактам" корупції з історіями, які описують наслідки корупційних злочинів. Створено та поширено понад 20 інформаційно-просвітницьких матеріалів, які висвітлюють наслідки корупції та важливість дотримання доброчесних стратегій поведінки - під час регіональних поїздок та інформаційних і просвітницьких заходів, організованих НАЗК. Розроблено, оприлюднено, поширено серію текстових матеріалів та інфографік на тему конфлікту інтересів у публічних службовців; викривання корупції тощо. Матеріали були багаторазово републіковані іншими ЦОВВ, регіональними органами влади та ОМС, медіа і ГО. Забезпечено системне інформування суспільства та публічних службовців про наслідки корупційних дій. Загалом підготовлено 9 інформаційних матеріалів. Ключовий акцент зроблено на детальному роз'ясненні правових механізмів притягнення до відповідальності, включаючи кримінальну відповідальність за корупційні злочини (зокрема, за неправдиве декларування) та адміністративні правопорушення, а також публікацію інформації про обвинувальні вироки та судові рішення, що демонструють реалізацію закону на практиці. Підготовлено 9 постів для соціальних мереж, аналітичну статтю. Таким чином, зважаючи на ступінь відповідності фактично вжитих дій вимогам ДАП щодо змісту та способу виконання заходу, вважаємо за можливе констатувати, що захід є виконаним повністю. | Implemented | 0.0
1.2 | Instilling a negative attitude towards corruption | 1.2.1 Everyday corrupt practices are an established norm of conduct and are not perceived as violations of moral or legal norms. There is no consistent demand from the population for public officials to uphold the prescribed rules of ethical conduct and integrity | 1.2.1.5 | The overall level of tolerance of corruption in Ukraine has decreased owing to the establishment of the culture of the rule of law, an atmosphere of integrity and intolerance of corruption in society, including through public service advertising. | 1.2.1.5.3 | Conducting communications and awareness raising campaigns devoted to popularizing integrity strategies (with the possible involvement of NGOs and international technical assistance projects in this activity) | 01.01.2024 | 31.12.2025 | National Agency on Corruption Prevention |  | state budget and/or international technical assistance funds | within the established budget allocations for the relevant year and/or international technical assistance funds | The communications and awareness raising campaign has been completed. The campaign results have been summarized. | Проведення інформаційно-просвітницьких кампаній, присвячених популяризації стратегій доброчесної поведінки здійснювалося протягом 2024 та 2025 років. Протягом 2024 року було розроблено та поширено матеріали (мультсеріал та документальний серіал, брошура). 16 серпня організовано та прокомуніковано Форум доброчесності громад. 17 серпня проведено тренінг зі стратегічних комунікацій для представників органів місцевого самоврядування у межах Форуму доброчесності громад 2024. Організовано флешмоб до Міжнародного дня боротьби з корупцією, до якого залучено органи влади, держпідприємства, громадські організації, які опублікували понад 40 дописів у Facebook з хештегом #AnticorDay2024. До Міжнародного дня боротьби з корупцією організовано низку коментарів, сюжетів та інтерв'ю на ТБ. Протягом I кварталу 2025 року організовано заходи для різних цільових груп в трьох регіонах України (Кропивницький, Запоріжжя, Тернопіль). Реалізовано проект із залучення ветеранів до антикорупційної діяльності. У II кварталі 2025 року організовано заходи для різних цільових груп у двох регіонах України (Чернігів, Полтава). Проведено комунікаційну кампанію щодо усунення корупційних ризиків у лісовому господарстві. А також започатковано нову рубрику “Медіа на тему корупції”, у якій висвітлюються матеріали з медіа, що містять поради (Медіа на тему корупції: як діяти, коли вимагають хабар за сесію?). Протягом III кварталу 2025 року проведення кампаній з популяризації доброчесної поведінки відбувалося шляхом регіональних поїздок і активної медіа-комунікації. Було організовано просвітницькі заходи для різних аудиторій на Київщині та Миколаївщині, що дозволило безпосередньо взаємодіяти з громадянами та інформувати про стратегії доброчесності на місцевому рівні. У соціальних мережах, особливо в Instagram, постійно поширювалися різноманітні матеріали – відео, інфографіка та інформаційні пости, які промотували та пояснювали доброчесні моделі поведінки широкій аудиторії. Проведено комунікаційну кампанію, присвячену усуненню корупційних ризиків у сфері відбудови, що є критично важливим для забезпечення прозорості та доброчесності у процесі відновлення держави. У IV кварталі 2025 року системні інформаційно-просвітницькі заходи охопили публічну службу та заклади освіти та були присвячені питанням доброчесності. 20 закладів професійної освіти з 17 міст і 15 областей стали учасниками нового пілотного проєкту «Прозора професійна освіта», який реалізує Офіс доброчесності НАЗК . Загалом надійшло 115 заявок з 21 області України, серед них експерти обрали 20 закладів. Також НАЗК презентувало Стратегію розвитку доброчесності в освіті на 2026–2030 роки. Понад дві тисячі закладів освіти з усіх регіонів України провели 7 тисяч уроків доброчесності. Крім того, Офіс доброчесності НАЗК провів тренінг «Ключові аспекти антикорупційного законодавства» для військовослужбовців Центр спеціального призначення "Омега". Враховуючи інформацію, надану за попередні звітні періоди, а також зважаючи на ступінь відповідності фактично вжитих дій вимогам ДАП, можна констатувати, що заходом досягнуто значного прогресу, однак показник формально не виконано у повному обсязі, оскільки відсутня інформація щодо узагальнення результатів кампанії (підбиття підсумків). | Partially implemented | 0.0
1.2 | Instilling a negative attitude towards corruption | 1.2.1 Everyday corrupt practices are an established norm of conduct and are not perceived as violations of moral or legal norms. There is no consistent demand from the population for public officials to uphold the prescribed rules of ethical conduct and integrity | 1.2.1.6 | The level of awareness of citizens who realize the importance of standards of integrity and ethical conduct of public servants has increased owing to active and systematic communications, awareness-raising and training activities integrated into formal and informal education | 1.2.1.6.1 | Developing and disseminating communications and awareness raising materials that explain the workings of the state and public institutions, the rights and duties of citizens, and where citizens should go to defend their rights and interests (with the possible involvement of NGOs and international technical assistance projects in this activity) | 01.01.2024 | 31.01.2025 | National Agency on Corruption Prevention | National Agency of Ukraine on Civil Service | state budget and/or international technical assistance funds | within the established budget allocations for the relevant year | The communications and awareness raising materials have been developed and disseminated among various target audiences. | Показник виконано в повному обсязі. За інформацією від виконавця - створено та поширено інформаційно-просвітницькі матеріали з понад 20 тем, що охоплюють питання функціонування держави та публічних інституцій, а також прав і обов’язків громадян щодо можливості звернення для захисту власних прав та інтересів. Зокрема, розкриті питання декларування публічних службовців та дотримання ними законодавства про конфлікт інтересів, канали повідомлень про корупцію, права та статус викривачів корупції, підслідність органів щодо корупційних правопорушень тощо. За даними системи моніторингу Semantrum, загальне охоплення аудиторії становить понад 5 мільйонів контактів, що підтверджує масштабність та ефективність розповсюдження. | Implemented | 0.0
1.2 | Instilling a negative attitude towards corruption | 1.2.1 Everyday corrupt practices are an established norm of conduct and are not perceived as violations of moral or legal norms. There is no consistent demand from the population for public officials to uphold the prescribed rules of ethical conduct and integrity | 1.2.1.6 | The level of awareness of citizens who realize the importance of standards of integrity and ethical conduct of public servants has increased owing to active and systematic communications, awareness-raising and training activities integrated into formal and informal education | 1.2.1.6.2 | Developing and disseminating communications and awareness raising materials devoted to standards of integrity and ethical conduct of civil servants, explaining what citizens should do when such civil servants violate those standards (with the possible involvement of NGOs and international technical assistance projects in this activity) | 01.12.2023 | 31.12.2024 | National Agency on Corruption Prevention | National Agency of Ukraine on Civil Service | state budget and/or international technical assistance funds | within the established budget allocations for the relevant year and/or international technical assistance funds | The communications and awareness raising materials have been developed and disseminated among various target audiences. | Розроблено та поширено інформаційно-просвітницькі матеріали, присвячені стандартам доброчесної та етичної поведінки публічних службовців та питанням щодо дій громадян, якщо вони їх не дотримуються. Зокрема, НАЗК спільно з партнерами вперше організували тренінг зі стратегічних комунікацій для представників ОМС в межах Форуму доброчесності громад (https://bit.ly/4g0RFqz) та виготовили відповідний онлайн-курс (за посиланнями в додатку). Інформаційні матеріали також були поширені під час низки організованих НАЗК з партнерами заходів (посилання додаються). | Implemented | 0.0
1.2 | Instilling a negative attitude towards corruption | 1.2.1 Everyday corrupt practices are an established norm of conduct and are not perceived as violations of moral or legal norms. There is no consistent demand from the population for public officials to uphold the prescribed rules of ethical conduct and integrity | 1.2.1.6 | The level of awareness of citizens who realize the importance of standards of integrity and ethical conduct of public servants has increased owing to active and systematic communications, awareness-raising and training activities integrated into formal and informal education | 1.2.1.6.3 | Developing and disseminating communications and awareness raising materials devoted to the role of elections in a democratic society, the importance of voting, and the monitoring of the conduct of elected officials (with the possible involvement of NGOs and international technical assistance projects in the implementation of this activity) | 01.03.2023 | 31.12.2025 | The Central Election Commission of Ukraine |  | state budget and/or international technical assistance funds | within the established budget allocations for the relevant year and/or international technical assistance funds | The communications and awareness raising materials have been developed and disseminated among various target audiences. | Розроблення та розповсюдження інформаційно-просвітницьких матеріалів, присвячених ролі виборів у демократичному суспільстві, важливості участі у виборах здійснювалося протягом 2023, 2024 та 2025 років. У 2023 на офіційному вебсайті Центральної виборчої комісії (далі - Комісія) розміщено посилання на безкоштовний просвітній портал про вибори – інформаційно-просвітницьку онлайн-платформу "ЦВК: просвіта", розроблений в рамках виконання проекту міжнародної технічної допомоги. Також було розроблено навчально-просвітницькі матеріали для наповнення навчального онлайн-курсу для офіційних спостерігачів з питань спостереження за виборами в Україні. Крім цього, на вебсайті Комісії у розділі "Актуальна інформація" було розміщено розроблені в рамках проєктів міжнародної технічної допомоги інфографіки, що роз’яснюють положення Виборчого кодексу України, зокрема щодо виборчих систем, за якими проводяться місцеві вибори, їх територіальної організації виборів, тощо. Також було створено YouTube-канал "ЦВК: просвіта".На YouTube-каналі було розміщено, зокрема: – серія просвітніх матеріалів "ПРОстими словами" – 11 відео (загальний перегляд – майже 11 млн відвідувачів); – онлайн-курс "Просто про вибори" – 28 відео (загальний перегляд – майже 29 тис. відвідувачів); – онлайн-курс "Про місцеві вибори для виборців" – 12 відео (загальний перегляд – понад 133 тис. відвідувачів). Також із залученням проектів міжнародної технічної допомоги фіналізовано 6 із 13 модулів, розроблених для наповнення навчального онлайн-курсу "ПРО всеукраїнський референдум", та підготовлено проморолик до вказаного онлайн-курсу. З метою розроблення онлайн-курсу щодо питань гендерної рівності та розширення політичної залученості та представництва жінок у воєнний та післявоєнний період у рамках співпраці Комісії з Офісом Ради Європи в України, спільно, 16 листопада 2023 року проведено стратегічну сесію «Гендерно збалансована участь та представництво жінок і чоловіків у суспільно-політичних та виборчих процесах у післявоєнний період: потреби, виклики та необхідні заходи підтримки». У 2024 у рамках співпраці Комісії з Офісом Ради Європи в Україні відповідно до погодженого листом Комісії від 05 березня 2024 року № 21-26-662 проекту програми тривала розробка освітнього онлайн-курсу "Збалансоване представництво жінок та чоловіків у політичних партіях та у виборчому процесі". Також у вересні: - опубліковано спільний медіапроект Комісії та видання The Village Україна за підтримки Міжнародної фундації виборчих систем в Україні "Не ридать, а здобувать": чому люди обирають боротися за Україну" про історії українців, чий вибір змінив їхнє і не тільки життя; - на офіційному вебсайті Комісії та сторінці у соціальній мережі "Фейсбук" розміщено два анімовані ролики, створені НАЗК з метою підвищення обізнаності громадян про ефективні інструменти громадського контролю. Також, у березні 2024 року Комісією опубліковано в інтернет-виданні "Українська правда" колонку "Що не так з виборами на росії", у якій йдеться, зокрема, про проведення "виборів" на тимчасово окупованих територіях України та порушення усіх стандартів, притаманних демократичному суспільству. У 2025 році у рамках співпраці з Офісом Ради Європи в Україні було розроблено просвітницький онлайн-курс "Збалансоване представництво жінок та чоловіків у політичних партіях та у виборчому процесі", який, зокрема, присвячений ролі виборів у демократичному суспільстві та важливості участі у виборах. Таким чином, зважаючи на ступінь відповідності фактично вжитих дій вимогам ДАП щодо змісту та способу виконання заходу, вважаємо за можливе констатувати, що захід є виконаним повністю. | Implemented | 0.0
1.2 | Instilling a negative attitude towards corruption | 1.2.1 Everyday corrupt practices are an established norm of conduct and are not perceived as violations of moral or legal norms. There is no consistent demand from the population for public officials to uphold the prescribed rules of ethical conduct and integrity | 1.2.1.6 | The level of awareness of citizens who realize the importance of standards of integrity and ethical conduct of public servants has increased owing to active and systematic communications, awareness-raising and training activities integrated into formal and informal education | 1.2.1.6.4 | Ensuring regular communications and awareness raising events devoted to the role of elections in a democratic society, the importance of voting, and the monitoring of the conduct of elected officials (with the possible involvement of NGOs and international technical assistance projects in the implementation of this activity) | 01.03.2023 | 31.12.2025 | The Central Election Commission of Ukraine |  | state budget and/or international technical assistance funds | within the established budget allocations for the relevant year and/or international technical assistance funds | Communications and awareness raising events are held on a regular basis. | Протягом 2023, 2024 та 2025 років забезпечувалося проведення регулярних інформаційно-просвітницьких заходів, присвячених ролі виборів у демократичному суспільстві, важливості участі у виборах. У 2023 у рамках виконання проектів міжнародної технічної допомоги Центральною виборчою комісією (далі - Комісія) було проведено низку інформаційно-просвітницьких заходів, а саме: – тренінг за методологією BRIDGE на тему "Виборчі системи" (15 – 17 березня 2023 року); – практичний семінар на тему "Інструменти цифрової трансформації повоєнних виборів в Україні (30 та 31 березня 2023 року)"; – тренінг за методологією BRIDGЕ на тему "Політичне фінансування" (25 – 27 квітня 2023 року); – онлайн семінар на тему "Недискримінація, інклюзивність та ґендерна рівність, як важлива складова післявоєнного відновлення та сталого демократичного врядування України" (20, 21 квітня та 20, 21 червня 2023 року); – панельна дискусія "Стійка демократія для успішної відбудови України" (15 – 17 травня 2023 року); – тренінг модуля 1 "Основи адміністрування виборів та навчання дорослих" (20 – 27 червня 2023 року). Крім того, у період з 01 березня до 31 травня 2023 року у Секретаріаті Комісії проходили стажування студенти закладів вищої освіти – випускники курсу IFES з громадянської освіти "Демократія: від теорії до практики". У період з 02 – 04 вересня 2023 року проведено тренінг за методологією BRIDGЕ на тему "Виборчі системи". У 2024 з метою формування виборчої культури "молодих виборців" Комісією у співпраці з Міжнародною фундацією виборчих систем в Україні розпочато роботу спрямовану на проведення конкурсу на виборчу тематику для "молодих виборців" (серед представників студентської молоді). З метою його здійснення розпорядженням Голови Комісії від 17 травня 2024 року № 28 утворено організаційний комітет з підготовки та проведення відповідного конкурсу. Організаційним комітетом на засіданні схвалено умови проведення відповідного конкурсу (протокол засідання від 24 травня 2024 року № 1), які 31 травня 2024 року розміщено на офіційному вебсайті Комісії у підрозділі "Конкурс творчих робіт" розділу "Для громадськості" за посиланням на сторінку "2024". Крім того, 31 травня 2024 року оголошено про проведення конкурсу на офіційному вебсайті Комісії, а також на сторінках у соціальних мережах "Facebook" та "Instagram". Організаційним комітетом у період з 01 червня до 30 вересня 2024 року забезпечено приймання творчих робіт від їх авторів та перевірку відповідності цих робіт умовам проведення конкурсу. З метою здійснення оцінювання творчих робіт, підбиття підсумків та визначення переможців конкурсу розпорядженням Голови Комісії від 17 вересня 2024 року № 56 утворено конкурсне журі з оцінки творчих робіт, поданих на відповідний конкурс до складу якого увійшли представники Комісії, Міжнародної фундації виборчих систем в Україні та закладів вищої освіти України. 01 жовтня 2024 року організаційним комітетом було розглянуто питання щодо відповідності поданих творчих робіт від їх авторів умовам проведення конкурсу (протокол засідання від 24 травня 2024 року № 1) та прийнято рішення щодо відповідності умовам конкурсу всіх робіт та їх передачу конкурсному журі для оцінки та визначення переможців. Конкурсним журі 28 листопада 2024 року визначено переможців конкурсу, а також оприлюднено інформацію про переможців та їх творчі роботи на офіційному вебсайті Комісії. 12 – 14 березня 2024 року проведено – тренінг за методологією BRIDGE "Виборчі системи". 25 квітня 2024 року проведено онлайн-семінар "Недискримінація, інклюзивність та гендерна рівність як важлива складова післявоєнного відновлення та сталого демократичного врядування України". У період з 01 березня до 31 травня 2024 року в Комісії відбулося стажування чотирьох студентів закладів вищої освіти – випускників курсів IFES. Комісією 13 листопада 2024 року проведено круглий стіл на тему "Важливість участі молоді у виборах для функціонування та розвитку демократичного суспільства", на якому висвітлювалися питання, присвячені ролі виборів у демократичному суспільстві та важливості участі в них, зокрема молоді. Протягом 2025 року у Комісії з метою формування виборчої культури молодих виборців проводиться конкурс на виборчу тематику серед молоді. Організаційним комітетом у період з 28 лютого до 31 липня 2025 року забезпечено приймання творчих робіт від їх авторів та перевірку відповідності цих робіт умовам проведення конкурсу. З метою здійснення оцінювання творчих робіт та визначення переможців конкурсу розпорядженням Голови Комісії від 22 липня 2025 року № 38 утворено конкурсне журі з оцінки творчих робіт, поданих на відповідний конкурс, до складу якого увійшли представники Комісії та закладів вищої освіти України. 01 серпня 2025 року на засіданні організаційного комітету було розглянуто питання щодо відповідності поданих творчих робіт умовам проведення конкурсу. Прийнято рішення про відповідність 60 із 61 роботи умовам проведення конкурсу та про передачу творчих робіт на розгляд конкурсному журі для їх оцінки та визначення переможців конкурсу. Конкурсним журі з оцінки творчих робіт, поданих на конкурс, оцінено творчі роботи та на його засіданні, яке відбулось 18 листопада 2025 року, визначено переможців конкурсу, що зафіксовано у протоколі засідання конкурсного журі. Інформацію про переможців оприлюднено на офіційному вебсайті Комісії. Із серпня до листопада 2025 року у Секретаріаті Комісії проходила стажування студентка Інституту журналістики Національного університету біоресурсів і природокористування України, з вересня до листопада 2025 року - студент Державного університету інфраструктури та технологій. Також Комісія долучилася до тижня доброчесності, який тривав в Україні з 1 до 10 грудня – щорічного навчально-просвітницького проєкту Офісу доброчесності НАЗК. У межах цієї ініціативи на сторінці Комісії у соціальній мережі "Фейсбук" опубліковано посилання на фільм "Після ери мовчання". Крім цього, у партнерстві з Міжнародною фундацією виборчих систем (IFES), Міжнародним інститутом демократії та сприяння виборів (IDEA), Бюро з демократичних інститутів і прав людини (БДІПЛ) ОБСЄ Комісія організувала інклюзивний експертний діалог "На шляху до ЄС: огляд рекомендацій БДІПЛ ОБСЄ щодо виборів в Україні", який відбувся 15 грудня 2025 року. Таким чином, зважаючи на ступінь відповідності фактично вжитих дій вимогам ДАП щодо змісту та способу виконання заходу, вважаємо за можливе констатувати, що захід є виконаним повністю. | Implemented | 0.0
1.2 | Instilling a negative attitude towards corruption | 1.2.1 Everyday corrupt practices are an established norm of conduct and are not perceived as violations of moral or legal norms. There is no consistent demand from the population for public officials to uphold the prescribed rules of ethical conduct and integrity | 1.2.1.6 | The level of awareness of citizens who realize the importance of standards of integrity and ethical conduct of public servants has increased owing to active and systematic communications, awareness-raising and training activities integrated into formal and informal education | 1.2.1.6.7 | Developing educational and methodological materials with elements of simulation and gamification devoted to the role of elections in a democratic society, the importance of voting, the activities of school self-government and parliament, for extracurricular classes as part of the educational process at institutions of general secondary and vocational secondary education (with the possible involvement of NGOs and international technical assistance projects in this activity) | 01.01.2025 | 31.12.2025 | National Agency on Corruption Prevention |  | state budget and/or international technical assistance funds | within the established budget allocations for the relevant year | The teaching methods materials have been developed, published, and disseminated among the concerned parties. | За інформацією Управління просвітницької роботи та навчальних програм апарату Національного агентства з питань запобігання корупції, у звітному періоді було забезпечено розроблення комплексу освітньо-методичних матеріалів з інтерактивними підходами до формування громадянських компетентностей, що включають елементи симуляції та ігровізації. Зокрема, створено настільну гру «Вибір є!», яка моделює процес прийняття рішень на виборах; квест «Місія: вибори», що занурює учнів у реалістичну ситуацію виборчого процесу. Також розроблено цифрову освітню гру: «Вибори: навчайся і практикуй». Матеріали поширено серед закладів освіти та розміщено на навчальній платформі Study.NAZK. Інформацію про зазначені ігрові та освітньо-методичні матеріали також включено до Методичних рекомендацій щодо організації і проведення Тижня доброчесності – 2025 у закладах загальної середньої освіти та професійної, фахової передвищої освіти, які надіслано листами до Міністерства освіти і науки України та до обласних та міських департаментів освіти з метою подальшого поширення та розповсюдження серед закладів освіти. Таким чином, зважаючи на ступінь відповідності фактично вжитих дій вимогам ДАП щодо змісту та способу виконання заходу, вважаємо за можливе констатувати, що захід є виконаним повністю. | Implemented | 0.0
1.2 | Instilling a negative attitude towards corruption | 1.2.1 Everyday corrupt practices are an established norm of conduct and are not perceived as violations of moral or legal norms. There is no consistent demand from the population for public officials to uphold the prescribed rules of ethical conduct and integrity | 1.2.1.6 | The level of awareness of citizens who realize the importance of standards of integrity and ethical conduct of public servants has increased owing to active and systematic communications, awareness-raising and training activities integrated into formal and informal education | 1.2.1.6.8 | Developing educational and methodological materials with elements of simulation and gamification devoted to policy making and interactions between civil servants and stakeholders, for extracurricular classes as part of the educational process at institutions of vocational secondary education (with the possible involvement of NGOs and international technical assistance projects in this activity) | 01.07.2025 | 31.12.2025 | National Agency on Corruption Prevention |  | state budget and/or international technical assistance funds | within the established budget allocations for the relevant year | The teaching methods materials have been developed, published, and disseminated among the concerned parties. | За інформацією Управління просвітницької роботи та навчальних програм апарату Національного агентства з питань запобігання корупції, забезпечено розроблення комплексу освітньо-методичних матеріалів з інтерактивними підходами до формування громадянських компетентностей, що включають елементи симуляції та ігровізації. Матеріали орієнтовано на позакласну діяльність у закладах профільної середньої освіти та спрямовано на розвиток навичок взаємодії між учнями як потенційними майбутніми публічними службовцями та заінтересованими сторонами. У межах зазначеної роботи розроблено тренінг «Я і держава: як правильно звертатися до державних органів», спрямований на формування правосвідомості та практичних навичок комунікації з органами публічної влади. Тренінг поширено серед закладів освіти в межах пілотного проєкту «Прозора професійна освіта» та розміщено на навчальній платформі Study.NAZK. Крім того, розроблено цифрову освітню гру «Служба у дії», яка забезпечує інтерактивне ознайомлення з принципами державного управління та стандартами доброчесності. Гру розміщено на навчальній платформі Study.NAZK. Інформацію про зазначені ігрові та освітньо-методичні матеріали також включено до Методичних рекомендацій щодо організації і проведення Тижня доброчесності – 2025 у закладах загальної середньої освіти та професійної, фахової передвищої освіти, які надіслано листами до Міністерства освіти і науки України та до обласних та міських департаментів освіти з метою подальшого поширення та розповсюдження серед закладів освіти. Таким чином, зважаючи на ступінь відповідності фактично вжитих дій вимогам ДАП щодо змісту та способу виконання заходу, вважаємо за можливе констатувати, що захід є виконаним повністю. | Implemented | 0.0